## Non-IS16444 Pilots
A. Smart Consumer Metering [Non IS16444 Certified (but standard functionality compliant) Smart Meter Projects]
Sl. | Nodal Agency | Name of State / UT | Name of DISCOM | Name of Scheme (RDSS / Non-RDSS*) | Sanctioned Quantity (Nos.) | Awarded Quantity (Nos.) | Deployment Commencement (Month and Year) | Achievement (Nos.)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1 | NSGM | Assam | APDCL | IPDS (SG Pilots) | 14519 | 14519 | March 2017 | 14519
2 | NSGM | Haryana | UHBVNL | IPDS (SG Pilots) | 10188 | 10188 | June 2017 | 10188
3 | NSGM | Haryana | SGKC Lab | IPDS (SG Pilots) | 10 | 10 | November 2017 | 10
4 | NSGM | Himachal Pradesh | HPSEBL | IPDS (SG Pilots) | 1335 | 1335 | October 2015 | 1335
5 | NSGM | Karnataka | CESC | IPDS (SG Pilots) | 21874 | 21874 | July 2015 | 21874
6 | NSGM | Puducherry | PED | IPDS (SG Pilots) | 28910 | 28910 | January 2018 | 28910
7 | Utility | Puducherry | PED | Utility Owned (Test Pilot) | 1658 | 1658 | April 2013 | 1658
8 | Utility | Rajasthan | AVVNL | Utility Owned (Test Pilot) | 1000 | 1000 | June 2016 | 1000
9 | NSGM | Tripura | TSECL | IPDS (SG Pilots) | 43081 | 43081 | July 2016 | 43081
10 | NSGM | Uttar Pradesh | IITK | IPDS (SG Pilots) | 28 | 28 | January 2017 | 28
11 | NSGM | West Bengal | WBSEDCL | IPDS (SG Pilots) | 5164 | 5164 | April 2018 | 5164
|  |  |  | Total | 127767 | 127767 |  | 127767

## Macro Sheet Weekly Installation (hidden)
Dashboard for Smart Metering Works Implementation (For Monitoring by MOP)
Reporting Month |  | #REF!
Progress as on Date |  | 2023-09-08
A. Smart Consumer Metering
| Name of Nodal Agency (REC / PFC) | Name of State / UT | Name of DISCOM | Name of Scheme (RDSS / Non-RDSS*) | Cumulative Smart Consumer metering installation till | Achievement | Cumulative Smart Consumer metering installation till | Achievement | Cumulative Smart Consumer metering installation till | Achievement | Cumulative Smart Consumer metering installation till | Achievement | Cumulative Smart Consumer metering installation till | Achievement | Cumulative Smart Consumer metering installation till | Achievement | Cumulative Smart Consumer metering installation till | Achievement | Cumulative Smart Consumer metering installation till | Achievement | Cumulative Smart metering installation till
[5 empty] | 2023-09-08 |  | 2023-08-25 |  | 2023-08-11 |  | 2023-07-28 |  | 2023-07-14 |  | 2023-06-30 |  | 2023-09-08 |  | 2023-06-02 |  | 2023-05-26
1 | 2 | 3 | 4 | 5
1 | PFC | Andhra Pradesh | APSPDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PFC | Andhra Pradesh | APCPDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PFC | Andhra Pradesh | APEPDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PFC | Uttarakhand | UPCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | PFC | Gujarat | DGVCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | PFC | Gujarat | MGVCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | PFC | Gujarat | PGVCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | PFC | Gujarat | UGVCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | PFC | Haryana | DHBVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | PFC | Haryana | UHBVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | PFC | Himachal Pradesh | HPSEBL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | PFC | Jharkhand | JBVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | PFC | Kerala | KSEBL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | PFC | Kerala | TCED | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | PFC | Madhya Pradesh | MP East​ | RDSS | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | PFC | Madhya Pradesh | MP Central​ | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | PFC | Madhya Pradesh | MP West​ | RDSS | 58238 | 5748 | 52490 | 4388 | 48102 | 5400 | 42702 | 6398 | 36304 | 2827 | 33477 | 4856 | 28621 | 2122 | 26499 | 52 | 26447
18 | PFC | Maharashtra | MSEDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | PFC | Maharashtra | BEST | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | PFC | Puducherry | PED | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | PFC | Punjab | PSPCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | REC | Andaman and Nicobar | EDANI | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | REC | Arunachal Pradesh | Arunachal PD | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | REC | Assam | APDCL | RDSS | 387030 | 21423 | 365607 | 0 | 365607 | 40778 | 324829 | 3541 | 321288 | 26528 | 294760 | 6943 | 287817 | 16063 | 271754 | 5326 | 266428
25 | REC | Bihar | NBPDCL | RDSS | 639191 | 288 | 638903 | 9298 | 629605 | 4216 | 625389 | 7678 | 617711 | 1582 | 616129 | 12234 | 603895 | 8709 | 595186 | 0 | 595186
26 | REC | Bihar | SBPDCL | RDSS | 837618 | 0 | 837618 | 15090 | 822528 | 13169 | 809359 | 0 | 809359 | 7078 | 802281 | 9184 | 793097 | 29301 | 763796 | 0 | 763796
27 | REC | Chhattisgarh | CSPDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | REC | Goa | Goa PD | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | REC | Jammu and Kashmir | JPDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | REC | Jammu and Kashmir | KPDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | REC | Karnataka | - | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | REC | Ladakh | Ladakh PD | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | REC | Manipur | MSPDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | REC | Meghalaya | MePDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | REC | Mizoram | Mizoram PD | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | REC | Nagaland | Nagaland PD | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | REC | Rajasthan | AVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | REC | Rajasthan | JdVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | REC | Rajasthan | JVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | REC | Sikkim | Sikkim PD | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | REC | Tamil Nadu | TANGEDCO | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | REC | Tripura | TSECL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | REC | Uttar Pradesh | DVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | REC | Uttar Pradesh | KESCO | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | REC | Uttar Pradesh | MVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | REC | Uttar Pradesh | PVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | REC | Uttar Pradesh | PuVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | REC | West Bengal | WBSEDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Sub-Total (RDSS) | 1922125 | 27507 | 1894618 | 28776 | 1865842 | 63563 | 1802279 | 17617 | 1784662 | 38015 | 1746647 | 33217 | 1713430 | 56195 | 1657235 | 5378 | 1651857
1 | EESL | Andaman and Nicobar | EDANI | IPDS | 36800 | 0 | 36800 | 0 | 36800 | 0 | 36800 | 0 | 36800 | 0 | 36800 | 0 | 36800 | 0 | 36800 | 0 | 36800
2 | REC | Andaman and Nicobar | EDANI | DDUGJY | 38400 | 0 | 38400 | 0 | 38400 | 0 | 38400 | 0 | 38400 | 0 | 38400 | 0 | 38400 | 0 | 38400 | 0 | 38400
3 | Utility | Andhra Pradesh | APEPDCL | Utility Owned | 2000 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 2000
4 | Utility | Assam | APDCL | Utility Owned | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000
5 | NSGM | Assam | APDCL | IPDS (SG Pilots) | 14519 | 0 | 14519 | 0 | 14519 | 0 | 14519 | 0 | 14519 | 0 | 14519 | 0 | 14519 | 0 | 14519 | 0 | 14519
6 | Utility | Assam | APDCL | Utility Owned | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000
7 | Utility | Assam | APDCL | Utility Owned | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000
8 | Utility | Assam | APDCL | Utility Owned | 2262 | 0 | 2262 | 0 | 2262 | 0 | 2262 | 0 | 2262 | 0 | 2262 | 0 | 2262 | 0 | 2262 | 0 | 2262
9 | EESL | Bihar | NBPDCL | Utility Owned | 263987 | 3615 | 260372 | 34059 | 226313 | 37039 | 189274 | 48934 | 140340 | 0 | 140340 | 20257 | 120083 | 18092 | 101991 | 0 | 101991
10 | EESL | Bihar | SBPDCL | Utility Owned | 66359 | 0 | 66359 | 8828 | 57531 | 15622 | 41909 | 0 | 41909 | 4926 | 36983 | 2922 | 34061 | 7667 | 26394 | 0 | 26394
11 | Utility | Bihar | SBPDCL | Utility Owned | 40500 | 0 | 40500 | 0 | 40500 | 0 | 40500 | 0 | 40500 | 0 | 40500 | 0 | 40500 | 0 | 40500 | 0 | 40500
12 | Utility | Bihar | IPCL | Utility Owned | 17100 | 0 | 17100 | 0 | 17100 | 0 | 17100 | 0 | 17100 | 0 | 17100 | 0 | 17100 | 0 | 17100 | 0 | 17100
13 | Utility | Bihar | BEDCPL | Utility Owned | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000
14 | NSGM | Chandigarh | CED | NSGM | 24214 | 0 | 24214 | 0 | 24214 | 0 | 24214 | 0 | 24214 | 0 | 24214 | 0 | 24214 | 0 | 24214 | 0 | 24214
15 | EESL | Delhi | NDMC | Utility Owned | 65000 | 0 | 65000 | 0 | 65000 | 0 | 65000 | 0 | 65000 | -59 | 65059 | 0 | 65059 | 0 | 65059 | 0 | 65059
16 | Utility | Delhi | TPDDL | Utility Owned | 195000 | 0 | 195000 | 0 | 195000 | 0 | 195000 | 0 | 195000 | 0 | 195000 | 0 | 195000 | 0 | 195000 | 0 | 195000
17 | NSGM | Gujarat | UGVCL | IPDS (SG Pilots) | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760
18 | NSGM | Haryana | UHBVNL | IPDS (SG Pilots) | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188
19 | NSGM | Haryana | SGKC Lab | IPDS (SG Pilots) | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10
20 | EESL | Haryana | DHBVNL | Utility Owned | 273001 | 10100 | 262901 | 1323 | 261578 | 4606 | 256972 | 1379 | 255593 | 1140 | 254453 | 2220 | 252233 | 1704 | 250529 | 847 | 249682
21 | EESL | Haryana | UHBVNL | Utility Owned | 451223 | 1640 | 449583 | 5927 | 443656 | 2266 | 441390 | 3091 | 438299 | 4039 | 434260 | 4476 | 429784 | 7784 | 422000 | 2205 | 419795
22 | NSGM | Himachal Pradesh | HPSEBL | IPDS (SG Pilots) | 1335 | 0 | 1335 | 0 | 1335 | 0 | 1335 | 0 | 1335 | 0 | 1335 | 0 | 1335 | 0 | 1335 | 0 | 1335
23 | PFCCL | Himachal Pradesh | HPSEBL | IPDS | 75712 | 0 | 75712 | 0 | 75712 | 0 | 75712 | 0 | 75712 | 0 | 75712 | 0 | 75712 | 0 | 75712 | 0 | 75712
24 | PFCCL | Himachal Pradesh | HPSEBL | Utility Owned | 76028 | 0 | 76028 | 0 | 76028 | 0 | 76028 | 0 | 76028 | 0 | 76028 | 0 | 76028 | 0 | 76028 | 725 | 75303
25 | REC | Jammu and Kashmir | JPDCL | PMDP-Phase-I | 66015 | 0 | 66015 | 0 | 66015 | 0 | 66015 | 0 | 66015 | 0 | 66015 | 0 | 66015 | 0 | 66015 | 0 | 66015
26 | REC | Jammu and Kashmir | JPDCL | PMDP-Phase-II | 118901 | 192 | 118709 | 1714 | 116995 | 9134 | 107861 | 15241 | 92620 | 486 | 92134 | 12284 | 79850 | 10380 | 69470 | 5102 | 64368
27 | REC | Jammu and Kashmir | KPDCL | PMDP-Phase-I | 58651 | 0 | 58651 | 0 | 58651 | 0 | 58651 | 0 | 58651 | 0 | 58651 | 0 | 58651 | 0 | 58651 | 0 | 58651
28 | REC | Jammu and Kashmir | KPDCL | PMDP-Phase-II | 126627 | 3335 | 123292 | 9290 | 114002 | 32435 | 81567 | 0 | 81567 | 14349 | 67218 | 0 | 67218 | 12129 | 55089 | 3243 | 51846
29 | NSGM | Karnataka | CESC | IPDS (SG Pilots) | 21874 | 0 | 21874 | 0 | 21874 | 0 | 21874 | 0 | 21874 | 0 | 21874 | 0 | 21874 | 0 | 21874 | 0 | 21874
30 | PFC | Kerala | CPT | IPDS ST&D | 805 | 0 | 805 | 0 | 805 | 0 | 805 | 0 | 805 | 0 | 805 | 0 | 805 | 0 | 805 | 0 | 805
31 | REC | Ladakh | Ladakh PD | SDP | 3279 | 0 | 3279 | 0 | 3279 | 2351 | 928 | 928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | PFC | Madhya Pradesh | MP-West | IPDS | 124477 | 0 | 124477 | 0 | 124477 | 0 | 124477 | 0 | 124477 | 0 | 124477 | 0 | 124477 | 0 | 124477 | 0 | 124477
33 | Utility | Madhya Pradesh | MP-West | Utility Owned | 104827 | 332 | 104495 | 14 | 104481 | 1179 | 103302 | 1708 | 101594 | 3468 | 98126 | 5667 | 92459 | 575 | 91884 | 398 | 91486
34 | PFC | Madhya Pradesh | MP-West | IPDS ST&D | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836
35 | Utility | Mizoram | Mizoram PD | Utility Owned | 656 | 0 | 656 | 0 | 656 | 0 | 656 | 0 | 656 | 0 | 656 | 656 | 0 | 0 | 0 | 0 | 0
36 | Utility | Odisha | OPTCL | Utility Owned | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000
37 | Utility | Odisha | PPT | Utility Owned | 500 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 500
38 | NSGM | Puducherry | PED | IPDS (SG Pilots) | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910
39 | Utility | Puducherry | PED | Utility Owned | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658
40 | PFC | Punjab | PSPCL | IPDS | 88107 | 0 | 88107 | 0 | 88107 | 0 | 88107 | 0 | 88107 | 0 | 88107 | 0 | 88107 | 0 | 88107 | 0 | 88107
41 | Utility | Punjab | PSPCL | Utility Owned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | Utility | Punjab | PSPCL | Utility Owned | 296743 | 0 | 296743 | 0 | 296743 | 10650 | 286093 | 0 | 286093 | 0 | 286093 | 0 | 286093 | 0 | 286093 | 0 | 286093
43 | EESL | Rajasthan | AVVNL | IPDS | 68673 | 0 | 68673 | 0 | 68673 | 0 | 68673 | 0 | 68673 | 0 | 68673 | 0 | 68673 | 0 | 68673 | 0 | 68673
44 | Utility | Rajasthan | AVVNL | Utility Owned | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000
45 | EESL | Rajasthan | JVVNL | IPDS | 240820 | 0 | 240820 | 0 | 240820 | 0 | 240820 | 0 | 240820 | 0 | 240820 | 0 | 240820 | -32878 | 273698 | 0 | 273698
46 | EESL | Rajasthan | JVVNL | Utility Owned | 33444 | 0 | 33444 | 0 | 33444 | 1067 | 32377 | 0 | 32377 | -501 | 32878 | 0 | 32878 | 32878 | 0 | 0 | 0
47 | NSGM | Rajasthan | JVVNL | NSGM | 143114 | 0 | 143114 | 0 | 143114 | 5312 | 137802 | 0 | 137802 | 2182 | 135620 | 0 | 135620 | 0 | 135620 | 0 | 135620
48 | Utility | Rajasthan | JVVNL | Utility Owned | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000
49 | EESL | Rajasthan | JdVVNL | IPDS | 56027 | 0 | 56027 | 0 | 56027 | 0 | 56027 | 0 | 56027 | 0 | 56027 | 0 | 56027 | 0 | 56027 | 0 | 56027
50 | Utility | Tamil Nadu | TANGEDCO | Utility Owned | 126510 | 0 | 126510 | 0 | 126510 | 0 | 126510 | 0 | 126510 | 0 | 126510 | 0 | 126510 | 0 | 126510 | 0 | 126510
51 | NSGM | Telangana | TSSPDCL | IPDS (SG Pilots) | 8882 | 0 | 8882 | 0 | 8882 | 0 | 8882 | 0 | 8882 | 0 | 8882 | 0 | 8882 | 0 | 8882 | 0 | 8882
52 | NSGM | Tripura | TSECL | IPDS (SG Pilots) | 43081 | 0 | 43081 | 0 | 43081 | 0 | 43081 | 0 | 43081 | 0 | 43081 | 0 | 43081 | 0 | 43081 | 0 | 43081
53 | NSGM | Uttar Pradesh | IITK | IPDS (SG Pilots) | 28 | 0 | 28 | 0 | 28 | 0 | 28 | 0 | 28 | 0 | 28 | 0 | 28 | 0 | 28 | 0 | 28
54 | EESL | Uttar Pradesh | MVVNL | Utility Owned | 380731 | 0 | 380731 | 0 | 380731 | 0 | 380731 | 0 | 380731 | 0 | 380731 | 0 | 380731 | 0 | 380731 | 0 | 380731
55 | EESL | Uttar Pradesh | PVVNL | Utility Owned | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726
56 | EESL | Uttar Pradesh | DVVNL | Utility Owned | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991
57 | EESL | Uttar Pradesh | PuVVNL | Utility Owned | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433
58 | EESL | Uttar Pradesh | KESCO | Utility Owned | 138072 | 0 | 138072 | 0 | 138072 | 0 | 138072 | 0 | 138072 | 0 | 138072 | 0 | 138072 | 576 | 137496 | 0 | 137496
59 | NSGM | West Bengal | WBSEDCL | IPDS (SG Pilots) | 5164 | 0 | 5164 | 0 | 5164 | 0 | 5164 | 0 | 5164 | 0 | 5164 | 0 | 5164 | 0 | 5164 | 0 | 5164
60 | Utility | West Bengal | CESC | Utility Owned | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000
61 | REC | West Bengal | WBSEDCL | Utility Owned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Sub-Total (Non-RDSS) | 5174960 | 19214 | 5155746 | 61155 | 5094591 | 121661 | 4972930 | 71281 | 4901649 | 30030 | 4871619 | 48482 | 4823137 | 58907 | 4764230 | 12520 | 4751710
|  |  |  | Total (RDSS + Non-RDSS) | 7097085 | 46721 | 7050364 | 89931 | 6960433 | 185224 | 6775209 | 88898 | 6686311 | 68045 | 6618266 | 81699 | 6536567 | 115102 | 6421465 | 17898 | 6403567
B. DT Metering
| Name of Nodal Agency (REC / PFC) | Name of State / UT | Name of DISCOM | Name of Scheme (RDSS / Non-RDSS*) | Cumulative Smart DT metering installation till | Achievement | Cumulative Smart DT metering installation till | Achievement | Cumulative Smart DT metering installation till | Achievement | Cumulative Smart DT metering installation till | Achievement | Cumulative Smart DT metering installation till | Achievement | Cumulative Smart DT metering installation till | Achievement | Cumulative Smart DT metering installation till | Achievement | Cumulative Smart DT metering installation till | Achievement | Cumulative Smart DT metering installation till
[5 empty] | 2023-09-08 |  | 2023-09-08 |  | 2023-09-08 |  | 2023-09-08 |  | 2023-09-08 |  | 2023-09-08 |  | 2023-09-08 |  | 2023-06-02 |  | 2023-05-26
1 | 2 | 3 | 4 | 5 | [16 empty] | 6
1 | PFC | Andhra Pradesh | APSPDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PFC | Andhra Pradesh | APCPDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PFC | Andhra Pradesh | APEPDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PFC | Uttarakhand | UPCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | PFC | Gujarat | DGVCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | PFC | Gujarat | MGVCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | PFC | Gujarat | PGVCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | PFC | Gujarat | UGVCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | PFC | Haryana | DHBVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | PFC | Haryana | UHBVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | PFC | Himachal Pradesh | HPSEBL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | PFC | Jharkhand | JBVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | PFC | Kerala | KSEBL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | PFC | Kerala | TCED | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | PFC | Madhya Pradesh | MP-East​ | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | PFC | Madhya Pradesh | MP-Central​ | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | PFC | Madhya Pradesh | MP-West​ | RDSS | 380 | 67 | 313 | 164 | 149 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | PFC | Maharashtra | MSEDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | PFC | Maharashtra | BEST | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | PFC | Puducherry | PED | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | PFC | Punjab | PSPCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | REC | Andaman and Nicobar | EDANI | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | REC | Arunachal Pradesh | Arunachal PD | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | REC | Assam | APDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | REC | Bihar | NBPDCL | RDSS | 0 | 0 | 0 | -31 | 31 | 0 | 31 | 0 | 31 | -5486 | 5517 | 0 | 5517 | 2356 | 3161 | 0 | 3161
26 | REC | Bihar | SBPDCL | RDSS | 31 | 0 | 31 | -59 | 90 | 0 | 90 | 0 | 90 | 0 | 90 | 14 | 76 | -9190 | 9266 | 0 | 9266
27 | REC | Chhattisgarh | CSPDCL | RDSS | 95 | 0 | 95 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | REC | Goa | Goa PD | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | REC | Jammu and Kashmir | JPDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | REC | Jammu and Kashmir | KPDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | REC | Karnataka | - | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | REC | Ladakh | Ladakh PD | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | REC | Manipur | MSPDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | REC | Meghalaya | MePDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | REC | Mizoram | Mizoram PD | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | REC | Nagaland | Nagaland PD | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | REC | Rajasthan | AVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | REC | Rajasthan | JdVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | REC | Rajasthan | JVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | REC | Sikkim | Sikkim PD | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | REC | Tamil Nadu | TANGEDCO | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | REC | Tripura | TSECL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | REC | Uttar Pradesh | DVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | REC | Uttar Pradesh | KESCO | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | REC | Uttar Pradesh | MVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | REC | Uttar Pradesh | PVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | REC | Uttar Pradesh | PuVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | REC | West Bengal | WBSEDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Sub-Total (RDSS) | 0 | 0 | 0 | -270 | 270 | 149 | 121 | 0 | 121 | -5486 | 5607 | 14 | 5593 | -6834 | 12427 | 0 | 12427
1 | REC | Assam | APDCL | Utility Owned | 506 | 67 | 439 | -1687 | 2126 | 0 | 2126 | 0 | 2126 | 0 | 2126 | 0 | 2126 | 0 | 2126 | 953 | 1173
2 | REC | Ladakh | Ladakh PD | SDP | 2126 | 0 | 2126 | 2126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | REC | Tamil Nadu | TANGEDCO | Utility Owned | 0 | 0 | 0 | -1210 | 1210 | 0 | 1210 | 0 | 1210 | 0 | 1210 | 0 | 1210 | 0 | 1210 | 0 | 1210
4 | REC | Jammu | JPDCL | PMDP | 1210 | 0 | 1210 | 1210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | REC | Kashmir | KPDCL | PMDP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Sub-Total (Non-RDSS) | 0 | 0 | 0 | -3336 | 3336 | 0 | 3336 | 0 | 3336 | 0 | 3336 | 0 | 3336 | 0 | 3336 | 953 | 2383
|  |  |  | Total (RDSS + Non-RDSS) | 3336 | 0 | 3336 | -270 | 3606 | 149 | 3457 | 0 | 3457 | -5486 | 8943 | 14 | 8929 | -6834 | 15763 | 953 | 14810
C. Feeder Metering
| Name of Nodal Agency (REC / PFC) | Name of State / UT | Name of DISCOM | Name of Scheme (RDSS / Non-RDSS*) | Cumulative Smart Feeder metering installation till | Achievement | Cumulative Smart Feeder metering installation till | Achievement | Cumulative Smart Feeder metering installation till | Achievement | Cumulative Smart Feeder metering installation till | Achievement | Cumulative Smart Feeder metering installation till | Achievement | Cumulative Smart Feeder metering installation till | Achievement | Cumulative Smart Feeder metering installation till | Achievement | Cumulative Smart Feeder metering installation till | Achievement | Cumulative Smart Feeder metering installation till
[5 empty] | 2023-09-08 |  | 2023-09-08 |  | 2023-09-08 |  | 2023-09-08 |  | 2023-09-08 |  | 2023-09-08 |  | 2023-09-08 |  | 2023-06-02 |  | 2023-05-26
1 | 2 | 3 | 4 | 5 | [16 empty] | 6
1 | PFC | Andhra Pradesh | APSPDCL | RDSS | 14 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PFC | Andhra Pradesh | APCPDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PFC | Andhra Pradesh | APEPDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PFC | Uttarakhand | UPCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | PFC | Haryana | DHBVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | PFC | Haryana | UHBVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | PFC | Himachal Pradesh | HPSEBL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | PFC | Jharkhand | JBVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | PFC | Kerala | KSEBL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | PFC | Kerala | TCED | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | PFC | Madhya Pradesh | MP-Central​ | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | PFC | Madhya Pradesh | MP-West​ | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | PFC | Maharashtra | MSEDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | PFC | Maharashtra | BEST | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | PFC | Puducherry | PED | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | PFC | Punjab | PSPCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | REC | Andaman and Nicobar | EDANI | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | REC | Arunachal Pradesh | Arunachal PD | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | REC | Assam | APDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | REC | Bihar | NBPDCL | RDSS | 0 | 0 | 0 | -205 | 205 | 0 | 205 | 0 | 205 | 0 | 205 | 0 | 205 | 0 | 205 | 0 | 205
21 | REC | Bihar | SBPDCL | RDSS | 0 | 0 | 0 | -21 | 21 | 0 | 21 | 0 | 21 | 0 | 21 | 0 | 21 | -2326 | 2347 | 0 | 2347
22 | REC | Chhattisgarh | CSPDCL | RDSS | 205 | 0 | 205 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | REC | Goa | Goa PD | RDSS | 28 | 0 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | REC | Jammu and Kashmir | JPDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | REC | Jammu and Kashmir | KPDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | REC | Karnataka | - | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | REC | Ladakh | Ladakh PD | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | REC | Manipur | MSPDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | REC | Meghalaya | MePDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | REC | Mizoram | Mizoram PD | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | REC | Nagaland | Nagaland PD | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | REC | Rajasthan | AVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | REC | Rajasthan | JdVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | REC | Rajasthan | JVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | REC | Sikkim | Sikkim PD | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | REC | Tamil Nadu | TANGEDCO | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | REC | Tripura | TSECL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | REC | Uttar Pradesh | DVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | REC | Uttar Pradesh | KESCO | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | REC | Uttar Pradesh | MVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | REC | Uttar Pradesh | PVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | REC | Uttar Pradesh | PuVVNL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | REC | West Bengal | WBSEDCL | RDSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Sub-Total (RDSS) | 0 | 0 | 0 | -226 | 226 | 0 | 226 | 0 | 226 | 0 | 226 | 0 | 226 | -2326 | 2552 | 0 | 2552
1 | REC | Ladakh | Ladakh PD | SDP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Sub-Total (Non-RDSS) | 233 | 0 | 233 | 233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total (RDSS + Non-RDSS) | 0 | 0 | 0 | -226 | 226 | 0 | 226 | 0 | 226 | 0 | 226 | 0 | 226 | -2326 | 2552 | 0 | 2552
* Non-RDSS - IPDS/ DDUGJY/ PMDP/ SG-Pilot/ NSGM/ Utility Owned/SDP

## WeeklyProgressMonitor (hidden)
Dashboard for Smart Metering Works Implementation (For Monitoring by MOP)
Reporting Month |  | #REF!
Progress as on Date |  | #REF!
A. Smart Consumer Metering
| Name of Nodal Agency (REC / PFC) | Name of State / UT | Name of DISCOM | Name of Scheme (RDSS / Non-RDSS*) |  |  | Last Week Total Awarded Scope - Cumulative Quantity (Nos.)
[5 empty] | TOTAL Sanctioned Till Last Week | Weekly Changes (+/-) in Sanctioned Quantity |  | Weekly Changes (+/-) in Awarded Quantity | Last Week Cumulative Achievement (Nos.) | Weekly Changes (+/-) in Cumulative Achievement | Last week Achievement - On Prepaid Mode (Nos.) | Weekly Changes (+/-) in Cumulative Achievement in Pre-paid
1 | 2 | 3 | 4 | 5 | 8 |  | 9 |  | 14 |  | 15
1 | PFC | Andhra Pradesh | APSPDCL | RDSS | 2302644 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
2 | PFC | Andhra Pradesh | APCPDCL | RDSS | 2050962 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
3 | PFC | Andhra Pradesh | APEPDCL | RDSS | 1255240 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
4 | PFC | Uttarakhand | UPCL | RDSS | 1584205 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
5 | PFC | Gujarat | DGVCL | RDSS | 4078120 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
6 | PFC | Gujarat | MGVCL | RDSS | 3299991 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
7 | PFC | Gujarat | PGVCL | RDSS | 5583509 | #REF! | 2257478 | #REF! | 0 | #REF! | 0 | #REF!
8 | PFC | Gujarat | UGVCL | RDSS | 3520251 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
9 | PFC | Haryana | DHBVNL | RDSS | 4165618 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
10 | PFC | Haryana | UHBVNL | RDSS | 3240000 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
11 | PFC | Himachal Pradesh | HPSEBL | RDSS | 2800945 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
12 | PFC | Jharkhand | JBVNL | RDSS | 1341306 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
13 | PFC | Kerala | KSEBL | RDSS | 13248923 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
14 | PFC | Kerala | TCED | RDSS | 40438 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
15 | PFC | Madhya Pradesh | MP East​ | RDSS | 5144451 | #REF! | 971306 | #REF! | 0 | #REF! | 0 | #REF!
16 | PFC | Madhya Pradesh | MP Central​ | RDSS | 3955918 | #REF! | 939527 | #REF! | 0 | #REF! | 0 | #REF!
17 | PFC | Madhya Pradesh | MP West​ | RDSS | 3879733 | #REF! | 374241 | #REF! | 26800 | #REF! | 0 | #REF!
18 | PFC | Maharashtra | MSEDCL | RDSS | 22488866 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
19 | PFC | Maharashtra | BEST | RDSS | 1075881 | #REF! | 1075890 | #REF! | 0 | #REF! | 0 | #REF!
20 | PFC | Puducherry | PED | RDSS | 403767 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
21 | PFC | Punjab | PSPCL | RDSS | 8784807 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
| Total PFC |  |  |  | 94245575 | #REF! | 5618442 | #REF! | 26800 | #REF! | 0 | #REF!
1 | REC | Assam | APDCL | RDSS | 5744698 | #REF! | 4954316 | #REF! | 225190 | #REF! | 0 | #REF!
2 | REC | Meghalaya | MePDCL | RDSS | 460000 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
3 | REC | Jammu and Kashmir | JPDCL | RDSS | 721346 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
4 | REC | Jammu and Kashmir | KPDCL | RDSS | 685699 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
5 | REC | Mizoram | Mizoram PD | RDSS | 289383 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
6 | REC | Uttar Pradesh | DVVNL | RDSS | 5354069 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
7 | REC | Uttar Pradesh | KESCO | RDSS | 625000 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
8 | REC | Uttar Pradesh | MVVNL | RDSS | 7528737 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
9 | REC | Uttar Pradesh | PVVNL | RDSS | 6143261 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
10 | REC | Uttar Pradesh | PuVVNL | RDSS | 7327988 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
11 | REC | Tamil Nadu | TANGEDCO | RDSS | 30000000 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
12 | REC | Bihar | NBPDCL | RDSS | 1030000 | #REF! | 1030000 | #REF! | 583950 | #REF! | 0 | #REF!
13 | REC | Bihar | SBPDCL | RDSS | 1320000 | #REF! | 1320000 | #REF! | 741950 | #REF! | 740608 | #REF!
14 | REC | Rajasthan | AVVNL | RDSS | 5432231 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
15 | REC | Rajasthan | JdVVNL | RDSS | 4080082 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
16 | REC | Rajasthan | JVVNL | RDSS | 4762643 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
17 | REC | Chhattisgarh | CSPDCL | RDSS | 5962115 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
18 | REC | Manipur | MSPDCL | RDSS | 154400 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
19 | REC | Tripura | TSECL | RDSS | 547489 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
20 | REC | Goa | Goa PD | RDSS | 741160 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
21 | REC | Sikkim | Sikkim PD | RDSS | 144680 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
22 | REC | Arunachal Pradesh | Arunachal PD | RDSS | 287445 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
23 | REC | Ladakh | Ladakh PD | RDSS | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
24 | REC | West Bengal | WBSEDCL | RDSS | 20717969 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
25 | REC | Karnataka | - | RDSS | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
26 | REC | Andaman and Nicobar | EDANI | RDSS | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
27 | REC | Nagaland | Nagaland PD | RDSS | 317210 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
| Total REC |  |  |  | 110377605 | #REF! | 7304316 | #REF! | 1551090 | #REF! | 740608 | #REF!
|  |  |  | Sub-Total (RDSS) | 204623180 | #REF! | 12922758 | #REF! | 1577890 | #REF! | 740608 | #REF!
1 | EESL | Andaman and Nicobar | EDANI | IPDS | 36800 | #REF! | 36800 | #REF! | 36800 | #REF! | 0 | #REF!
2 | EESL | Andaman and Nicobar | EDANI | Utility Owned | 28102 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
3 | REC | Andaman and Nicobar | EDANI | DDUGJY | 38400 | #REF! | 38400 | #REF! | 38400 | #REF! | 0 | #REF!
4 | Gram Power | Andhra Pradesh | EPDCL | Utility Owned | 2000 | #REF! | 2000 | #REF! | 2000 | #REF! | 0 | #REF!
5 | APDCL | Assam | APDCL | Utility Owned | 70000 | #REF! | 70000 | #REF! | 70000 | #REF! | 2720 | #REF!
6 | APDCL | Assam | APDCL | IPDS (SG Pilots) | 14259 | #REF! | 14259 | #REF! | 14259 | #REF! | 0 | #REF!
7 | APDCL | Assam | APDCL | Utility Owned | 134000 | #REF! | 134000 | #REF! | 134000 | #REF! | 7926 | #REF!
8 | APDCL | Assam | APDCL | Utility Owned | 134000 | #REF! | 134000 | #REF! | 134000 | #REF! | 9187 | #REF!
9 | APDCL | Assam | APDCL | Utility Owned | 363500 | #REF! | 363500 | #REF! | 120666 | #REF! | 102320 | #REF!
10 | APDCL | Assam | APDCL | Utility Owned | 256600 | #REF! | 256600 | #REF! | 106422 | #REF! | 55334 | #REF!
11 | EESL | Bihar | NBPDCL | Utility Owned | 1030000 | #REF! | 1030000 | #REF! | 582514 | #REF! | 581728 | #REF!
12 | EESL | Bihar | SBPDCL | Utility Owned | 1320000 | #REF! | 1320000 | #REF! | 753819 | #REF! | 753015 | #REF!
13 | Gram Power | Bihar | SBPDCL | Utility Owned | 40500 | #REF! | 40500 | #REF! | 30500 | #REF! | 30500 | #REF!
14 | Gram Power | Bihar | IPCL | Utility Owned | 17100 | #REF! | 17100 | #REF! | 17100 | #REF! | 17100 | #REF!
15 | Gram Power | Bihar | BEDCPL | Utility Owned | 1000 | #REF! | 1000 | #REF! | 1000 | #REF! | 1000 | #REF!
16 | RECPDCL | Chandigarh | CED | NSGM | 29433 | #REF! | 29433 | #REF! | 24214 | #REF! | 0 | #REF!
17 | EESL | Delhi | NDMC | Utility Owned | 64713 | #REF! | 64713 | #REF! | 65059 | #REF! | 0 | #REF!
18 | TPDDL | Delhi | TPDDL | Utility Owned | 195000 | #REF! | 195000 | #REF! | 195000 | #REF! | 0 | #REF!
19 | NSGM | Gujrat | UGVCL | IPDS (SG Pilots) | 23760 | #REF! | 23760 | #REF! | 23760 | #REF! | 0 | #REF!
20 | NSGM | Haryana | UHBVNL | IPDS (SG Pilots) | 10188 | #REF! | 10188 | #REF! | 10188 | #REF! | 0 | #REF!
21 | NSGM | Haryana | SGKC Lab | IPDS (SG Pilots) | 10 | #REF! | 10 | #REF! | 10 | #REF! | 0 | #REF!
22 | EESL | Haryana | DHBVNL | Utility Owned | 500000 | #REF! | 500000 | #REF! | 242521 | #REF! | 501 | #REF!
23 | EESL | Haryana | UHBVNL | Utility Owned | 500000 | #REF! | 500000 | #REF! | 405171 | #REF! | 958 | #REF!
24 | NSGM | Himachal Pradesh | HPSEBL | IPDS (SG Pilots) | 1335 | #REF! | 1335 | #REF! | 1335 | #REF! | 0 | #REF!
25 | PFCCL | Himachal Pradesh | HPSEBL | IPDS | 75712 | #REF! | 75712 | #REF! | 75712 | #REF! | 0 | #REF!
26 | PFCCL | Himachal Pradesh | HPSEBL | Utility Owned | 76028 | #REF! | 76028 | #REF! | 75303 | #REF! | 0 | #REF!
27 | RECPDCL | Jammu | JPDCL | PMDP | 127050 | #REF! | 127050 | #REF! | 124666 | #REF! | 0 | #REF!
28 | RECPDCL | Jammu | JPDCL | PMDP | 307766 | #REF! | 307766 | #REF! | 81228 | #REF! | 0 | #REF!
29 | RECPDCL | Jammu | JPDCL | PMDP | 250672 | #REF! | 250672 | #REF! | 8580 | #REF! | 0 | #REF!
30 | PFC | Karnaraka | CESC | IPDS (SG Pilots) | 20916 | #REF! | 20916 | #REF! | 20916 | #REF! | 0 | #REF!
31 | PFC | Kerala | CPT | IPDS ST&D | 805 | #REF! | 805 | #REF! | 805 | #REF! | 0 | #REF!
32 | PFC | Madhya Pradesh | MP-West | IPDS | 124477 | #REF! | 124477 | #REF! | 124477 | #REF! | 0 | #REF!
33 | MP Smart Grid | Madhya Pradesh | MP-West | Utility Owned | 225523 | #REF! | 225523 | #REF! | 0 | #REF! | 0 | #REF!
34 | PFC | Madhya Pradesh | MP-West | IPDS ST&D | 118836 | #REF! | 118836 | #REF! | 118836 | #REF! | 0 | #REF!
35 | OPTCL | Odisha | OPTCL | Utility Owned | 4000 | #REF! | 4000 | #REF! | 4000 | #REF! | 0 | #REF!
36 | Gram Power | Odisha | PPT | Utility Owned | 500 | #REF! | 500 | #REF! | 500 | #REF! | 0 | #REF!
37 | NSGM | Puducherry | PED | IPDS (SG Pilots) | 28910 | #REF! | 28910 | #REF! | 28910 | #REF! | 0 | #REF!
38 | PED | Puducherry | PED | Utility Owned | 1658 | #REF! | 1658 | #REF! | 1658 | #REF! | 0 | #REF!
39 | PFC | Punjab | PSPCL | IPDS | 88107 | #REF! | 88107 | #REF! | 88107 | #REF! | 0 | #REF!
40 | PSPCL | Punjab | PSPCL | Utility Owned | 7893 | #REF! | 7893 | #REF! | 0 | #REF! | 0 | #REF!
41 | EESL | Rajasthan | AVVNL | IPDS | 68673 | #REF! | 68673 | #REF! | 68673 | #REF! | 0 | #REF!
42 | EESL | Rajasthan | AVVNL | Utility Owned | 122149 | #REF! | 122149 | #REF! | 0 | #REF! | 0 | #REF!
43 | APDCL | Rajasthan | AVVNL | Utility Owned | 1000 | #REF! | 1000 | #REF! | 1000 | #REF! | 0 | #REF!
44 | EESL | Rajasthan | JaVVNL | IPDS | 240820 | #REF! | 240820 | #REF! | 240820 | #REF! | 0 | #REF!
45 | EESL | Rajasthan | JaVVNL | Utility Owned | 40980 | #REF! | 40980 | #REF! | 0 | #REF! | 0 | #REF!
46 | Genus | Rajasthan | JaVVNL | NSGM | 150000 | #REF! | 150000 | #REF! | 135444 | #REF! | 0 | #REF!
47 | Genus | Rajasthan | JaVVNL | Utility Owned | 70000 | #REF! | 70000 | #REF! | 70000 | #REF! | 0 | #REF!
48 | EESL | Rajasthan | JdVVNL | IPDS | 56027 | #REF! | 56027 | #REF! | 56027 | #REF! | 0 | #REF!
49 | EESL | Rajasthan | JdVVNL | Utility Owned | 46155 | #REF! | 46155 | #REF! | 0 | #REF! | 0 | #REF!
50 | Genus | Tamil Nadu | TANGEDCO | Utility Owned | 141000 | #REF! | 141000 | #REF! | 126510 | #REF! | 0 | #REF!
51 | NSGM | Telangana | TSSPDCL | IPDS (SG Pilots) | 8882 | #REF! | 8882 | #REF! | 8882 | #REF! | 0 | #REF!
52 | NSGM | Tripura | TSECL | IPDS (SG Pilots) | 43081 | #REF! | 43081 | #REF! | 43081 | #REF! | 0 | #REF!
53 | NSGM | Uttar Pradesh | IITK | IPDS (SG Pilots) | 28 | #REF! | 28 | #REF! | 28 | #REF! | 0 | #REF!
54 | EESL | Uttar Pradesh | MVVNL | Utility Owned | 905769 | #REF! | 905769 | #REF! | 380731 | #REF! | 3337 | #REF!
55 | EESL | Uttar Pradesh | PVVNL | Utility Owned | 1164138 | #REF! | 1164138 | #REF! | 198726 | #REF! | 20 | #REF!
56 | EESL | Uttar Pradesh | DVVNL | Utility Owned | 628686 | #REF! | 628686 | #REF! | 147991 | #REF! | 127 | #REF!
57 | EESL | Uttar Pradesh | PuVVNL | Utility Owned | 1147102 | #REF! | 1147102 | #REF! | 321433 | #REF! | 1135 | #REF!
58 | EESL | Uttar Pradesh | KESCO | Utility Owned | 156532 | #REF! | 156532 | #REF! | 134727 | #REF! | 98577 | #REF!
59 | NSGM | West Bengal | WBSEDCL | IPDS (SG Pilots) | 5164 | #REF! | 5164 | #REF! | 5164 | #REF! | 0 | #REF!
60 | CESC | West Bengal | CESC | Utility Owned | 10000 | #REF! | 10000 | #REF! | 10000 | #REF! | 0 | #REF!
|  |  |  | Sub-Total (Non-RDSS) | 11275739 | #REF! | 11247637 | #REF! | 5711673 | #REF! | 1665485 | #REF!
|  |  |  | Total (RDSS + Non-RDSS) | 215898919 | #REF! | 24170395 | #REF! | 7289563 | #REF! | 2406093 | #REF!
B. DT Metering
| Name of Nodal Agency (REC / PFC) | Name of State / UT | Name of DISCOM | Name of Scheme (RDSS / Non-RDSS*) |  |  | Awarded Scope - Cumulative Quantity (Nos.)
[5 empty] | TOTAL |  |  |  | Cumulative Achievement (Nos.)
1 | 2 | 3 | 4 | 5 | 8 |  | 9 |  | 14 |  | 15
1 | PFC | Andhra Pradesh | APSPDCL | RDSS | 102246 | #REF! | 0 | #REF! | 0 | #REF!
2 | PFC | Andhra Pradesh | APCPDCL | RDSS | 113650 | #REF! | 0 | #REF! | 0 | #REF!
3 | PFC | Andhra Pradesh | APEPDCL | RDSS | 77244 | #REF! | 0 | #REF! | 0 | #REF!
4 | PFC | Uttarakhand | UPCL | RDSS | 38016 | #REF! | 0 | #REF! | 0 | #REF!
5 | PFC | Gujarat | DGVCL | RDSS | 82336 | #REF! | 0 | #REF! | 0 | #REF!
6 | PFC | Gujarat | MGVCL | RDSS | 56129 | #REF! | 0 | #REF! | 0 | #REF!
7 | PFC | Gujarat | PGVCL | RDSS | 109130 | #REF! | 109130 | #REF! | 0 | #REF!
8 | PFC | Gujarat | UGVCL | RDSS | 52892 | #REF! | 0 | #REF! | 0 | #REF!
9 | PFC | Haryana | DHBVNL | RDSS | 128340 | #REF! | 0 | #REF! | 0 | #REF!
10 | PFC | Haryana | UHBVNL | RDSS | 66979 | #REF! | 0 | #REF! | 0 | #REF!
11 | PFC | Himachal Pradesh | HPSEBL | RDSS | 39012 | #REF! | 0 | #REF! | 0 | #REF!
12 | PFC | Jharkhand | JBVNL | RDSS | 19512 | #REF! | 0 | #REF! | 0 | #REF!
13 | PFC | Kerala | KSEBL | RDSS | 87168 | #REF! | 0 | #REF! | 0 | #REF!
14 | PFC | Kerala | TCED | RDSS | 447 | #REF! | 0 | #REF! | 0 | #REF!
15 | PFC | Madhya Pradesh | MP East​ | RDSS | 130721 | #REF! | 12229 | #REF! | 0 | #REF!
16 | PFC | Madhya Pradesh | MP Central​ | RDSS | 173746 | #REF! | 18231 | #REF! | 0 | #REF!
17 | PFC | Madhya Pradesh | MP West​ | RDSS | 102036 | #REF! | 5468 | #REF! | 0 | #REF!
18 | PFC | Maharashtra | MSEDCL | RDSS | 407507 | #REF! | 0 | #REF! | 0 | #REF!
19 | PFC | Maharashtra | BEST | RDSS | 3398 | #REF! | 3398 | #REF! | 0 | #REF!
20 | PFC | Puducherry | PED | RDSS | 3105 | #REF! | 0 | #REF! | 0 | #REF!
21 | PFC | Punjab | PSPCL | RDSS | 184044 | #REF! | 0 | #REF! | 0 | #REF!
22 | REC | Assam | APDCL | RDSS | 77547 | #REF! | 60187 | #REF! | 0 | #REF!
23 | REC | Meghalaya | MePDCL | RDSS | 11419 | #REF! | 0 | #REF! | 0 | #REF!
24 | REC | Jammu and Kashmir | JPDCL | RDSS | 47367 | #REF! | 0 | #REF! | 0 | #REF!
25 | REC | Jammu and Kashmir | KPDCL | RDSS | 40670 | #REF! | 0 | #REF! | 0 | #REF!
26 | REC | Mizoram | Mizoram PD | RDSS | 2300 | #REF! | 0 | #REF! | 0 | #REF!
27 | REC | Uttar Pradesh | DVVNL | RDSS | 187910 | #REF! | 0 | #REF! | 0 | #REF!
28 | REC | Uttar Pradesh | KESCO | RDSS | 6715 | #REF! | 0 | #REF! | 0 | #REF!
29 | REC | Uttar Pradesh | MVVNL | RDSS | 383158 | #REF! | 0 | #REF! | 0 | #REF!
30 | REC | Uttar Pradesh | PVVNL | RDSS | 531164 | #REF! | 0 | #REF! | 0 | #REF!
31 | REC | Uttar Pradesh | PuVVNL | RDSS | 417854 | #REF! | 0 | #REF! | 0 | #REF!
32 | REC | Tamil Nadu | TANGEDCO | RDSS | 472500 | #REF! | 0 | #REF! | 0 | #REF!
33 | REC | Bihar | NBPDCL | RDSS | 143683 | #REF! | 31000 | #REF! | 3161 | #REF!
34 | REC | Bihar | SBPDCL | RDSS | 107043 | #REF! | 21000 | #REF! | 8654 | #REF!
35 | REC | Rajasthan | AVVNL | RDSS | 155453 | #REF! | 0 | #REF! | 0 | #REF!
36 | REC | Rajasthan | JdVVNL | RDSS | 167809 | #REF! | 0 | #REF! | 0 | #REF!
37 | REC | Rajasthan | JVVNL | RDSS | 111346 | #REF! | 0 | #REF! | 0 | #REF!
38 | REC | Chhattisgarh | CSPDCL | RDSS | 210644 | #REF! | 0 | #REF! | 0 | #REF!
39 | REC | Manipur | MSPDCL | RDSS | 11451 | #REF! | 0 | #REF! | 0 | #REF!
40 | REC | Tripura | TSECL | RDSS | 14908 | #REF! | 0 | #REF! | 0 | #REF!
41 | REC | Goa | Goa PD | RDSS | 8369 | #REF! | 0 | #REF! | 0 | #REF!
42 | REC | Sikkim | Sikkim PD | RDSS | 3229 | #REF! | 0 | #REF! | 0 | #REF!
43 | REC | Arunachal Pradesh | Arunachal PD | RDSS | 10116 | #REF! | 0 | #REF! | 0 | #REF!
44 | REC | Ladakh | Ladakh PD | RDSS | 0 | #REF! | 0 | #REF! | 0 | #REF!
45 | REC | West Bengal | WBSEDCL | RDSS | 305419 | #REF! | 0 | #REF! | 0 | #REF!
46 | REC | Karnataka | - | RDSS | 0 | #REF! | 0 | #REF! | 0 | #REF!
47 | REC | Andaman and Nicobar | EDANI | RDSS | 0 | #REF! | 0 | #REF! | 0 | #REF!
48 | REC | Nagaland | Nagaland PD | RDSS | 6276 | #REF! | 0 | #REF! | 0 | #REF!
|  |  |  | Sub-Total (RDSS) | 5412008 | #REF! | 260643 | #REF! | 11815 | #REF!
1 | REC | Assam | APDCL | Utility Owned | 17000 | #REF! | 0 | #REF! | 1173 | #REF!
2 | REC | Ladakh | Ladakh PD | SDP | 1931 | #REF! | 0 | #REF! | 0 | #REF!
3 | REC | Tamil Nadu | TANGEDCO | Utility Owned | 1220 | #REF! | 0 | #REF! | 1210 | #REF!
|  |  |  | Sub-Total (Non-RDSS) | 20151 | #REF! | 0 | #REF! | 2383 | #REF!
|  |  |  | Total (RDSS + Non-RDSS) | 5432159 | #REF! | 260643 | #REF! | 14198 | #REF!
C. Feeder Metering
| Name of Nodal Agency (REC / PFC) | Name of State / UT | Name of DISCOM | Name of Scheme (RDSS / Non-RDSS*) |  |  | Awarded Scope - Cumulative Quantity (Nos.)
[5 empty] | TOTAL |  |  |  | Cumulative Achievement (Nos.)
1 | 2 | 3 | 4 | 5 | 8 | #REF! | 9 |  | 14
1 | PFC | Andhra Pradesh | APSPDCL | RDSS | 9741 | #REF! | 0 | #REF! | 0 | #REF!
2 | PFC | Andhra Pradesh | APCPDCL | RDSS | 3726 | #REF! | 0 | #REF! | 0 | #REF!
3 | PFC | Andhra Pradesh | APEPDCL | RDSS | 3891 | #REF! | 0 | #REF! | 0 | #REF!
4 | PFC | Uttarakhand | UPCL | RDSS | 1686 | #REF! | 0 | #REF! | 0 | #REF!
5 | PFC | Haryana | DHBVNL | RDSS | 6604 | #REF! | 0 | #REF! | 0 | #REF!
6 | PFC | Haryana | UHBVNL | RDSS | 6600 | #REF! | 0 | #REF! | 0 | #REF!
7 | PFC | Himachal Pradesh | HPSEBL | RDSS | 1951 | #REF! | 0 | #REF! | 0 | #REF!
8 | PFC | Jharkhand | JBVNL | RDSS | 1226 | #REF! | 0 | #REF! | 0 | #REF!
9 | PFC | Kerala | KSEBL | RDSS | 6003 | #REF! | 0 | #REF! | 0 | #REF!
10 | PFC | Kerala | TCED | RDSS | 22 | #REF! | 0 | #REF! | 0 | #REF!
11 | PFC | Madhya Pradesh | MP Central​ | RDSS | 6127 | #REF! | 0 | #REF! | 0 | #REF!
12 | PFC | Madhya Pradesh | MP West​ | RDSS | 2284 | #REF! | 0 | #REF! | 0 | #REF!
13 | PFC | Maharashtra | MSEDCL | RDSS | 27826 | #REF! | 0 | #REF! | 0 | #REF!
14 | PFC | Maharashtra | BEST | RDSS | 1388 | #REF! | 1388 | #REF! | 0 | #REF!
15 | PFC | Puducherry | PED | RDSS | 180 | #REF! | 0 | #REF! | 0 | #REF!
16 | PFC | Punjab | PSPCL | RDSS | 12563 | #REF! | 0 | #REF! | 0 | #REF!
17 | REC | Assam | APDCL | RDSS | 2782 | #REF! | 2123 | #REF! | 0 | #REF!
18 | REC | Meghalaya | MePDCL | RDSS | 1324 | #REF! | 0 | #REF! | 0 | #REF!
19 | REC | Jammu and Kashmir | JPDCL | RDSS | 1123 | #REF! | 0 | #REF! | 0 | #REF!
20 | REC | Jammu and Kashmir | KPDCL | RDSS | 1485 | #REF! | 0 | #REF! | 0 | #REF!
21 | REC | Mizoram | Mizoram PD | RDSS | 398 | #REF! | 0 | #REF! | 0 | #REF!
22 | REC | Uttar Pradesh | DVVNL | RDSS | 4393 | #REF! | 0 | #REF! | 0 | #REF!
23 | REC | Uttar Pradesh | KESCO | RDSS | 693 | #REF! | 0 | #REF! | 0 | #REF!
24 | REC | Uttar Pradesh | MVVNL | RDSS | 1745 | #REF! | 0 | #REF! | 0 | #REF!
25 | REC | Uttar Pradesh | PVVNL | RDSS | 9349 | #REF! | 0 | #REF! | 0 | #REF!
26 | REC | Uttar Pradesh | PuVVNL | RDSS | 4694 | #REF! | 0 | #REF! | 0 | #REF!
27 | REC | Tamil Nadu | TANGEDCO | RDSS | 18274 | #REF! | 0 | #REF! | 0 | #REF!
28 | REC | Bihar | NBPDCL | RDSS | 3806 | #REF! | 205 | #REF! | 0 | #REF!
29 | REC | Bihar | SBPDCL | RDSS | 2621 | #REF! | 250 | #REF! | 0 | #REF!
30 | REC | Rajasthan | AVVNL | RDSS | 11007 | #REF! | 0 | #REF! | 0 | #REF!
31 | REC | Rajasthan | JdVVNL | RDSS | 10322 | #REF! | 0 | #REF! | 0 | #REF!
32 | REC | Rajasthan | JVVNL | RDSS | 5799 | #REF! | 0 | #REF! | 0 | #REF!
33 | REC | Chhattisgarh | CSPDCL | RDSS | 6720 | #REF! | 0 | #REF! | 0 | #REF!
34 | REC | Manipur | MSPDCL | RDSS | 357 | #REF! | 0 | #REF! | 0 | #REF!
35 | REC | Tripura | TSECL | RDSS | 473 | #REF! | 0 | #REF! | 0 | #REF!
36 | REC | Goa | Goa PD | RDSS | 827 | #REF! | 0 | #REF! | 0 | #REF!
37 | REC | Sikkim | Sikkim PD | RDSS | 633 | #REF! | 0 | #REF! | 0 | #REF!
38 | REC | Arunachal Pradesh | Arunachal PD | RDSS | 688 | #REF! | 0 | #REF! | 0 | #REF!
39 | REC | Ladakh | Ladakh PD | RDSS | 0 | #REF! | 0 | #REF! | 0 | #REF!
40 | REC | West Bengal | WBSEDCL | RDSS | 11874 | #REF! | 0 | #REF! | 0 | #REF!
41 | REC | Karnataka | - | RDSS | 0 | #REF! | 0 | #REF! | 0 | #REF!
42 | REC | Andaman and Nicobar | EDANI | RDSS | 0 | #REF! | 0 | #REF! | 0 | #REF!
43 | REC | Nagaland | Nagaland PD | RDSS | 392 | #REF! | 0 | #REF! | 0 | #REF!
|  |  |  | Sub-Total (RDSS) | 193597 | #REF! | 3966 | #REF! | 0 | #REF!
1 | REC | Ladakh | Ladakh PD | SDP | 54 | #REF! | 0 | #REF! | 0 | #REF!
|  |  |  | Sub-Total (Non-RDSS) | 54 | #REF! | 0 | #REF! | 0 | #REF!
|  |  |  | Total (RDSS + Non-RDSS) | 193651 | #REF! | 3966 | #REF! | 0 | #REF!
* Non-RDSS - IPDS/ DDUGJY/ PMDP/ SG-Pilot/ NSGM/ Utility Owned/SDP

## Overall_Summary (hidden)
Last Updated |  | 2023-05-18 |  | Already Completed Projects
Sl | State | Utility | Project Area(s) | Completion timeline | Nos. of Smart Meters Sanctioned |  | Nos. of Smart Meters Awarded |  | Business Model (Capex/Opex/Hybrid/DBFOOT) | Scheme under which it is funded (Revamped/ IPDS/ NSGM/ Own) | Implementation Agency | Agency Responsible | Nos. of Smart Meters available at Store (Inventory of PROJECT) | Nos. of Smart Meters Installed |  | Target May 2023 Month | Achievement May 2023 Month | Installed till 1st May 2023 | Achievement April 2023 Month | Installed till 1st April 2023 | Achievement March 2023 Month | Installed till 1st March 2023 | Achievement February 2023 Month | Installed till 1st February 2023 | Achievement January 2023 Month | Installed till 1st January 2023 | Achievement December 2022 Month | Installed till 1st December 2022 | Achievement November 2022 Month | Installed till 1st November 2022 | Achievement October 2022 Month | Installed till 1st October 2022 | Achievement September 2022 Month | Installed till 1st September 2022 | Achievement August 2022 Month | Installed till 1st August 2022 | Achievement July 2022 Month | Installed till 1st July 2022 | Achievement June 2022 Month | Installed till 1st June 2022 | Achievement May 2022 Month | Installed till 1st May 2022 | Achievement April 2022 Month | Installed till 1st April 2022 | Achievement March 2022 Month | Installed till 1st March 2022 | Achievement February 2022 Month | Installed till 1st February 2022 | Achievement January 2022 Month | Installed till 1st January 2022 | Achievement December 2021 Month | Installed till 1st December 2021 | Achievement November Month | Installed till 1st November 2021 | Achievement Oct'21 Month | Installed as of 1st October 2021 | Achievement Sep'21 Month | Installed as of 1st September 2021 | Achievement Aug'21 Month | Installed as of 1st August 2021 | Achievement July'21 Month | Installed as of 1st July 2021
[5 empty] | of Smart type | of Smart Prepaid type | of Smart type | of Smart Prepaid type |  |  |  |  | of Smart type | of Smart type | of Smart Prepaid type
| Smart Meters in Completed Projects |  |  |  | 1676208 | 68433 |  |  | - | - | - |  | 0 | 1676208 | 68433
| Ongoing Smart Meter Installation |  |  |  | 211252871 | 204602531 |  |  | - | - | - |  | 745659 | 4075535 | 1597052
1 | Andaman and Nicobar | EDANI | Andman | Completed | 36800 | 0 | 36800 | 0 | Opex | IPDS | BOSCH | EESL | 0 | 36800 | 0 | 0 | 0 | 36800 | 0 | 36800 | 0 | 36800 | 0 | 36800 | 0 | 36800 | 0 | 36800 | 0 | 36800 | 0 | 36800 | 0 | 36800 | 0 | 36800 | 0 | 36800 | 0 | 36800 | 0 | 36800 | 0 | 36500 | 0 | 36500 | 592 | 35908 | 573 | 35335 | -1863 | 37198 | 1335 | 35863 | 2042 | 33821 | -505 | 34326 | 738 | 33588 | 905 | 32683
| Andaman and Nicobar | EDANI | Andman | Ongoing | 28102 | 0 | 0 | 0 | - | Utility Owned | - | Utility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Andaman and Nicobar | EDANI | Andman | Completed | 38400 | 0 | 38400 | 0 | Opex | DDUGJY | BOSCH | EESL | 0 | 38400 | 0 | 0 | 0 | 38400 | 0 | 38400 | 0 | 38400 | 0 | 38400 | 0 | 38400 | 0 | 38400 | 0 | 38400 | 0 | 38400 | 0 | 38400 | 0 | 38400 | 0 | 38400 | 0 | 38400 | 0 | 38400 | 0 | 38400 | 0 | 38400 | 289 | 38111 | 2328 | 35783 | 6673 | 29110 | 10211 | 18899 | 1401 | 17498 | -1339 | 18837 | 271 | 18566 | 696 | 17870
2 | Assam | APDCL | Guwahati, Dibrugarh | Completed | 70000 | 0 | 70000 | 0 | Capex | Utility Owned | Anvil Cables, Sinhal Udyog | Utility | 0 | 70000 | 2720 | 0 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | - | 70000 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 70000
| Assam | APDCL | 3 Towns | Completed | 134000 | 0 | 134000 | 0 | Capex | Utility Owned | Anvil Cables, Sinhal Udyog | Utility | 0 | 134000 | 7926 | 0 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 1433 | 132567 | 6134 | 126433 | 3123 | 123310 | 2883 | 120427 | 4808 | 115619 | 5092 | 110527 | 4679 | 105848 | 4577 | 101271 | 10567 | 90704 | 10003 | 80701 | 12700 | 68001 | 8760 | 59241 | 6673 | 52568 | 11916 | 40652 | 11640 | 29012
| Assam | APDCL | 4 Towns | Completed | 134000 | 0 | 134000 | 0 | Capex | Utility Owned | Purbanchal Enterprise | Utility | 0 | 134000 | 9187 | 0 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 0 | 134000 | 1658 | 132342 | 11133 | 121209 | 9825 | 111384 | 9628 | 101756 | 32718 | 69038 | 13667 | 55371 | 6477 | 48894 | 16411 | 32483 | 11899 | 20584 | 1259 | 19325 | 3869 | 15456 | 7825 | 7631 | 625 | 7006 | 2363 | 4643 | 3667 | 976 | 976 | 0
| Assam | APDCL | Guwahati | Completed | 14519 | 0 | 14519 | 0 | Capex | SG Pilot | Fluent Grid | Utility | 0 | 14519 | 0 | 0 | 0 | 14519 | 0 | 14519 | 0 | 14519 | 0 | 14519 | 0 | 14519 | 260 | 14259 | 0 | 14259 | 0 | 14259 | 0 | 14259 | 0 | 14259 | 0 | 14259 | 0 | 14259 | 0 | 14259 | 0 | 14259 | - | 14259 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 14259
| Assam | APDCL | 11 Towns | Ongoing | 363500 | 363500 | 363500 | 363500 | DBFOOT | Utility Owned | Intellismart | REC | 139747 | 120666 | 102320 | 10000 | 838 | 119828 | 5110 | 114718 | 8376 | 106342 | 13117 | 93225 | 15098 | 78127 | 14428 | 63699 | 19074 | 44625 | -19837 | 64462 | 18277 | 46185 | 21260 | 24925 | 19586 | 5339 | 4713 | 626 | 626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
| Assam | APDCL | 8 Towns | Ongoing | 256600 | 256600 | 256600 | 256600 | DBFOOT | Utility Owned | Intellismart | REC | 122351 | 106422 | 55334 | 10000 | 3162 | 103260 | 14958 | 88302 | 27202 | 61100 | 11838 | 49262 | 12377 | 36885 | 6971 | 29914 | 4954 | 24960 | 24960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
| Assam | APDCL | Bongaigaon, Kokrajhar | Awarded | 681303 | 680400 | 681303 | 680400 | TOTEX | RDSS | Apraava | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Assam | APDCL | Badarpur, Cachar | Awarded | 692022 | 691000 | 692022 | 691000 | TOTEX | RDSS | Genus Power | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Assam | APDCL | Nagaon, Golaghat | Awarded | 712328 | 711200 | 712328 | 711200 | TOTEX | RDSS | Hi-Print | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Assam | APDCL | Jorhat, Tinsukia, Sivasagar | Awarded | 735964 | 733800 | 735964 | 733800 | TOTEX | RDSS | Genus Power | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Assam | APDCL | Barpeta, Rangia | Awarded | 753613 | 749300 | 753613 | 749300 | TOTEX | RDSS | Hi-Print | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Assam | APDCL | N.Lakhimpur, Tezpur, Mangaldoi | Awarded | 758986 | 757700 | 758986 | 757700 | TOTEX | RDSS | Adani Transmission | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Assam | APDCL | - | Proposed | 790382 | 790382 |  |  | TOTEX | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Arunachal Pradesh | Arunachal PD | - | Proposed | 287445 | 287445 |  |  | TOTEX | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Andhra Pradesh | APEPDCL | Vizag | Completed | 2000 | 0 | 2000 | 0 | Capex | Utility Owned | Gram Power | Utility | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | - | - | 2000 | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| Andhra Pradesh | APSPDCL | All Districts | Tendering | 2302644 | 2302644 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Andhra Pradesh | APCPDCL | All Districts | Tendering | 2050962 | 2050962 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Andhra Pradesh | APEPDCL | All Districts | Tendering | 1255240 | 1255240 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Bihar | NBPDCL | Across Bihar | Ongoing | 1030000 | 1030000 | 1030000 | 1030000 | Opex | RDSS | EDF, Genus | REC | 94618 | 582514 | 581728 | 30000 | 0 | 582514 | 15833 | 566681 | 13446 | 553235 | 11357 | 541878 | 20416 | 521462 | 29810 | 491652 | 22362 | 469290 | 18704 | 450586 | 23903 | 426683 | 28387 | 398296 | 29267 | 369029 | 37109 | 331920 | 35658 | 296262 | 33720 | 262542 | 48792 | 213750 | 21135 | 192615 | 28324 | 164291 | 21280 | 143011 | 10850 | 132161 | 19127 | 113034 | 25445 | 87589 | 6321 | 81268 | 5518 | 75750
| Bihar | SBPDCL | Across Bihar | Ongoing | 1320000 | 1320000 | 1320000 | 1320000 | Opex | RDSS | EDF, Genus | REC | 94618 | 753819 | 753015 | 30000 | 0 | 753819 | 21467 | 732352 | 20884 | 711468 | 20630 | 690838 | 18457 | 672381 | 24964 | 647417 | 22848 | 624569 | 15052 | 609517 | 21177 | 588340 | 42529 | 545811 | 44430 | 501381 | 50302 | 451079 | 41448 | 409631 | 37366 | 372265 | 56924 | 315341 | 39990 | 275351 | 39990 | 235361 | 26086 | 209275 | 15704 | 193571 | 26010 | 167561 | 39328 | 128233 | 28025 | 100208
| Bihar | SBPDCL | Gaya, Manpur | Completed | 40500 | 40500 | 40500 | 40500 | Opex | Utility Owned | Gram Power | Utility | 0 | 30500 | 30500 | 0 | 0 | 30500 | 0 | 30500 | 0 | 30500 | 0 | 30500 | 0 | 30500 | 0 | 30500 | 0 | 30500 | 0 | 30500 | 0 | 30500 | 0 | 30500 | 0 | 30500 | 0 | 30500 | 0 | 30500 | 0 | 30500 | 0 | 30500 | 0
| Bihar | IPCL | Bodhgaya | Completed | 17100 | 17100 | 17100 | 17100 | Capex | Utility Owned | Gram Power | Utility | 0 | 17100 | 17100 | 0 | 0 | 17100 | 0 | 17100 | 0 | 17100 | 0 | 17100 | 0 | 17100 | 0 | 17100 | 0 | 17100 | 0 | 17100 | 0 | 17100 | 0 | 17100 | 0 | 17100 | 0 | 17100 | 0 | 17100 | 0 | 17100 | 0 | 17100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bihar | BEDCPL | Bhagalpur | Completed | 1000 | 1000 | 1000 | 1000 | Capex | Utility Owned | Gram Power | Utility | 0 | 1000 | 1000 | 0 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Chandigarh | CED | Sub Div 5 | Ongoing | 29433 | 0 | 29433 | 0 | Capex | NSGM | Genus, Synergy | RECPDCL | 0 | 24214 | 0 | 0 | 0 | 24214 | 0 | 24214 | 0 | 24214 | 0 | 24214 | 0 | 24214 | 0 | 24214 | 1 | 24213 | 0 | 24213 | 0 | 24213 | 0 | 24213 | 0 | 24213 | 64 | 24149 | 9 | 24140 | 199 | 23941 | 3169 | 20772 | 1516 | 19256 | 1276 | 17980 | 1049 | 16931 | 2032 | 14899 | 2308 | 12591 | 1420 | 11171 | 659 | 10512 | 1069 | 9443
| Chhattisgarh | CSPDCL | - | Proposed | 5962115 | 5962115 |  |  | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Delhi | NDMC | NDMC Area | Ongoing | 64713 | 0 | 64713 | 0 | Opex | Utility Owned | Larsen Toubro | EESL | 355 | 65059 | 0 | 0 | 0 | 65059 | 0 | 65059 | 0 | 65059 | 0 | 65059 | 131 | 64928 | 197 | 64731 | 236 | 64495 | 401 | 64094 | 103 | 63991 | 105 | 63886 | 75 | 63811 | 119 | 63692 | 70 | 63622 | 84 | 63538 | 154 | 63384 | 95 | 63289 | 1195 | 62094 | 645 | 61449 | 168 | 61281 | 179 | 61102 | 267 | 60835 | 244 | 60591 | 178 | 60413
| Delhi | TPDDL | North Delhi | Completed | 195000 | 0 | 195000 | 0 | Capex | Utility Owned | Landis Gyr | Utility | 0 | 195000 | 0 | 0 | 0 | 195000 | 0 | 195000 | 0 | 195000 | 0 | 195000 | 0 | 195000 | 0 | 195000 | 0 | 195000 | 0 | 195000 | 0 | 195000 | 0 | 195000 | 0 | 195000 | 0 | 195000 | 0 | 195000 | 0 | 195000 | - | 195000 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 195000
8 | Goa | Goa PD | - | Proposed | 741160 | 741160 |  |  | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Gujarat | UGVCL | Naroda | Completed | 23760 | 0 | 23760 | 0 | Capex | SG Pilot | Genus | Utility | 0 | 23760 | 0 | 0 | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760 | - | 23760 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 23760
| Gujarat | DGVCL | All Districts | Tendering | 4078120 | 4078120 | #REF! | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gujarat | MGVCL | All Districts | Tendering | 3299991 | 3299991 | #REF! | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gujarat | PGVCL | All Districts | Tendering | 5583509 | 5583509 | #REF! | #REF! | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gujarat | UGVCL | All Districts | Tendering | 3520251 | 3520251 | #REF! | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Haryana | UHBVNL | Panipat | Completed | 10188 | 0 | 10188 | 0 | Capex | SG Pilot | NEDO | Utility | 0 | 10188 | 0 | 0 | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188 | - | 10188 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 10188
| Haryana | DHBVNL | Across Haryana | Ongoing | 500000 | 0 | 500000 | 0 | Opex | Utility Owned | Larsen Toubro | EESL | 59776.5 | 242521 | 501 | 15500 | 0 | 242521 | 8095 | 234426 | 0 | 234426 | 0 | 234426 | 4439 | 229987 | 9651 | 220336 | 8229 | 212107 | 3431 | 208676 | 4725 | 203951 | 9627 | 194324 | 6274 | 188050 | 6989 | 181061 | 4366 | 176695 | 1651 | 175044 | 3097 | 171947 | 4767 | 167180 | 5046 | 162134 | 4472 | 157662 | 4704 | 152958 | 9574 | 143384 | 12185 | 131199 | 2481 | 128718 | 3478 | 125240
| Haryana | UHBVNL | Across Haryana | Ongoing | 500000 | 0 | 500000 | 0 | Opex | Utility Owned | Larsen Toubro | EESL | 59776.5 | 405171 | 958 | 15500 | 0 | 405171 | 13735 | 391436 | 0 | 391436 | 0 | 391436 | 12550 | 378886 | 22346 | 356540 | 19034 | 337506 | 18087 | 319419 | 16626 | 302793 | 19608 | 283185 | 15669 | 267516 | 16272 | 251244 | 13692 | 237552 | 2204 | 235348 | 5792 | 229556 | 7326 | 222230 | 5260 | 216970 | 9793 | 207177 | 7285 | 199892 | 11635 | 188257 | 15099 | 173158 | 11538 | 161620 | 6912 | 154708
| Haryana | DHBVNL | All Districts | Proposed | 4165618 | 4165618 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Haryana | UHBVNL | All Districts | Proposed | 3240000 | 3240000 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Haryana | POWERGRID | Manesar | Completed | 10 | 0 | 10 | 0 | Capex | SG Pilot | Genus | Utility | 0 | 10 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | - | 10 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 10
11 | Himachal Pradesh | HPSEBL | Kala Amb | Completed | 1335 | 0 | 1335 | 0 | Capex | SG Pilot | General Electric | Utility | 0 | 1335 | 0 | 0 | 0 | 1335 | 0 | 1335 | 0 | 1335 | 0 | 1335 | 0 | 1335 | 0 | 1335 | 0 | 1335 | 0 | 1335 | 0 | 1335 | 0 | 1335 | 0 | 1335 | 0 | 1335 | 0 | 1335 | 0 | 1335 | - | 1335 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 1335
| Himachal Pradesh | HPSEBL | Shimla, Dharamshala | Completed | 75712 | 0 | 75712 | 0 | Capex | IPDS | Schneider Electric | PFCCL | 0 | 75712 | 0 | 0 | 0 | 75712 | 0 | 75712 | 0 | 75712 | 0 | 75712 | 0 | 75712 | 0 | 75712 | 0 | 75712 | 0 | 75712 | 0 | 75712 | 0 | 75712 | 0 | 75712 | 0 | 75712 | 0 | 75712 | 0 | 75712 | 5354 | 70358 | 22381 | 47977 | 16154 | 31823 | 8689 | 23134 | 15200 | 7934 | 7934 | 0 | 0 | 0 | 0 | 0
| Himachal Pradesh | HPSEBL | Shimla, Dharamshala | Ongoing | 76028 | 0 | 76028 | 0 | Capex | Utility Owned | Schneider Electric | PFCCL | 1994 | 75303 | 0 | 0 | 0 | 75303 | 0 | 75303 | 0 | 75303 | 0 | 75303 | 2420 | 72883 | 0 | 72883 | 0 | 72883 | 2826 | 70057 | 0 | 70057 | 615 | 69442 | 1572 | 67870 | 7702 | 60168 | 60168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
| Himachal Pradesh | HPSEBL | All Districts | Tendering | 2800945 | 2800945 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Jammu and Kashmir | JPDCL & KPDCL | Jammu and Srinagar | Ongoing | 127050 | 0 | 127050 | 0 | Capex | PMDP | Techno Electric | RECPDCL | 2384 | 124666 | 0 | 0 | 0 | 124666 | 0 | 124666 | 277 | 124389 | -407 | 124796 | 1433 | 123363 | 765 | 122598 | 3544 | 119054 | 5197 | 113857 | 7876 | 105981 | 9364 | 96617 | 6804 | 89813 | 13763 | 76050 | 15941 | 60109 | 10321 | 49788 | 19416 | 30372 | 9234 | 21138 | 6890 | 14248 | 417 | 13831 | 4931 | 8900 | 4447 | 4453 | 2202 | 2251 | 2251 | 0 | 0 | -
| Jammu and Kashmir | JPDCL & KPDCL | Jammu and Kashmir (Lot A) | Ongoing | 307766 | 0 | 307766 | 0 | DBFOOT | PMDP | Anvil Cables | RECPDCL | 14372 | 84954 | 0 | 30000 | 6170 | 78784 | 11164 | 67620 | 16784 | 50836 | 18069 | 32767 | 10497 | 22270 | 7076 | 15194 | 9020 | 6174 | 6174 | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| Jammu and Kashmir | JPDCL & KPDCL | Jammu and Kashmir (Lot B) | Ongoing | 250672 | 0 | 250672 | 0 | DBFOOT | PMDP | Techno Electric | RECPDCL | 41420 | 17364 | 0 | 20000 | 11844 | 5520 | 5520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| Jammu and Kashmir | JPDCL | - | Proposed | 721346 | 721346 |  |  | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Jammu and Kashmir | KPDCL | - | Proposed | 685699 | 685699 |  |  | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Jharkhand | JBVNL | All Districts | Proposed | 1341306 | 1341306 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Karnataka | CESCOM | Mysuru | Completed | 20916 | 0 | 20916 | 0 | Capex | SG Pilot | Enzen Global | Utility | 0 | 20916 | 0 | 0 | 0 | 20916 | 0 | 20916 | 0 | 20916 | 0 | 20916 | 0 | 20916 | 0 | 20916 | 0 | 20916 | 0 | 20916 | 0 | 20916 | 0 | 20916 | 0 | 20916 | 0 | 20916 | 0 | 20916 | 0 | 20916 | - | 20916 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 20916
15 | Kerala | Cochin Port | Cochin Port | Completed | 805 | 0 | 805 | 0 | Capex | IPDS | Nsoft India | Utility | 0 | 805 | 0 | 0 | 0 | 805 | 0 | 805 | 0 | 805 | 0 | 805 | 0 | 805 | 0 | 805 | 0 | 805 | 0 | 805 | 0 | 805 | 0 | 805 | 0 | 805 | 0 | 805 | 0 | 805 | 0 | 805 | - | 805 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 780
| Kerala | KSEBL | All Districts | Proposed | 13248923 | 13248923 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kerala | TCED | Thrissur | Proposed | 40438 | 40438 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Madhya Pradesh | MP-West | 5 Towns | Completed | 124477 | 0 | 124477 | 0 | Capex+Opex | IPDS | MP Smart Grid | Utility | 0 | 124477 | 0 | 0 | 0 | 124477 | 0 | 124477 | 0 | 124477 | 0 | 124477 | 0 | 124477 | 0 | 124477 | 0 | 124477 | 0 | 124477 | 0 | 124477 | 0 | 124477 | 0 | 124477 | 0 | 124477 | 0 | 124477 | 0 | 124477 | -4523 | 129000 | 6700 | 122300 | 12286 | 110014 | 13740 | 96274 | 11274 | 85000 | 12709 | 72291 | 6396 | 65895 | 14491 | 51404 | 5691 | 45713
| Madhya Pradesh | MP-West | Included above | Ongoing | 225523 | 0 | 225523 | 0 | Capex+Opex | Utility Owned | MP Smart Grid | Utility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Madhya Pradesh | MP-East​ | All Districts | Partially Awarded | 5144451 | 5144451 | #REF! | #REF! | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Madhya Pradesh | MP-Central​ | All Districts | Tendering | 3955918 | 3955918 | #REF! | #REF! | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Madhya Pradesh | MP-West​ | All Districts | Partially Awarded | 3879733 | 3879733 | #REF! | #REF! | Totex | RDSS | - | PFC | 1945 | 26800 | 0 | 12000 | 1358 | 25442 | 10471 | 14971 | 5494 | 9477 | 9477 | 0 | 0 | 0 | 0
| Madhya Pradesh | MP-West | Indore | Completed | 118836 | 0 | 118836 | 0 | Capex | IPDS | Larsen Toubro | Utility | 0 | 118836 | 0 | 0 | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836 | - | 118836 | - | - | - | - | - | - | - | - | - | - | - | - | - | -
17 | Maharashtra | MSEDCL | All Districts | Tendering | 22488866 | 22488866 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Maharashtra | BEST | Mumbai City | Awarded | 1075881 | 1075881 | 1075881 | 1075881 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Manipur | MSPDCL | - | Proposed | 154400 | 154400 |  |  | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Meghalaya | MePDCL | - | Proposed | 460000 | 460000 |  |  | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Mizoram | Mizoram PD | - | Proposed | 289383 | 289383 |  |  | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Nagaland | Nagaland PD | - | Proposed | 317210 | 317210 |  |  | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Odisha | OPTCL | Across Odisha | Completed | 4000 | 0 | 4000 | 0 | BOOT | Utility Owned | JnJ | Utility | 0 | 4000 | 0 | 0 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | - | 4000 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 4000
| Odisha | Paradip Port | Paradip | Completed | 500 | 0 | 500 | 0 | Capex | Utility Owned | Gram Power | Utility | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 500 | - | 500 | - | -
23 | Puducherry | PED | Puducherry | Completed | 28910 | 0 | 28910 | 0 | Capex | SG Pilot | Dongfang Electronics | Utility | 0 | 28910 | 0 | 0 | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910 | - | 28910 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 28910
| Puducherry | PED | Puducherry | Completed | 1658 | 0 | 1658 | 0 | Capex | Utility Owned | Multiple Vendors | Utility | 0 | 1658 | 0 | 0 | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658 | - | 1658 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 1658
| Puducherry | PED | All districts | Tendering | 403767 | 403767 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Punjab | PSPCL | Ludhiana | Completed | 88107 | 0 | 88107 | 0 | Capex | IPDS | PSPCL, HPL | Utility | 0 | 88107 | 0 | 0 | 0 | 88107 | 0 | 88107 | 0 | 88107 | 0 | 88107 | 0 | 88107 | 0 | 88107 | 7 | 88100 | 0 | 88100 | 0 | 88100 | 0 | 88100 | 0 | 88107 | 0 | 88107 | 0 | 88107 | 0 | 88107 | 0 | 88107 | 10107 | 78000 | 15000 | 63000 | 10000 | 53000 | 22322 | 30678 | 12911 | 17767 | 5950 | 11817 | 4414 | 7403 | 4803 | 2600
| Punjab | PSPCL | Ludhiana | Ongoing | 7893 | 0 | 7893 | 0 | Capex | Utility Owned | PSPCL, HPL | Utility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 7 | 0 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Punjab | PSPCL | All districts | Proposed | 8784807 | 8784807 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Rajasthan | JaVVNL | Jaipur and Tonk | Completed | 240820 | 0 | 240820 | 0 | Capex | IPDS | Genus | Utility | 0 | 240820 | 0 | 0 | 0 | 240820 | 0 | 240820 | 0 | 240820 | 0 | 240820 | 0 | 240820 | 0 | 240820 | 0 | 240820 | 0 | 240820 | 0 | 240820 | 0 | 240820 | 0 | 240820 | 0 | 240820 | 0 | 240820 | 0 | 240820 | -7407 | 248227 | 48875 | 199352 | 30694 | 168658 | 25172 | 143486 | 28813 | 114673 | 11158 | 103515 | 19238 | 84277 | 25883 | 58394 | 12745 | 45649
| Rajasthan | JaVVNL | Jaipur and Tonk | Ongoing | 40980 | 0 | 40980 | 0 | Capex | Utility Owned | Genus | Utility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Rajasthan | AVVNL | 66 Towns (Part) | Completed | 68673 | 0 | 68673 | 0 | Opex | IPDS | BOSCH | EESL | 0 | 68673 | 0 | 0 | 0 | 68673 | 0 | 68673 | 0 | 68673 | 0 | 68673 | 0 | 68673 | 0 | 68673 | 0 | 68673 | 0 | 68673 | 0 | 68673 | 0 | 68673 | 0 | 68673 | 0 | 68673 | 0 | 68673 | 0 | 68673 | -119 | 68792 | 453 | 68339 | 644 | 67695 | 11194 | 56501 | 9623 | 46878 | 5379 | 41499 | 15188 | 26311 | 9584 | 16727 | 9984 | 6743
| Rajasthan | AVVNL | 66 Towns (Part) | MI on Hold | 122149 | 0 | 122149 | 0 | Opex | Utility Owned | BOSCH | EESL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Rajasthan | JdVVNL | Jodhpur | Completed | 56027 | 0 | 56027 | 0 | Opex | IPDS | BOSCH | EESL | 0 | 56027 | 0 | 0 | 0 | 56027 | 0 | 56027 | 0 | 56027 | 0 | 56027 | 0 | 56027 | 0 | 56027 | 0 | 56027 | 0 | 56027 | 0 | 56027 | 0 | 56027 | 0 | 56027 | 0 | 56027 | 0 | 56027 | 0 | 56027 | -81 | 56108 | 373 | 55735 | 883 | 54852 | 16013 | 38839 | 3710 | 35129 | 3829 | 31300 | 9767 | 21533 | 21533
| Rajasthan | JdVVNL | Jodhpur | MI on Hold | 46155 | 0 | 46155 | 0 | Opex | Utility Owned | BOSCH | EESL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7326 | 7326
| Rajasthan | AVVNL | Ajmer | Completed | 1000 | 0 | 1000 | 0 | Capex | Utility Owned | Radius, JnJ | Utility | 0 | 1000 | 0 | 0 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000 | - | 1000 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 1000
| Rajasthan | JaVVNL | 6 Towns | Ongoing | 150000 | 0 | 150000 | 0 | Hybrid | NSGM | Genus | Utility | 13300 | 135944 | 0 | 2000 | 908 | 135036 | 866 | 134170 | 789 | 133381 | 1083 | 132298 | 4798 | 127500 | 5302 | 122198 | 1650 | 120548 | 1110 | 119438 | 1669 | 117769 | 372 | 117397 | 951 | 116446 | 1838 | 114608 | 1540 | 113068 | 3313 | 109755 | 7970 | 101785 | 12790 | 88995 | 9647 | 79348 | 10715 | 68633 | 10220 | 58413 | 7123 | 51290 | 7558 | 43732 | 13088 | 30644 | 6969 | 23675
| Rajasthan | JaVVNL | Kota | Completed | 70000 | 0 | 70000 | 0 | Capex | Utility Owned | Genus | Utility | 0 | 70000 | 0 | 0 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | - | 70000 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 70000
| Rajasthan | AVVNL | - | Proposed | 5432231 | 5432231 |  |  | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Rajasthan | JdVVNL | - | Proposed | 4080082 | 4080082 |  |  | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Rajasthan | JVVNL | - | Proposed | 4762643 | 4762643 |  |  | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Sikkim | Sikkim PD | - | Proposed | 144680 | 144680 |  |  | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Tamil Nadu | TANGEDCO | Chennai | Ongoing | 141000 | 0 | 141000 | 0 | Capex | Utility Owned | Genus | Utility | 13187 | 126510 | 0 | 0 | 0 | 126510 | -1920 | 128430 | 449 | 127981 | 70 | 127911 | 266 | 127645 | 518 | 127127 | 132 | 126995 | 2050 | 124945 | 1062 | 123883 | 1397 | 122486 | 924 | 121562 | 4035 | 117527 | 11118 | 106409 | 5550 | 100859 | 5792 | 95067 | 9082 | 85985 | 16243 | 69742 | 17260 | 52482 | 6267 | 46215 | 12075 | 34140 | 7770 | 26370 | 5431 | 20939 | 8535 | 12404
| Tamil Nadu | TANGEDCO | - | Proposed | 30000000 | 30000000 |  |  | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | Tripura | TSECL | - | Proposed | 547489 | 547489 |  |  | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tripura | TSECL | Agartala | Completed | 43081 | 0 | 43081 | 0 | Capex | SG Pilot | Wipro | Utility | 0 | 43081 | 0 | 0 | 0 | 43081 | 0 | 43081 | 0 | 43081 | 0 | 43081 | 0 | 43081 | 0 | 43081 | 0 | 43081 | 0 | 43081 | 0 | 43081 | 0 | 43081 | 0 | 43081 | 0 | 43081 | 0 | 43081 | 0 | 43081 | - | 43081 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 43081
29 | Telangana | TSSPDCL | Jeedimetla | Completed | 8882 | 0 | 8882 | 0 | Capex | SG Pilot | ECIL | Utility | 0 | 8882 | 0 | 0 | 0 | 8882 | 0 | 8882 | 0 | 8882 | 0 | 8882 | 0 | 8882 | 0 | 8882 | 0 | 8882 | 0 | 8882 | 0 | 8882 | 0 | 8882 | 0 | 8882 | 0 | 8882 | 0 | 8882 | 0 | 8882 | - | 8882 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 8882
30 | Uttar Pradesh | IITK | Kanpur | Completed | 28 | 0 | 28 | 0 | Capex | SG Pilot | Synergy | Utility | 0 | 28 | 0 | 0 | 0 | 28 | 0 | 28 | 0 | 28 | 0 | 28 | 0 | 28 | 0 | 28 | 0 | 28 | 0 | 28 | 0 | 28 | 0 | 28 | 0 | 28 | 0 | 28 | 0 | 28 | 0 | 28 | - | 28 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 28
| Uttar Pradesh | MVVNL | Lucknow | Ongoing | 905769 | 0 | 905769 | 0 | Opex | Utility Owned | Larsen Toubro | EESL | 17163 | 380731 | 3337 | 0 | 0 | 380731 | 0 | 380731 | 0 | 380731 | 0 | 380731 | 55 | 380676 | 341 | 380335 | 363 | 379972 | 985 | 378987 | 125 | 378862 | 0 | 378862 | 0 | 378862 | 0 | 378862 | 0 | 378862 | 0 | 378862 | 0 | 378862 | 0 | 378862 | 24 | 378838 | 0 | 378838 | 0 | 378838 | 2989 | 375849 | 0 | 375849 | 0 | 375849 | 0 | 375849
| Uttar Pradesh | PVVNL | Meerut | MI on Hold | 1164138 | 0 | 1164138 | 0 | Opex | Utility Owned | Larsen Toubro | EESL | 17163 | 198726 | 20 | 0 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 0 | 198726 | 304 | 198422 | 0 | 198422 | 0 | 198422 | 0 | 198422
| Uttar Pradesh | DVVNL | Agra | MI on Hold | 628686 | 0 | 628686 | 0 | Opex | Utility Owned | Larsen Toubro | EESL | 17163 | 147991 | 127 | 0 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 0 | 147991 | 531 | 147460 | 0 | 147460 | 0 | 147460 | 0 | 147460
| Uttar Pradesh | PuVVNL | Varanasi | MI on Hold | 1147102 | 0 | 1147102 | 0 | Opex | Utility Owned | Larsen Toubro | EESL | 17163 | 321433 | 1135 | 0 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 0 | 321433 | 1487 | 319946 | 0 | 319946 | 0 | 319946 | 0 | 319946
| Uttar Pradesh | KESCO | Kanpur | Ongoing | 156532 | 0 | 156532 | 0 | Opex | Utility Owned | Larsen Toubro | EESL | 17163 | 134727 | 98577 | 6000 | 0 | 134727 | 5575 | 129152 | 0 | 129152 | 0 | 129152 | 4288 | 124864 | 4375 | 120489 | 3971 | 116518 | 6828 | 109690 | 2372 | 107318 | 0 | 107318 | 0 | 107318 | 0 | 107318 | 0 | 107318 | 0 | 107318 | 0 | 107318 | 0 | 107318 | 0 | 107318 | 0 | 107318 | 0 | 107318 | 1085 | 106233 | 0 | 106233 | 0 | 106233 | 0 | 106233
| Uttar Pradesh | DVVNL | - | Proposed | 5354069 | 5354069 |  |  | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Uttar Pradesh | KESCO | - | Proposed | 625000 | 625000 |  |  | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Uttar Pradesh | MVVNL | - | Proposed | 7528737 | 7528737 |  |  | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Uttar Pradesh | PVVNL | - | Proposed | 6143261 | 6143261 |  |  | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Uttar Pradesh | PuVVNL | - | Proposed | 7327988 | 7327988 |  |  | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Uttarakhand | UPCL | All districts | Proposed | 1584205 | 1584205 |  |  | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | West Bengal | WBSEDCL | Siliguri | Completed | 5164 | 0 | 5164 | 0 | Capex | SG Pilot | Chemtrols | Utility | 0 | 5164 | 0 | 0 | 0 | 5164 | 0 | 5164 | 0 | 5164 | 0 | 5164 | 0 | 5164 | 0 | 5164 | 0 | 5164 | 0 | 5164 | 0 | 5164 | 0 | 5164 | 0 | 5164 | 0 | 5164 | 0 | 5164 | 0 | 5164 | - | 5164 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 5164
| West Bengal | CESC | Kolkata | Completed | 10000 | 0 | 10000 | 0 | Capex | Utility Owned | Genus, Secure | Utility | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | - | 10000 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | #VALUE! | 10000
| West Bengal | WBSEDCL | - | Proposed | 20717969 | 20717969 |  |  | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Grand Total |  |  |  | 212929079 | 204670964 | #REF! | #REF! |  |  |  |  | 745659 | 5751743 | 1665485 | 181000 | 24280 | 5727463 | 110874 | 5616589 | 93701 | 5522888 | 85234 | 5437654 | 107225 | 5330429 | 127004 | 5203425 | 115418 | 5088007 | 87626 | 5000381 | 110481 | 4889900 | 149223 | 4740677 | 138303 | 4602374 | 178507 | 4423867 | 203111 | 4220756 | 105977 | 4112479 | 165420 | 3949059 | 212181 | 3057946 | 204283 | 2853663 | 195207 | 2658456 | 185174 | 2473282 | 165622 | 2307660 | 175005 | 2132655 | 162535 | 1970120 | -335990 | 2306110

## PivotTable (hidden)
State | Utility | Area | Completion Status | Sanctioned Meters | Sanctioned Prepaid | Awarded Meters | Awarded Prepaid | Model | Scheme | Implementor | Agency | Stock | Installed Meters | Installed Prepaid | Target Month | Achievement | Till 1st of This Month | Previous Month Achievement
Andaman and Nicobar | EDANI | Andman | Completed | 36800 | 0 | 36800 | 0 | Opex | IPDS | BOSCH | EESL | 0 | 36800 | 0 | 0 | 0 | 36800 | 0 | 36800 | 0
Andaman and Nicobar | EDANI | Andman | Ongoing | 28102 | 0 | 0 | 0 | - | Utility Owned | - | Utility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | Target Completion | Target Required Per Month
Andaman and Nicobar | EDANI | Andman | Completed | 38400 | 0 | 38400 | 0 | Opex | DDUGJY | BOSCH | EESL | 0 | 38400 | 0 | 0 | 0 | 38400 | 0 | 38400 | 0 | Scheme | Sanctioned | Awarded | Installed Till Date | Prepaid Till Date | In Stock | Current Month Target | Current Month Achievement | Prev Month Achievement | 2021-12-31 | #VALUE!
Assam | APDCL | Guwahati, Dibrugarh | Completed | 70000 | 0 | 70000 | 0 | Capex | Utility Owned | Anvil Cables, Sinhal Udyog | Utility | 0 | 70000 | 2720 | 0 | 0 | 70000 | 0 | 70000 | 0 | DDUGJY | 38400 | 38400 | 38400 | 0 | 0 | 0 | 0 | 0 | 2024-03-31 | 0
Assam | APDCL | 3 Towns | Completed | 134000 | 0 | 134000 | 0 | Capex | Utility Owned | Anvil Cables, Sinhal Udyog | Utility | 0 | 134000 | 7926 | 0 | 0 | 134000 | 0 | 134000 | 0 | IPDS | 810257 | 810257 | 810257 | 0 | 0 | 0 | 0 | 0 | 2022-03-31 | #NUM!
Assam | APDCL | 4 Towns | Completed | 134000 | 0 | 134000 | 0 | Capex | Utility Owned | Purbanchal Enterprise | Utility | 0 | 134000 | 9187 | 0 | 0 | 134000 | 0 | 134000 | 0 | NSGM | 179433 | 179433 | 160158 | 0 | 13300 | 2000 | 908 | 866 | 2021-12-31 | 918
Assam | APDCL | Guwahati | Completed | 14519 | 0 | 14519 | 0 | Capex | SG Pilot | Fluent Grid | Utility | 0 | 14519 | 0 | 0 | 0 | 14519 | 0 | 14519 | 0 | PMDP | 685488 | 685488 | 226984 | 0 | 58176 | 50000 | 18014 | 16684 | - | -
Assam | APDCL | 11 Towns | Ongoing | 363500 | 363500 | 363500 | 363500 | DBFOOT | Utility Owned | Intellismart | REC | 139747 | 120666 | 102320 | 10000 | 838 | 119828 | 5110 | 114718 | 8376 | RDSS | 204003080 | #REF! | 1363133 | 1334743 | 191181 | 72000 | 1358 | 47771
Assam | APDCL | 8 Towns | Ongoing | 256600 | 256600 | 256600 | 256600 | DBFOOT | Utility Owned | Intellismart | REC | 122351 | 106422 | 55334 | 10000 | 3162 | 103260 | 14958 | 88302 | 27202 | SG Pilot | 156793 | 156793 | 156793 | 0 | 0 | 0 | 0 | 0
Assam | APDCL | Bongaigaon, Kokrajhar | Awarded | 681303 | 680400 | 681303 | 680400 | TOTEX | RDSS | Apraava | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Utility Owned | 7055628 | 7027526 | 2996018 | 330742 | 483002 | 57000 | 4000 | 45553
Assam | APDCL | Badarpur, Cachar | Awarded | 692022 | 691000 | 692022 | 691000 | TOTEX | RDSS | Genus Power | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | (blank)
Assam | APDCL | Nagaon, Golaghat | Awarded | 712328 | 711200 | 712328 | 711200 | TOTEX | RDSS | Hi-Print | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Grand Total | 212929079 | #REF! | 5751743 | 1665485 | 745659 | 181000 | 24280 | 110874
Assam | APDCL | Jorhat, Tinsukia, Sivasagar | Awarded | 735964 | 733800 | 735964 | 733800 | TOTEX | RDSS | Genus Power | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assam | APDCL | Barpeta, Rangia | Awarded | 753613 | 749300 | 753613 | 749300 | TOTEX | RDSS | Hi-Print | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assam | APDCL | N.Lakhimpur, Tezpur, Mangaldoi | Awarded | 758986 | 757700 | 758986 | 757700 | TOTEX | RDSS | Adani Transmission | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assam | APDCL | - | Proposed | 790382 | 790382 | 0 | 0 | TOTEX | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arunachal Pradesh | Arunachal PD | - | Proposed | 287445 | 287445 | 0 | 0 | TOTEX | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | Target Completion | Target Required Per Month
Andhra Pradesh | APEPDCL | Vizag | Completed | 2000 | 0 | 2000 | 0 | Capex | Utility Owned | Gram Power | Utility | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | Agency | Sanctioned | Awarded | Installed Till Date | Prepaid Till Date | In Stock | Current Month Target | Current Month Achievement | Prev Month Achievement | 2022-12-31 | #VALUE!
Andhra Pradesh | APSPDCL | All Districts | Tendering | 2302644 | 2302644 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EESL | 5435144 | 5435144 | 2096259 | 104655 | 205723 | 37000 | 0 | 27405 | 2022-04-30 | #NUM!
Andhra Pradesh | APCPDCL | All Districts | Tendering | 2050962 | 2050962 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PFC | 95466568 | #REF! | 26800 | 0 | 1945 | 12000 | 1358 | 10471 | 2022-03-31 | #NUM!
Andhra Pradesh | APEPDCL | All Districts | Tendering | 1255240 | 1255240 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PFCCL | 151740 | 151740 | 151015 | 0 | 1994 | 0 | 0 | 0 | - | -
Bihar | NBPDCL | Across Bihar | Ongoing | 1030000 | 1030000 | 1030000 | 1030000 | Opex | RDSS | EDF, Genus | REC | 94618 | 582514 | 581728 | 30000 | 0 | 582514 | 15833 | 566681 | 13446 | REC | 109156612 | 7304316 | 1563421 | 1492397 | 451334 | 80000 | 4000 | 57368
Bihar | SBPDCL | Across Bihar | Ongoing | 1320000 | 1320000 | 1320000 | 1320000 | Opex | RDSS | EDF, Genus | REC | 94618 | 753819 | 753015 | 30000 | 0 | 753819 | 21467 | 732352 | 20884 | RECPDCL | 714921 | 714921 | 251198 | 0 | 58176 | 50000 | 18014 | 16684
Bihar | SBPDCL | Gaya, Manpur | Completed | 40500 | 40500 | 40500 | 40500 | Opex | Utility Owned | Gram Power | Utility | 0 | 30500 | 30500 | 0 | 0 | 30500 | 0 | 30500 | 0 | Utility | 2004094 | 1975992 | 1663050 | 68433 | 26487 | 2000 | 908 | -1054
Bihar | IPCL | Bodhgaya | Completed | 17100 | 17100 | 17100 | 17100 | Capex | Utility Owned | Gram Power | Utility | 0 | 17100 | 17100 | 0 | 0 | 17100 | 0 | 17100 | 0 | (blank)
Bihar | BEDCPL | Bhagalpur | Completed | 1000 | 1000 | 1000 | 1000 | Capex | Utility Owned | Gram Power | Utility | 0 | 1000 | 1000 | 0 | 0 | 1000 | 0 | 1000 | 0 | Grand Total | 212929079 | #REF! | 5751743 | 1665485 | 745659 | 181000 | 24280 | 110874
Chandigarh | CED | Sub Div 5 | Ongoing | 29433 | 0 | 29433 | 0 | Capex | NSGM | Genus, Synergy | RECPDCL | 0 | 24214 | 0 | 0 | 0 | 24214 | 0 | 24214 | 0
Chhattisgarh | CSPDCL | - | Proposed | 5962115 | 5962115 | 0 | 0 | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delhi | NDMC | NDMC Area | Ongoing | 64713 | 0 | 64713 | 0 | Opex | Utility Owned | Larsen Toubro | EESL | 355 | 65059 | 0 | 0 | 0 | 65059 | 0 | 65059 | 0
Delhi | TPDDL | North Delhi | Completed | 195000 | 0 | 195000 | 0 | Capex | Utility Owned | Landis Gyr | Utility | 0 | 195000 | 0 | 0 | 0 | 195000 | 0 | 195000 | 0
Goa | Goa PD | - | Proposed | 741160 | 741160 | 0 | 0 | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gujarat | UGVCL | Naroda | Completed | 23760 | 0 | 23760 | 0 | Capex | SG Pilot | Genus | Utility | 0 | 23760 | 0 | 0 | 0 | 23760 | 0 | 23760 | 0
Gujarat | DGVCL | All Districts | Tendering | 4078120 | 4078120 | #REF! | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gujarat | MGVCL | All Districts | Tendering | 3299991 | 3299991 | #REF! | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gujarat | PGVCL | All Districts | Tendering | 5583509 | 5583509 | #REF! | #REF! | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gujarat | UGVCL | All Districts | Tendering | 3520251 | 3520251 | #REF! | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Haryana | UHBVNL | Panipat | Completed | 10188 | 0 | 10188 | 0 | Capex | SG Pilot | NEDO | Utility | 0 | 10188 | 0 | 0 | 0 | 10188 | 0 | 10188 | 0
Haryana | DHBVNL | Across Haryana | Ongoing | 500000 | 0 | 500000 | 0 | Opex | Utility Owned | Larsen Toubro | EESL | 59776.5 | 242521 | 501 | 15500 | 0 | 242521 | 8095 | 234426 | 0
Haryana | UHBVNL | Across Haryana | Ongoing | 500000 | 0 | 500000 | 0 | Opex | Utility Owned | Larsen Toubro | EESL | 59776.5 | 405171 | 958 | 15500 | 0 | 405171 | 13735 | 391436 | 0
Haryana | DHBVNL | All Districts | Proposed | 4165618 | 4165618 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Haryana | UHBVNL | All Districts | Proposed | 3240000 | 3240000 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Haryana | POWERGRID | Manesar | Completed | 10 | 0 | 10 | 0 | Capex | SG Pilot | Genus | Utility | 0 | 10 | 0 | 0 | 0 | 10 | 0 | 10 | 0
Himachal Pradesh | HPSEBL | Kala Amb | Completed | 1335 | 0 | 1335 | 0 | Capex | SG Pilot | General Electric | Utility | 0 | 1335 | 0 | 0 | 0 | 1335 | 0 | 1335 | 0
Himachal Pradesh | HPSEBL | Shimla, Dharamshala | Completed | 75712 | 0 | 75712 | 0 | Capex | IPDS | Schneider Electric | PFCCL | 0 | 75712 | 0 | 0 | 0 | 75712 | 0 | 75712 | 0
Himachal Pradesh | HPSEBL | Shimla, Dharamshala | Ongoing | 76028 | 0 | 76028 | 0 | Capex | Utility Owned | Schneider Electric | PFCCL | 1994 | 75303 | 0 | 0 | 0 | 75303 | 0 | 75303 | 0
Himachal Pradesh | HPSEBL | All Districts | Tendering | 2800945 | 2800945 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jammu and Kashmir | JPDCL & KPDCL | Jammu and Srinagar | Ongoing | 127050 | 0 | 127050 | 0 | Capex | PMDP | Techno Electric | RECPDCL | 2384 | 124666 | 0 | 0 | 0 | 124666 | 0 | 124666 | 277
Jammu and Kashmir | JPDCL & KPDCL | Jammu and Kashmir (Lot A) | Ongoing | 307766 | 0 | 307766 | 0 | DBFOOT | PMDP | Anvil Cables | RECPDCL | 14372 | 84954 | 0 | 30000 | 6170 | 78784 | 11164 | 67620 | 16784
Jammu and Kashmir | JPDCL & KPDCL | Jammu and Kashmir (Lot B) | Ongoing | 250672 | 0 | 250672 | 0 | DBFOOT | PMDP | Techno Electric | RECPDCL | 41420 | 17364 | 0 | 20000 | 11844 | 5520 | 5520 | 0 | 0
Jammu and Kashmir | JPDCL | - | Proposed | 721346 | 721346 | 0 | 0 | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jammu and Kashmir | KPDCL | - | Proposed | 685699 | 685699 | 0 | 0 | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jharkhand | JBVNL | All Districts | Proposed | 1341306 | 1341306 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Karnataka | CESCOM | Mysuru | Completed | 20916 | 0 | 20916 | 0 | Capex | SG Pilot | Enzen Global | Utility | 0 | 20916 | 0 | 0 | 0 | 20916 | 0 | 20916 | 0
Kerala | Cochin Port | Cochin Port | Completed | 805 | 0 | 805 | 0 | Capex | IPDS | Nsoft India | Utility | 0 | 805 | 0 | 0 | 0 | 805 | 0 | 805 | 0
Kerala | KSEBL | All Districts | Proposed | 13248923 | 13248923 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kerala | TCED | Thrissur | Proposed | 40438 | 40438 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Madhya Pradesh | MP-West | 5 Towns | Completed | 124477 | 0 | 124477 | 0 | Capex+Opex | IPDS | MP Smart Grid | Utility | 0 | 124477 | 0 | 0 | 0 | 124477 | 0 | 124477 | 0
Madhya Pradesh | MP-West | Included above | Ongoing | 225523 | 0 | 225523 | 0 | Capex+Opex | Utility Owned | MP Smart Grid | Utility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Madhya Pradesh | MP-East​ | All Districts | Partially Awarded | 5144451 | 5144451 | #REF! | #REF! | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Madhya Pradesh | MP-Central​ | All Districts | Tendering | 3955918 | 3955918 | #REF! | #REF! | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Madhya Pradesh | MP-West​ | All Districts | Partially Awarded | 3879733 | 3879733 | #REF! | #REF! | Totex | RDSS | - | PFC | 1945 | 26800 | 0 | 12000 | 1358 | 25442 | 10471 | 14971 | 5494
Madhya Pradesh | MP-West | Indore | Completed | 118836 | 0 | 118836 | 0 | Capex | IPDS | Larsen Toubro | Utility | 0 | 118836 | 0 | 0 | 0 | 118836 | 0 | 118836 | 0
Maharashtra | MSEDCL | All Districts | Tendering | 22488866 | 22488866 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maharashtra | BEST | Mumbai City | Awarded | 1075881 | 1075881 | 1075881 | 1075881 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Manipur | MSPDCL | - | Proposed | 154400 | 154400 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Meghalaya | MePDCL | - | Proposed | 460000 | 460000 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mizoram | Mizoram PD | - | Proposed | 289383 | 289383 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Nagaland | Nagaland PD | - | Proposed | 317210 | 317210 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Odisha | OPTCL | Across Odisha | Completed | 4000 | 0 | 4000 | 0 | BOOT | Utility Owned | JnJ | Utility | 0 | 4000 | 0 | 0 | 0 | 4000 | 0 | 4000 | 0
Odisha | Paradip Port | Paradip | Completed | 500 | 0 | 500 | 0 | Capex | Utility Owned | Gram Power | Utility | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 500 | 0
Puducherry | PED | Puducherry | Completed | 28910 | 0 | 28910 | 0 | Capex | SG Pilot | Dongfang Electronics | Utility | 0 | 28910 | 0 | 0 | 0 | 28910 | 0 | 28910 | 0
Puducherry | PED | Puducherry | Completed | 1658 | 0 | 1658 | 0 | Capex | Utility Owned | Multiple Vendors | Utility | 0 | 1658 | 0 | 0 | 0 | 1658 | 0 | 1658 | 0
Puducherry | PED | All districts | Tendering | 403767 | 403767 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Punjab | PSPCL | Ludhiana | Completed | 88107 | 0 | 88107 | 0 | Capex | IPDS | PSPCL, HPL | Utility | 0 | 88107 | 0 | 0 | 0 | 88107 | 0 | 88107 | 0
Punjab | PSPCL | Ludhiana | Ongoing | 7893 | 0 | 7893 | 0 | Capex | Utility Owned | PSPCL, HPL | Utility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Punjab | PSPCL | All districts | Proposed | 8784807 | 8784807 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rajasthan | JaVVNL | Jaipur and Tonk | Completed | 240820 | 0 | 240820 | 0 | Capex | IPDS | Genus | Utility | 0 | 240820 | 0 | 0 | 0 | 240820 | 0 | 240820 | 0
Rajasthan | JaVVNL | Jaipur and Tonk | Ongoing | 40980 | 0 | 40980 | 0 | Capex | Utility Owned | Genus | Utility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rajasthan | AVVNL | 66 Towns (Part) | Completed | 68673 | 0 | 68673 | 0 | Opex | IPDS | BOSCH | EESL | 0 | 68673 | 0 | 0 | 0 | 68673 | 0 | 68673 | 0
Rajasthan | AVVNL | 66 Towns (Part) | MI on Hold | 122149 | 0 | 122149 | 0 | Opex | Utility Owned | BOSCH | EESL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rajasthan | JdVVNL | Jodhpur | Completed | 56027 | 0 | 56027 | 0 | Opex | IPDS | BOSCH | EESL | 0 | 56027 | 0 | 0 | 0 | 56027 | 0 | 56027 | 0
Rajasthan | JdVVNL | Jodhpur | MI on Hold | 46155 | 0 | 46155 | 0 | Opex | Utility Owned | BOSCH | EESL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rajasthan | AVVNL | Ajmer | Completed | 1000 | 0 | 1000 | 0 | Capex | Utility Owned | Radius, JnJ | Utility | 0 | 1000 | 0 | 0 | 0 | 1000 | 0 | 1000 | 0
Rajasthan | JaVVNL | 6 Towns | Ongoing | 150000 | 0 | 150000 | 0 | Hybrid | NSGM | Genus | Utility | 13300 | 135944 | 0 | 2000 | 908 | 135036 | 866 | 134170 | 789
Rajasthan | JaVVNL | Kota | Completed | 70000 | 0 | 70000 | 0 | Capex | Utility Owned | Genus | Utility | 0 | 70000 | 0 | 0 | 0 | 70000 | 0 | 70000 | 0
Rajasthan | AVVNL | - | Proposed | 5432231 | 5432231 | 0 | 0 | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rajasthan | JdVVNL | - | Proposed | 4080082 | 4080082 | 0 | 0 | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rajasthan | JVVNL | - | Proposed | 4762643 | 4762643 | 0 | 0 | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sikkim | Sikkim PD | - | Proposed | 144680 | 144680 | 0 | 0 | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tamil Nadu | TANGEDCO | Chennai | Ongoing | 141000 | 0 | 141000 | 0 | Capex | Utility Owned | Genus | Utility | 13187 | 126510 | 0 | 0 | 0 | 126510 | -1920 | 128430 | 449
Tamil Nadu | TANGEDCO | - | Proposed | 30000000 | 30000000 | 0 | 0 | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tripura | TSECL | - | Proposed | 547489 | 547489 | 0 | 0 | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tripura | TSECL | Agartala | Completed | 43081 | 0 | 43081 | 0 | Capex | SG Pilot | Wipro | Utility | 0 | 43081 | 0 | 0 | 0 | 43081 | 0 | 43081 | 0
Telangana | TSSPDCL | Jeedimetla | Completed | 8882 | 0 | 8882 | 0 | Capex | SG Pilot | ECIL | Utility | 0 | 8882 | 0 | 0 | 0 | 8882 | 0 | 8882 | 0
Uttar Pradesh | IITK | Kanpur | Completed | 28 | 0 | 28 | 0 | Capex | SG Pilot | Synergy | Utility | 0 | 28 | 0 | 0 | 0 | 28 | 0 | 28 | 0
Uttar Pradesh | MVVNL | Lucknow | Ongoing | 905769 | 0 | 905769 | 0 | Opex | Utility Owned | Larsen Toubro | EESL | 17163 | 380731 | 3337 | 0 | 0 | 380731 | 0 | 380731 | 0
Uttar Pradesh | PVVNL | Meerut | MI on Hold | 1164138 | 0 | 1164138 | 0 | Opex | Utility Owned | Larsen Toubro | EESL | 17163 | 198726 | 20 | 0 | 0 | 198726 | 0 | 198726 | 0
Uttar Pradesh | DVVNL | Agra | MI on Hold | 628686 | 0 | 628686 | 0 | Opex | Utility Owned | Larsen Toubro | EESL | 17163 | 147991 | 127 | 0 | 0 | 147991 | 0 | 147991 | 0
Uttar Pradesh | PuVVNL | Varanasi | MI on Hold | 1147102 | 0 | 1147102 | 0 | Opex | Utility Owned | Larsen Toubro | EESL | 17163 | 321433 | 1135 | 0 | 0 | 321433 | 0 | 321433 | 0
Uttar Pradesh | KESCO | Kanpur | Ongoing | 156532 | 0 | 156532 | 0 | Opex | Utility Owned | Larsen Toubro | EESL | 17163 | 134727 | 98577 | 6000 | 0 | 134727 | 5575 | 129152 | 0
Uttar Pradesh | DVVNL | - | Proposed | 5354069 | 5354069 | 0 | 0 | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Uttar Pradesh | KESCO | - | Proposed | 625000 | 625000 | 0 | 0 | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Uttar Pradesh | MVVNL | - | Proposed | 7528737 | 7528737 | 0 | 0 | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Uttar Pradesh | PVVNL | - | Proposed | 6143261 | 6143261 | 0 | 0 | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Uttar Pradesh | PuVVNL | - | Proposed | 7327988 | 7327988 | 0 | 0 | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Uttarakhand | UPCL | All districts | Proposed | 1584205 | 1584205 | 0 | 0 | Totex | RDSS | - | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
West Bengal | WBSEDCL | Siliguri | Completed | 5164 | 0 | 5164 | 0 | Capex | SG Pilot | Chemtrols | Utility | 0 | 5164 | 0 | 0 | 0 | 5164 | 0 | 5164 | 0
West Bengal | CESC | Kolkata | Completed | 10000 | 0 | 10000 | 0 | Capex | Utility Owned | Genus, Secure | Utility | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0
West Bengal | WBSEDCL | - | Proposed | 20717969 | 20717969 | 0 | 0 | Totex | RDSS | - | REC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## NPMU (hidden)
Monthly report for monitoring implementation of smart meters in the country (Status as on last date of a month to be submitted by 5th of ensuing month)
Part A: Details of Smart meter projects | [16 empty] | Part A1: Consumer metering in DISCOMs
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
S No. | State | Utility | Project Area(s) | Project Scope (Covers Smart Meters/ HES/ MDM) | Project Status (Completed/Ongoing/Tendered/Proposed) | Nos. of Smart Meters Sanctioned |  |  |  | Project Cost |  |  | Business Model (Capex/Opex/Hybrid) | Scheme under which it is funded (Revamped/ IPDS/ NSGM/ Own) | Implementation Agency |  | Total Nos. of metered consumers in the utility as on date | Nos. of metered consumers in the utility which are of type Smart meter/Smart prepaid | Nos. of metered consumers in the utility which are of type Simple prepaid
[6 empty] | @Consumer level |  | @DT Level | @Feeder Level | CAPEX | OPEX |  |  |  | Agency | Vendor
[6 empty] | of Smart type | of Smart Prepaid type |  |  |  | Cost/meter/month (Rs.) | Contract Period (Months)
1 | Andaman | EDANI** | Aberdeen Bazar, Bambooflat, Chakkargaon, Chouldari, Dairy Farm, Ferrargunj, Haddo, Manglutan, Phoneix Bay, Prem Nagar, Prothrapur, Shadipur, Sippighat, Wimberligunj | All above | Completed | 36800 |  |  |  |  | 29 | 96 | Opex | IPDS | EESL | BOSCH
2 |  | EDANI** |  | All above | Ongoing | 28102
3 |  | EDANI |  | All above | Completed | 38400 |  |  |  |  | 29 | 96 | Opex | DDUGJY | EESL | BOSCH
4 | Andhra Pradesh | EPDCL | Vishakapatnam | All above | Completed | 2000 | [6 empty] | Capex | Utility owned |  | Gram Power
5 |  | APSPDCL* | All Districts | All above | Tendering | 2302644 | 2302644 | 102246 | 9741 |  |  | 93 | Totex | RDSS
6 |  | APCPDCL* | All Districts | All above | Tendering | 2050962 | 2050962 | 113650 | 3726 |  |  | 93 | Totex | RDSS
7 |  | APEPDCL* | All Districts | All above | Tendering | 1255240 | 1255240 | 77244 | 3891 |  |  | 93 | Totex | RDSS
8 | Assam | APDCL | Guwahati and Dibrugarh | All above | Completed | 70000 |  |  |  | Rs. 57.74 Crs |  |  | Capex | Utility owned |  | Anvil Cables & Sinhal Udyog
9 |  | APDCL | Guwahati | All above | Completed | 14519 |  |  |  | Rs. 19.16 Crs |  |  | Capex | SG Pilot |  | Fluent Grid
10 |  | APDCL | Selected areas of Jorhat, Silchar and Guwahati Town | All above | Completed | 134000 |  |  |  | Rs. 108.93 Crs |  |  | Capex | Utility owned |  | M/s Anvil Cables Pvt Ltd consortium with M/s Sinhal Udyog
11 |  | APDCL | Selected areas of Kokrajhar, Goalpara, Nalbari and Guwahati Town | All above | Completed | 134000 |  |  |  | Rs. 113.90 Crs |  |  | Capex | Utility owned |  | M/s Purbanchal Enterprise (Meter Make: Landis Gyr)
12 |  | APDCL | DBFOOT - I, Package - I - Nagaon, Morigaon,KANCH, Cachar, Badarpur, Jorhat , Golaghat, Sivsagar, Dibrugarh, Tinsukia, GEC-I | All above | Ongoing | 363500 | 363500 |  |  | 0 | 106.61 | 90 meter-months from the date of Contract 08.12.2021 | TOTEX | RDSS/Own |  | M/s Intellismart Infrastructure Private Ltd, New Delhi
13 |  | APDCL | DBFOOT - I, Package - II -Kokrajhar, Bongaigaon, Barpeta, Rangia, Mangaldoi, Tezpur, North Lakhimpur, GEC-II | All above | Ongoing | 256600 | 256600 |  |  | 0 | 106.61 | 90 meter-months from the date of Contract 08.12.2021 | TOTEX | RDSS/Own |  | M/s Intellismart Infrastructure Private Ltd, New Delhi
14 |  | APDCL | Urban areas of all remaining 17 Electrical Circles | All above | Ongoing | 0 | 0 | 17000 | 0 | 56.87 | 0 | Project Completion Timeline is 15 months from the date of issue of LoA after which FMS will start for 7 years. | Capex | SOPD |  | M/s Anvil Cables Pvt. Ltd
15 |  | APDCL | Bongaigaon & Kokrajhar Circle | All above | Awarded | 681303 | 680400 | 11353 | 234 | 98.1 | 85.55 | 93 meter-months from the date of contract 02.03.2023 | TOTEX | RDSS |  | M/s Apraava Smart Meter Private Limited
16 |  | APDCL | Badarpur & Cachar Circle | All above | Awarded | 692022 | 691000 | 11872 | 323 | 99.92 | 88 | 93 meter-months from the date of contract | TOTEX | RDSS |  | Genus Power Infrastructure Limited
17 |  | APDCL | Nagaon & Golaghat Circle | All above | Awarded | 712328 | 711200 | 11740 | 299 | 102.54 | 85.23 | 93 meter-months from the date of contract | TOTEX | RDSS |  | Hi-Print Metering Solutions Private Limited
18 |  | APDCL | Jorhat, Sivasagar & Tinsukia Circle | All above | Awarded | 735964 | 733800 | 18044 | 600 | 109.36 | 91.41 | 93 meter-months from the date of contract | TOTEX | RDSS |  | Genus Power Infrastructure Limited
19 |  | APDCL | Barpeta & Rangia Circle | All above | Awarded | 753613 | 749300 | 11134 | 878 | 108.5 | 85.86 | 93 meter-months from the date of contract | TOTEX | RDSS |  | Hi-Print Metering Solutions Private Limited
20 |  | APDCL | Mangaldoi, Tezpur & North Lakhimpur Circle | All above | Awarded | 758986 | 757700 | 13404 | 448 | 109.85 | 98.8 | 93 meter-months from the date of contract | TOTEX | RDSS |  | Adani Transmission Limited
|  | APDCL | - | All above | Proposed | 790382 | 790382 | [5 empty] | TOTEX | RDSS
21 | Arunachal Pradesh | Arunachal PD | - | All above | Proposed | 287445 | 287445 | 10116 | 688 |  |  |  | TOTEX | RDSS
22 | Bihar | NBPDCL | Motihari, Barauni, Dalsingsarai, Begusarai, Rosera, Bettiah, Sheohar, Muzaffarpur(W), Mahua, Hazipur,Darbhanga(R), Katihar, Supaul, Samastipur, Muzaffarpur(U-I), Ishanganj, Gopalganj, Madhubani, Siwan, Saharsa, Purnea, Forbisganj, Purnea (East), Madhepura, Jhanjharpur, Muzaffarpur(E), Sitamarhi, Khagaria, Chapra(W), Chapra(E), Bagha, Raxaul, Muzaffarpur(U-Ii), Bhagalpur(U), Patna, Gaya(U), Khagaul, Arwal, Bhagalpur(E), Bihta, Buxar, Biharsarif, Rajgir, Ekangarsarai, Jagdishpur, Nawada, Rajauli, Dehrionsone, Aurangabad, Banka, Barh, Bhabhua, Dakbanglow (Poc), Daudnagar, Gaya(R), Sherghati, Jahanabad, Jamui, Lakhisarai, Manpur, Amarpur, Naugachia, Munger, Patna Rural (Poc), Sasaram, Arrah, Masaurhi, Fatuha | All above | Ongoing | 1030000 | 1030000 | 143683 | 3806 | NA |  |  | TOTEX | RDSS | EESL | EDF
23 |  | SBPDCL |  | All above | Ongoing | 1320000 | 1320000 | 107043 | 2621 | NA |  |  | TOTEX | RDSS | EESL | EDF
24 |  | SBPDCL | Gaya Rural and Urban,Manpur division | All above | Ongoing | 40500 | 40500 | [5 empty] | Opex | Utility owned |  | Gram Power India Private Limited
25 |  | IPCL | Bodhgaya | All above | Completed | 17100 | 17100 | [5 empty] | Capex | Utility owned |  | Gram Power India Private Limited
26 |  | BEDCPL/SPML | Bhagalpur | All above | Completed | 1000 | 1000 | [5 empty] | Capex | Utility owned |  | Gram Power India Private Limited
27 | Chandigarh | CED | Chandigarh (Sub Div-5) | All above | Ongoing | 29433 |  |  |  | Rs. 28.58 Crs |  |  | Capex | NSGM | RECPDCL | Genus, Synergy Signals & Systems
28 | Chhattisgarh | CSPDCL | - | All above | Proposed | 5962115 | 5962115 | 210644 | 6720 |  |  |  | TOTEX | RDSS
29 | Delhi | NDMC | New Delhi Area | All above | Ongoing | 64713 |  |  |  |  | 83.84 | 66 | Opex | Utility owned | EESL | L&T
30 |  | TPDDL | North Delhi | All above | Completed | 195000 | [7 empty] | Utility owned |  | Landis + Gyr
31 | Goa | Goa PD | - | All above | Proposed | 741160 | 741160 | 8369 | 827 |  |  |  | Totex | RDSS
32 | Gujarat | UGVCL | Naroda | All above | Completed | 23760 |  |  |  | Rs. 23.18 Crs |  |  | Capex | SG Pilot |  | Genus
33 |  | DGVCL* | All Districts | All above | Tendering | 4078120 | 4078120 | 82336 | 0 |  |  | 93 | Totex | RDSS
34 |  | MGVCL* | All Districts | All above | Tendering | 3299991 | 3299991 | 56129 | 0 |  |  | 93 | Totex | RDSS
35 |  | PGVCL* | All Districts | All above | Tendering | 5583509 | 5583509 | 109130 | 0 |  |  | 93 | Totex | RDSS
36 |  | UGVCL* | All Districts | All above | Tendering | 3520251 | 3520251 | 52892 | 0 |  |  | 93 | Totex | RDSS
37 | Haryana | UHBVNL | Panipat | All above | Completed | 10188 |  |  |  | NA |  |  | Capex | SG Pilot |  | NEDO
38 |  | SGKC Lab | Gurugram | All above | Completed | 10 |  |  |  | Rs. 5.96 Crs |  |  | Capex | SG Pilot |  | Genus
39 |  | DHBVNL | Gurugram, Faridabad, Karnal, Panipat, Gharaunda, Panchkula, Kalka, Pinjore | All above | Ongoing | 500000 |  |  |  |  | 86.98 | 96 | Opex | Utility owned | EESL | L&T
40 |  | UHBVNL |  | All above | Ongoing | 500000 |  |  |  |  | 86.98 | 96 | Opex | Utility owned | EESL | L&T
41 |  | DHBVNL* | All Districts |  | Proposed | 4165618 | 4165618 | 128340 | 6604 |  |  |  | NA |  |  |  | Decision regardgin Business Model yet to be taken hence RfP issuance is delaying |  |  | Decision regardgin Business Model yet to be taken hence RfP issuance is delaying
42 |  | UHBVNL* | All Districts |  | Proposed | 3240000 | 3240000 | 66979 | 6600 |  |  |  | NA
43 | Himanchal Pradesh | HPSEBL | Kala Amb | All above | Completed | 1335 |  |  |  | Rs. 19.44 Crs |  |  | Capex | SG Pilot |  | GE T&D
44 |  | HPSEBL | Shimla, Dharamshala | All above | Completed | 75712 | Configurable to work in Pre-Paid |  |  | Rs. 83.03 Cr | 76.972 |  | Capex | IPDS | PFCCL | SEIPL
45 |  | HPSEBL | Shimla, Dharamshala | All above | Ongoing | 76028 | Configurable to work in Pre-Paid | [5 empty] | Capex | Utility owned | PFCCL | SEIPL
46 |  | HPSEBL* | All Districts | All above | Tendering | 2800945 | 2800945 | 39012 | 1951 |  |  |  | TOTEX | RDSS
47 | Jammu & Kashmir | JPDCL & KPDCL | Jammu & Srinagar Towns | All above | Ongoing | 127050 |  |  |  | 125.77 Cr |  |  | Capex | PMDP | RECPDCL | Techno Electric
48 | Jammu & Kashmir | JPDCL & KPDCL | Jammu & Kashmir Region (Lot A) | All above | Ongoing | 307766 |  |  |  | 90 Cr | 1-ph-₹ 36, 3-ph-₹ 46, LTCT Consumer-₹ 153 LTCT DT-₹ 154, CTPT Consumer-₹ 131 |  | DBFOOT | PMDP | RECPDCL | Anvil Cables
49 | Jammu & Kashmir | JPDCL & KPDCL | Jammu & Kashmir Region (Lot B) | All above | Ongoing | 250672 |  |  |  | 90 Cr | 1-ph-₹ 66, 3-ph-₹ 82, LTCT Consumer-₹ 120 LTCT DT-₹ 164, CTPT Consumer-₹ 196 |  | DBFOOT | PMDP | RECPDCL | Techno Electric
50 | Jammu & Kashmir | JPDCL | - | All above | Proposed | 721346 | 721346 | 47367 | 1123 |  |  |  | TOTEX | RDSS
51 | Jammu & Kashmir | KPDCL | - | All above | Proposed | 685699 | 685699 | 40670 | 1485 |  |  |  | TOTEX | RDSS
52 | Jharkhand | JBVNL* | All Districts | All above | Proposed | 1341306 | 1341306 | 19512 | 1226 |  |  |  | Totex | RDSS
53 | Karnataka | CESC | Mysore | All above | Completed | 20916 |  |  |  | Rs. 32.56 Crs |  |  | Capex | SG Pilot |  | Enzen Global
54 | Kerala | CPT | Cochin Port | All above | Completed | 805 | [6 empty] | Capex | IPDS ST&D
55 |  | KSEBL* | All Districts | All above | Proposed | 13248923 | 13248923 | 87168 | 6003 |  |  |  | Totex | RDSS
56 |  | TCED* | Thrissur | All above | Proposed | 40438 | 40438 | 447 | 22 |  |  |  | Totex | RDSS
57 | MP | MP-West** | Dewas, Ujjain, Ratlam, Mhow, Khargone | All above | Completed | 124477 |  |  |  | Rs. 123.90 Crs. | Rs. 135.87 Crs. (Rs. 64.70 per node per month) | 30 (implementation)+ 60 (O&M) | Capex+Opex | IPDS |  | MP Smart grid pvt ltd
58 |  | MP-West** | Dewas, Ujjain, Ratlam, Mhow, Khargone | All above | Ongoing | 225523 | [6 empty] | Capex+Opex | Utility owned |  | MP Smart grid pvt ltd
59 |  | MP-West | Indore city | All above | Completed | 118836 |  |  |  | Rs. 59.34 Crs. | Rs.15.62 Crs. (Rs. 78.10 Lakhs per quarter) | 24 (implementation)+ 60 (O&M) | Capex | IPDS ST&D |  | L&T
60 |  | MP-East​* | All Districts | All above | Awarded | 5144451 | 5144451 | 130721 | 0 |  | 80.56 | 90 | Totex | RDSS |  | L1 declared - M/s Montecarlo (Indore Discom). LoA Awarded
61 |  | MP-Central​* | All Districts | All above | Tendered | 3955918 | 3955918 | 173746 | 6127 |  |  | 90 | Totex | RDSS
62 |  | MP-West​* | All Districts | All above | Awarded | 3879733 | 3879733 | 102036 | 2284 |  | 96.17 | 90 | Totex | RDSS |  | L1 declared - BCITS (Indore Discom). LoA awarded
63 | Maharashtra | MSEDCL* | All Districts | All above | Tendering | 22488866 | 22488866 | 407507 | 27826 |  |  |  | Totex (Hybrid) | RDSS
64 |  | BEST* | Mumbai City | All above | Awarded | 1075881 | 1075881 | 3398 | 1388 |  |  | 99.32 | TOTEX | RDSS |  | L1 Identified-M/s Adani. LoA issued on 30.09.2022
65 | Manipur | MSPDCL | - | All above | Proposed | 154400 | 154400 | 11451 | 357 |  |  |  | TOTEX | RDSS
66 | Meghalaya | MePDCL | - | All above | Proposed | 460000 | 460000 | 11419 | 1324 |  |  |  | TOTEX | RDSS
67 | Mizoram | Mizoram PD | - | All above | Proposed | 289383 | 289383 | 2300 | 398 |  |  |  | TOTEX | RDSS
68 | Nagaland | Nagaland PD | - | All above | Proposed | 317210 | 317210 | 6276 | 392 |  |  |  | TOTEX | RDSS
69 | Odisha | OPTCL | Across Odisha | All above | Completed | 4000 | [6 empty] | NA | Utility owned |  | JnJ
70 |  | Paradip Port Trust | Paradip | All above | Completed | 500 | [6 empty] | Capex | Utility owned |  | Gram Power India Private Limited
71 | Puducherry | PED | Puducherry | All above | Completed | 28910 |  |  |  | Rs. 35.43 Crs |  |  | Capex | SG Pilot |  | Dongfang Electronics
72 |  | PED | Puducherry | All above | Completed | 1658 | [6 empty] | NA | Utility owned |  | Multiple Vendors
73 |  | PED* | All districts | All above | Tendering | 403767 | 403767 | 3105 | 180 |  |  |  | Totex | RDSS
74 | Punjab | PSPCL** | Punjab | All above | Completed | 88107 |  |  |  | Rs. 50.99 Crs | Rs.19.80 Crs (Rs. 99 Lakhs per quarter) | 11 (implementation)+ 60 (O&M) | Capex | IPDS |  | PSPCL and HPL
75 |  | PSPCL | Punjab | All above | Ongoing | 7893 | [6 empty] | Capex | Utility owned |  | PSPCL and HPL
76 |  | PSPCL* | All districts | All above | Proposed | 8784807 | 8784807 | 184044 | 12563 |  |  |  | Totex | RDSS
78 | Rajasthan | AVVNL** | Makarana and Pushkar | All above | Ongoing | 68673 |  |  |  |  | 64 | 120 | Opex | IPDS | EESL | BOSCH
79 |  | AVVNL** | Makarana and Pushkar | All above | Ongoing | 122149 |  |  |  |  | 64 | 120 | Opex | Utility owned | EESL | BOSCH
80 |  | AVVNL | Satguru Colony, Ajmer | All above | Completed | 1000 | [6 empty] | NA | Utility owned |  | Radius, JnJ
81 |  | JaVVNL** | Jaipur City and Tonk Circle | All above | Ongoing | 240820 |  |  |  | Rs. 149.95 Crs. | Rs. 43.79 Crs. (Rs. 2.19 Crs per quarter) | 12 (implementation) + 60 (O&M) | Capex | IPDS |  | Genus Power (GPIL)
82 |  | JaVVNL** | Jaipur City and Tonk Circle | All above | Ongoing | 40980 | [6 empty] | Capex | Utility owned |  | Genus Power (GPIL)
83 |  | JaVVNL | Urban consumers on Baran, Bundi, Bharatpur, Jhalawar, Karauli, Dholpur Circles | All above | Ongoing | 150000 | All smart meters are having functionality of Smart Prepaid Type | NA | NA | Rs. 87.43 Crs. | 45.3 | 60 months | Hybrid | NSGM |  | Genus
84 |  | JaVVNL | Kota | All above | Completed | 70000 | [6 empty] | Capex | Utility owned |  | Genus
85 |  | JdVVNL** | Jodhpur | All above | Ongoing | 56027 |  |  |  |  | 64 | 120 | Opex | IPDS | EESL | BOSCH
86 |  | JdVVNL** | Jodhpur | All above | Ongoing | 46155 |  |  |  |  | 64 | 120 | Opex | Utility owned | EESL | BOSCH
87 |  | AVVNL | - | All above | Proposed | 5432231 | 5432231 | 155453 | 11007 |  |  |  | Totex | RDSS
88 |  | JdVVNL | - | All above | Proposed | 4080082 | 4080082 | 167809 | 10322 |  |  |  | Totex | RDSS
89 |  | JVVNL | - | All above | Proposed | 4762643 | 4762643 | 111346 | 5799 |  |  |  | Totex | RDSS
90 | Sikkim | Sikkim PD | - | All above | Proposed | 144680 | 144680 | 3229 | 633 |  |  |  | Totex | RDSS
91 | Tamil Nadu | TANGEDCO | Chennai (MoU with Smart Cities) | All above | Ongoing | 141000 | [6 empty] | Capex | Utility owned |  | Genus
92 |  | TANGEDCO |  | All above | Proposed | 30000000 | 30000000 | 472500 | 18274 |  |  |  | Totex | RDSS
93 | Telangana | TSSPDCL | Jeedimetla | All above | Completed | 8882 |  |  |  | Rs. 34.93 Crs |  |  | Capex | SG Pilot |  | ECIL
94 | Tripura | TSECL | Aragtala | All above | Completed | 43081 |  |  |  | Rs. 63.43 Crs |  |  | Capex | SG Pilot |  | Wipro
95 |  | TSECL | - | All above | Proposed | 547489 | 547489 | 14908 | 473 |  |  |  | Totex | RDSS
96 | Uttar Pradesh | IITK | IIT Kanpur Campus | All above | Completed | 28 |  |  |  | Rs. 11.39 Crs |  |  | Capex | SG Pilot
97 |  | MVVNL | Prayagraj, Azamgarh, Barabanki, Faizabad, Farrukhabad, Gonda, Gorakhpur, Hardoi, Jhansi, Jaunpur, Lucknow, Mirzapur, Orai, Raibareilly, Sahjahanpur, Sultanpur, Unnao, Varanasi, Mughalsarai, Aligarh, Bareilly, Bulandshahar, Etawah, Mainpuri, Moradabad, Meerut, Mathura, Muzaffarnagar, Rampur, Saharanpur, Vrindavan, Firozabad, Hapur, Loni, Sikandrabad, Modinagar, Muradnagar, Khurja, Amroha, Kanpur | All above | Ongoing | 905769 |  |  |  |  | 85.95 | 96 | Opex | Utility owned | EESL | L&T
98 |  | PVVNL |  | All above | Ongoing | 1164138 |  |  |  |  | 85.95 | 96 | Opex | Utility owned | EESL | L&T
99 |  | DVVNL |  | All above | Ongoing | 628686 |  | 0 |  |  | 85.95 | 96 | Opex | Utility owned | EESL | EESL
100 |  | PuVVNL |  | All above | Ongoing | 1147102 |  |  |  |  | 85.95 | 96 | Opex | Utility owned | EESL | L&T
101 |  | KESCO |  | All above | Ongoing | 156532 |  |  |  |  | 85.95 | 96 | Opex | Utility owned | EESL | L&T
102 |  | DVVNL | - | All above | Proposed | 5354069 | 5354069 | 187910 | 4393 |  |  |  | Totex | RDSS
103 |  | KESCO | - | All above | Proposed | 625000 | 625000 | 6715 | 693 |  |  |  | Totex | RDSS
104 |  | MVVNL | - | All above | Proposed | 7528737 | 7528737 | 383158 | 1745 |  |  |  | Totex | RDSS
105 |  | PVVNL | - | All above | Proposed | 6143261 | 6143261 | 531164 | 9349 |  |  |  | Totex | RDSS
106 |  | PuVVNL | - | All above | Proposed | 7327988 | 7327988 | 417854 | 4694 |  |  |  | Totex | RDSS
107 | Uttarakhand | UPCL* | All Districts | All above | Proposed | 1584205 | 1584205 | 38016 | 1686 |  |  |  | Totex | RDSS
108 | West Bengal | WBSEDCL | Siliguri | All above | Completed | 5164 |  |  |  | Rs. 6.95 Crs |  |  | Capex | SG Pilot |  | Chemtrols
109 |  | CESC | Kolkata | All above | Completed | 10000 | [7 empty] | Utility owned |  | Genus & Secure
110 |  | WBSEDCL | - | All above | Proposed | 20717969 | 20717969 | 305419 | 11874 |  |  |  | Totex | RDSS
| Total |  |  |  |  | 212929079 | 204670964 | 5429008 | 193597 | [7 empty] | 0 | 0 | 0
Note -
* Data as shared by PFC regarding RDSS Projects
** Changes due to IPDS projects satuaration as per final installed quantity as shared by IPDS. As per PFC email dated 12.01.2023
Part B: Format for monitoring periodic progress
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
S No. | Utility | No of Smart meters implemented till 1st day of the Current month |  |  |  | Absolute Physical Progress till last week |  |  |  | Financial progress
|  | @Consumer level |  | @DT Level | @Feeder Level | Nos. of Smart Meters | No. of Smart Prepaid type | HES as on date | MDM as on date | in Rs. Lakhs | in %
|  | of Smart type (including Smart Prepaid) | of Smart Prepaid type
1 | APDCL (DBFOOT - I, Package - I) | 119828 | 102314 |  |  | 120666 | 102320 | Cyan Cannode/Crystle/PCP | Esyasoft
2 | APDCL (DBFOOT - I, Package - II) | 103260 | 55334 |  |  | 106422 | 55334 | Crystal Power/Cyan Cannode | Esyasoft
3 | DHBVN | 242521 | 501 |  |  | 242521 | 501 | Trilliant | Oracle
4 | UHBVN | 405171 | 958 |  |  | 405171 | 958 | Trilliant | Oracle
5 | NDMC | 65059 | 0 |  |  | 65059 | 0 | Fluent Grid | Fluent Grid
6 | MVVNL | 380731 | 3337 |  |  | 380731 | 3337 | Trilliant | Oracle
7 | PVVNL | 198726 | 20 |  |  | 198726 | 20 | Trilliant | Oracle
8 | DVVNL | 147991 | 127 |  |  | 147991 | 127 | Trilliant | Oracle
9 | PuVVNL | 321433 | 1135 |  |  | 321433 | 1135 | Trilliant | Oracle
10 | KESCO | 134727 | 98577 |  |  | 134727 | 98577 | Trilliant | Oracle
11 | NBPDCL | 582514 | 581728 |  |  | 582514 | 581728 | Scneider India | Siemens
12 | SBPDCL | 753819 | 753015 |  |  | 753819 | 753015 | Scneider India | Siemens
13 | AVVNL | 68673 | 0 |  |  | 68673 | 0 | Bosch | Fluent Grid
14 | JdVVNL | 56027 | 0 |  |  | 56027 | 0 | Bosch | Fluent Grid
15 | EDANI (IPDS) | 36800 | 0 |  |  | 36800 | 0 | Bosch | Fluent Grid
16 | EDANI (DDUGJY) | 38400 | 0 |  |  | 38400 | 0 | Bosch | Fluent Grid
17 | JaVVNL (IPDS) | 240820 | 0 |  |  | 240820 | 0 | Cyan Cannode | BCITS
18 | MP-West | 124477 | 0 |  |  | 124477 | 0 | Cyan Cannode | Esyasoft
19 | PSPCL | 88107 | 0 |  |  | 88107 | 0 | HPL | Analogics Tech
20 | HPSEB | 151015 | 0 |  |  | 151015 | 0 | Cyan Cannode | Esyasoft | 1499.99
21 | MP-West* (RDSS) | 25442 | 0 |  |  | 26800 | 0 | BCITS | Esya Soft
22 | JaVVNL (NSGM) | 135036 | 0 |  |  | 135036 | 0 | Cyan Cannode | BCITS | 3310.71
23 | CED | 24214 | 0 |  |  | 24214 | 0 | L+G | Analogics Tech | 1803 | 64
24 | JPDCL & KPDCL | 124666 | 0 |  |  | 124666 | 0 | L+G | Oracle | 11122.22 | 86
25 | JPDCL & KPDCL (Lot A) | 78784 | 0 |  |  | 81228 | 0 | Sinhal Udyog | Abjayon | 620 | 7
26 | JPDCL & KPDCL (Lot B) | 5520 | 0 |  |  | 8580 | 0
27 | TANGEDCO | 126510 | 0 |  |  | 126510 | 0 | Cyan Cannode | Esyasoft | 5996.4 | 41.5
Total |  | 4780271 | 1597046 | 0 | 0 | 4791133 | 1597052
Part C: Format for monitoring weekly progress
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 18
S No. | Utility | No of Smart meters implemented between 29th April 2023 to 4th May 2023 |  |  |  | Absolute Physical Progress |  |  |  | Financial progress |  | No of smart meters available at store | Project Completion Timeline | Target (Cuurent Month) | Achievement (Current Month) | Implementation issues | Remarks |  |  | Remarks
|  | @Consumer level |  | @DT Level | @Feeder Level | Nos. of Smart Meters | No. of Smart Prepaid type | HES as on date | MDM as on date | in Rs. Lakhs | in %
|  | of Smart type (including Smart Prepaid) | of Smart Prepaid type
1 | APDCL (DBFOOT - I, Pkg - I) | 0 | 0 |  |  | 120666 | 102320 | CyanConnode Crystal | Esyasoft |  |  | 139747 | 90 months from the date of Contract 08.12.2021 | 10000 | 838
2 | APDCL (DBFOOT - I, Pkg - II) | 0 | 0 |  |  | 106422 | 55334 | Ashoka Buildcon | Esyasoft |  |  | 122351 | 90 months from the date of Contract 08.12.2021 | 10000 | 3162
3 | DHBVN | 0 | 0 |  |  | 242521 | 501 | Trilliant | Oracle |  |  | 119553 | July 2022 (However as per agreement it is Dec'2023 and January 2024 for UHBVN and DHBVN respectively) | 31000 | 0 |  |  |  |  | Data not received for this week
4 | UHBVN | 0 | 0 |  |  | 405171 | 958 | Trilliant | Oracle | [10 empty] | Data not received for this week
5 | NDMC | 0 | 0 |  |  | 65059 | 0 | Fluent Grid | Fluent Grid |  |  | 355 | NDMC has already been saturated. The remaining meters are for new service connections | 0 | 0 |  |  |  |  | Data not received for this week
6 | MVVNL | 0 | 0 |  |  | 380731 | 3337 | Trilliant | Oracle |  |  | 85815 |  | 6000 | 0 |  |  |  |  | Data not received for this week
7 | PVVNL | 0 | 0 |  |  | 198726 | 20 | Trilliant | Oracle | [5 empty] | 0 |  |  |  |  | Data not received for this week
8 | DVVNL | 0 | 0 |  |  | 147991 | 127 | Trilliant | Oracle | [5 empty] | 0 |  |  |  |  | Data not received for this week
9 | PuVVNL | 0 | 0 |  |  | 321433 | 1135 | Trilliant | Oracle | [5 empty] | 0 |  |  |  |  | Data not received for this week
10 | KESCO | 0 | 0 |  |  | 134727 | 98577 | Trilliant | Oracle | [5 empty] | 0 |  |  |  |  | Data not received for this week
11 | NBPDCL | 0 | 0 |  |  | 582514 | 581728 | Scneider India | Siemens |  |  | 189236 | December 2022 (The earlier plan, before second wave of CoVid, was to complete MI by July 2022 as per the agreement. However due to CoVid the same needs to be relooked. | 60000 | 0 |  |  |  |  | Data not received for this week
12 | SBPDCL | 0 | 0 |  |  | 753819 | 753015 | Scneider India | Siemens | [10 empty] | Data not received for this week
13 | AVVNL | 0 | 0 |  |  | 68673 | 0 | Bosch | Fluent Grid |  |  | 0 | IPDS funding is closed | 0 | 0 | MI on Hold by Discom |  |  |  | Data not received for this week
14 | JdVVNL | 0 | 0 |  |  | 56027 | 0 | Bosch | Fluent Grid | [10 empty] | Data not received for this week
15 | EDANI (IPDS) | 0 | 0 |  |  | 36800 | 0 | Bosch | Fluent Grid |  |  | 0 | IPDS funding is closed | 0 | 0 | Communication issues due to poor network(BSNL ). CoVid imposed restrictions have been there, Force Majeure notice was issued to Discoms. |  |  |  | Data not received for this week
16 | EDANI (DDUGJY) | 0 | 0 |  |  | 38400 | 0 | Bosch | Fluent Grid |  |  |  |  | 0 | 0 |  |  |  |  | Data not received for this week
17 | JaVVNL (IPDS) | 0 | 0 |  |  | 240820 | 0 | Cyan Cannode | BCITS |  |  | 0 |  | 0 | 0 |  |  |  |  | Data not received for this week
18 | MP-West | 0 | 0 |  |  | 124477 | 0 | Cyan Cannode | Esyasoft |  |  | 0 |  | 0 | 0 |  |  |  |  | Data not received for this week
19 | PSPCL | 0 | 0 |  |  | 88107 | 0 | HPL | Analogics Tech |  |  | 0 |  | 0 | 0 |  |  |  |  | Data not received for this week | 0
20 | HPSEB | 0 | 0 |  |  | 151015 | 0 | Cyan Cannode | Esyasoft | 1499.99 |  | 1994 |  | 0 | 0 |  |  |  |  | Data not received for this week
21 | MP-West* (RDSS) | 0 | 0 |  |  | 26800 | 0 | BCITS | Esya Soft |  |  | 1945 | 2023-12-31 | 12000 | 1358
22 | JaVVNL (NSGM) | 908 | 0 |  |  | 135944 | 0 | Cyan Cannode | BCITS | 3310.71 |  | 13300 | 2022-03-01 | 2000 | 908 |  |  |  |  | Data not received for this week
23 | CED (SD-5) | 0 | 0 |  |  | 24214 | 0 | L+G | Analogics Tech | 1803 | 64 | 0 | 2022-03-01 | 0 | 0 |  |  |  |  | "Closure activity of the project is under progress 518 Nos. Smart Meters have been kept as O&M stock"
24 | JPDCL & KPDCL | 0 | 0 |  |  | 124666 | 0 | L+G | Oracle | 11122.22 | 86 | 2384 | 2023-03-30 | 0 | 0
25 | JPDCL & KPDCL (Lot A) | 3726 | 0 |  |  | 84954 | 0 | Sinhal Udyog | Abjayon | 620 | 7 | 14372 | 2023-10-31 | 30000 | 6170
26 | JPDCL & KPDCL (Lot B) | 8784 | 0 |  |  | 17364 | 0 |  |  |  |  | 41420 | 2023-10-31 | 20000 | 11844
27 | TANGEDCO | 0 | 0 |  |  | 126510 | 0 | CyanConnode | EsyaSoft | 5996.4 | 41.5 | 13187 | 28.12.2021 and AMC for 7yrs | 0 | 0 |  |  |  |  | Data not received for this week
Total |  | 13418 | 0 | 0 | 0 | 4804551 | 1597052 |  |  |  |  | 745659 |  | 181000 | 24280

## MoP_Summary (hidden)
MoP Summary | [15 empty] | Part A1: Consumer metering in DISCOMs
1 | 2 | 3 | 4 | 5 | 4 | 5 | 6 |  | 9 | 10 |  |  | 7 | 8 | 13 | 14 | 15 | 16 | 9 | 10
S No. | State | Utility | Project Area(s) | Project Scope (Covers Smart Meters/ HES/ MDM) | Project Status (Completed/Ongoing/Tendered/Proposed) | Nos. of Smart Meters Sanctioned |  |  |  | Project Cost |  |  | Business Model (Capex/Opex/Hybrid) | Scheme under which it is funded (Revamped/ IPDS/ NSGM/ Own) | Implementation Vendor | Total Nos. of metered consumers in the utility as on date | Nos. of metered consumers in the utility which are of type Smart meter/Smart prepaid | Nos. of metered consumers in the utility which are of type Simple prepaid | Nos. of Smart Meters Installed
[6 empty] | of Smart type | of Smart Prepaid type already included in Col 5 | Smart DT Meters | Smart Feeder Meters |  | Cost/meter/month (Rs.) | Contract Period (Months) | [6 empty] | of Smart type | of Smart Prepaid type already included in Col 9 | Smart prepaid meters till Last week
1 | Andaman | EDANI | Aberdeen Bazar, Bambooflat, Chakkargaon, Chouldari, Dairy Farm, Ferrargunj, Haddo, Manglutan, Phoneix Bay, Prem Nagar, Prothrapur, Shadipur, Sippighat, Wimberligunj | All above | Completed | 36800 | 0 |  |  |  | 29 | 96 | Opex | IPDS | BOSCH |  |  |  | 36800 | 0
2 | Andaman | EDANI |  |  | Ongoing | 27302 | 0 | [5 empty] | Opex |  | - |  |  |  | 0 | 0
3 | Andaman | EDANI |  |  | Ongoing | 39200 | 0 | [5 empty] | Opex |  | BOSCH |  |  |  | 38400 | 0
4 | Andhra Pradesh | EPDCL |  |  | Completed | 2000 | 0 | [5 empty] | Capex |  | Gram Power |  |  |  | 2000 | 0
5 |  | APSPDCL* |  |  | Tendering | 2302644 | 2302644 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
6 |  | APCPDCL* |  |  | Tendering | 2050962 | 2050962 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
7 |  | APEPDCL* |  |  | Tendering | 1255240 | 1255240 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
8 | Assam | APDCL | Guwahati and Dibrugarh | All above | Completed | 70000 | 0 | [5 empty] | Capex | Utility owned | Anvil Cables & Sinhal Udyog |  |  |  | 70000 | 2720 | 2720
9 |  | APDCL |  |  | Completed | 134000 | 0 | [5 empty] | Capex | Utility owned | Anvil Cables & Sinhal Udyog |  |  |  | 134000 | 7926 | 609
10 |  | APDCL |  |  | Completed | 134000 | 0 | [5 empty] | Capex | Utility owned | Purbanchal Enterprise |  |  |  | 134000 | 9187
11 |  | APDCL | Guwahati | All above | Completed | 14519 | 0 |  |  | Rs. 19.16 Crs |  |  | Capex | SG Pilot | Fluent Grid |  |  |  | 14519 | 0
12 |  | APDCL |  |  | Ongoing | 363500 | 363500 | [5 empty] | DBFOOT | Utility owned | Intellismart |  |  |  | 120666 | 102320
13 |  | APDCL |  |  | Ongoing | 256600 | 256600 | [5 empty] | DBFOOT | Utility owned | Intellismart |  |  |  | 106422 | 55334
14 |  | APDCL |  |  | Ongoing | 0 | 0 | 17000 | 0
15 |  | APDCL |  |  | Awarded | 681303 | 680400 | 11353 | 234
16 |  | APDCL |  |  | Awarded | 692022 | 691000 | 11872 | 323
17 |  | APDCL |  |  | Awarded | 712328 | 711200 | 11740 | 299
18 |  | APDCL |  |  | Awarded | 735964 | 733800 | 18044 | 600
19 |  | APDCL |  |  | Awarded | 753613 | 749300 | 11134 | 878
20 |  | APDCL |  |  | Awarded | 758986 | 757700 | 13404 | 448
21 |  | APDCL |  |  |  | 790382 | 790382
22 | Arunachal Pradesh | Arunachal PD |  |  | Proposed | 287445 | 287445 | 10116 | 688
23 | Bihar | NBPDCL | Motihari, Barauni, Dalsingsarai, Begusarai, Rosera, Bettiah, Sheohar, Muzaffarpur(W), Mahua, Hazipur,Darbhanga(R), Katihar, Supaul, Samastipur, Muzaffarpur(U-I), Ishanganj, Gopalganj, Madhubani, Siwan, Saharsa, Purnea, Forbisganj, Purnea (East), Madhepura, Jhanjharpur, Muzaffarpur(E), Sitamarhi, Khagaria, Chapra(W), Chapra(E), Bagha, Raxaul, Muzaffarpur(U-Ii), Bhagalpur(U), Patna, Gaya(U), Khagaul, Arwal, Bhagalpur(E), Bihta, Buxar, Biharsarif, Rajgir, Ekangarsarai, Jagdishpur, Nawada, Rajauli, Dehrionsone, Aurangabad, Banka, Barh, Bhabhua, Dakbanglow (Poc), Daudnagar, Gaya(R), Sherghati, Jahanabad, Jamui, Lakhisarai, Manpur, Amarpur, Naugachia, Munger, Patna Rural (Poc), Sasaram, Arrah, Masaurhi, Fatuha | All above | Ongoing | 1030000 | 1030000 | 0 | 0 | NA | 77.2 | 96 | Opex | IPDS | EDF | 10322630 | 68556 | 2505 | 582514 | 581728 | 83481
24 |  | SBPDCL |  | All above | Ongoing | 1320000 | 1320000 | 0 | 0 | NA | 77.2 | 96 | Opex | IPDS | EDF | 5955560 | 71631 | 6517 | 753819 | 753015 | 112058
25 |  | SBPDCL (Gram Power) |  |  | Completed | 40500 | 40500 | [5 empty] | Opex |  | Gram Power |  |  |  | 30500 | 30500
26 |  | IPCL |  |  | Completed | 17100 | 17100 | [5 empty] | Capex |  | Gram Power |  |  |  | 17100 | 17100
27 |  | BEDCPL/SPML |  |  | Completed | 1000 | 1000 | [5 empty] | Capex |  | Gram Power |  |  |  | 1000 | 1000
28 | Chandigarh | CED | Chandigarh (Sub Div-5) | All above | Ongoing | 29433 | 0 |  |  | Rs. 28.58 Crs |  |  | Capex | NSGM | Genus, Synergy Signals & Systems |  |  |  | 24214 | 0
29 | Chhattisgarh | CSPDCL |  |  | Proposed | 5962115 | 5962115 | 210644 | 6720
30 | Delhi | NDMC | New Delhi Area | All above | Ongoing | 64713 | 0 |  |  |  | 83.84 | 66 | Opex | IPDS | L&T |  |  |  | 65059 | 0
31 |  | TPDDL | North Delhi | All above | Completed | 195000 | 0 | [5 empty] | Capex | Utility owned | Landis + Gyr |  |  |  | 195000 | 0
32 | Goa | Goa PD |  |  | Proposed | 741160 | 741160 | 8369 | 827
33 | Gujarat | UGVCL | Naroda | All above | Completed | 23760 | 0 |  |  | Rs. 23.18 Crs |  |  | Capex | SG Pilot | Genus |  |  |  | 23760 | 0
34 |  | DGVCL* |  |  | Tendering | 4078120 | 4078120 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
35 |  | MGVCL* |  |  | Tendering | 3299991 | 3299991 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
36 |  | PGVCL* |  |  | Tendering | 5583509 | 5583509 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
37 |  | UGVCL* |  |  | Tendering | 3520251 | 3520251 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
38 | Haryana | UHBVNL | Panipat | All above | Completed | 10188 | 0 |  |  | NA |  |  | Capex | SG Pilot | NEDO |  |  |  | 10188 | 0
39 |  | SGKC Lab | Gurugram | All above | Completed | 10 | 0 |  |  | Rs. 5.96 Crs |  |  | Capex | SG Pilot | Genus |  |  |  | 10 | 0
40 |  | DHBVNL | Gurugram, Faridabad, Karnal, Panipat, Gharaunda, Panchkula, Kalka, Pinjore | All above | Ongoing | 500000 | 0 |  |  |  | 86.98 | 96 | Opex | Utility owned | L&T |  |  |  | 242521 | 501 | 7
41 |  | UHBVNL |  | All above | Ongoing | 500000 | 0 |  |  |  | 86.98 | 96 | Opex | Utility owned | L&T |  |  |  | 405171 | 958 | 244
42 |  | DHBVNL* |  |  | Proposed | 4165618 | 4165618 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
43 |  | UHBVNL* |  |  | Proposed | 3240000 | 3240000 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
44 | Himachal Pradesh | HPSEBL | Kala Amb | All above | Completed | 1335 | 0 |  |  | Rs. 19.44 Crs |  |  | Capex | SG Pilot | GE T&D |  |  |  | 1335 | 0
45 |  | HPSEBL |  |  | Completed | 75712 | 0 | [5 empty] | Capex | IPDS | Schneider Electric |  |  |  | 75712 | 0
46 |  | HPSEBL |  |  | Ongoing | 76028 | 0 | [5 empty] | Capex |  | Schneider Electric |  |  |  | 75303 | 0
47 |  | HPSEBL* |  |  | Tendering | 2800945 | 2800945 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
48 | Jammu & Kashmir | JPDCL & KPDCL |  |  | Ongoing | 127050 | 0 | [5 empty] | Capex | PMDP(U) | Techno Electric |  |  |  | 124666 | 0
49 | Jammu & Kashmir | JPDCL & KPDCL |  |  | Ongoing | 307766 | 0 | [5 empty] | DBFOOT |  | Anvil Cables |  |  |  | 84954 | 0
50 | Jammu & Kashmir | JPDCL & KPDCL |  |  | Ongoing | 250672 | 0 | [5 empty] | DBFOOT |  | Techno Electric |  |  |  | 17364 | 0
51 | Jammu & Kashmir | JPDCL |  |  | Proposed | 721346 | 721346 | 47367 | 1123
52 | Jammu & Kashmir | KPDCL |  |  | Proposed | 685699 | 685699 | 40670 | 1485
53 | Jharkhand | JBVNL* |  |  | Proposed | 1341306 | 1341306 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
54 | Karnataka | CESCOM | Mysore | All above | Completed | 20916 |  |  |  | Rs. 32.56 Crs |  |  | Capex | SG Pilot | Enzen Global |  |  |  | 20916 | 0
55 | Kerala | CPT |  | All above | Completed | 805 | [6 empty] | Capex | IPDS ST&D | Genus |  |  |  | 805 | 0
56 |  | KSEBL* |  |  | Proposed | 13248923 | 13248923 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
57 |  | TCED* |  |  | Proposed | 40438 | 40438 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
58 | Madhya Pradesh | MP-West | Dewas, Ujjain, Ratlam, Mhow, Khargone | All above | Completed | 124477 | 0 |  |  | Rs. 123.90 Crs. | Rs. 135.87 Crs. (Rs. 64.70 per node per month) | 30 (implementation)+ 60 (O&M) | Capex+Opex | IPDS | MP Smart Grid Pvt Ltd |  |  |  | 124477 | 0
59 |  | MP-West |  |  | Ongoing | 225523 | 0 | [5 empty] | Capex+Opex |  | MP Smart Grid Pvt Ltd |  |  |  | 0 | 0
60 |  | MP-West | Indore city | All above | Completed | 118836 | 0 |  |  | Rs. 59.34 Crs. | Rs.15.62 Crs. | 24 (implementation)+ 60 (O&M) | Capex | IPDS ST&D | L&T |  |  |  | 118836 | 0 | 1200
61 |  | MP-East​* |  |  | Partially Awarded | 5144451 | 5144451 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
62 |  | MP-Central​* |  |  | Tendering | 3955918 | 3955918 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
63 |  | MP-West​* |  |  | Partially Awarded | 3879733 | 3879733 | [5 empty] | Totex |  | - |  |  |  | 26800 | 0
64 | Maharashtra | MSEDCL* |  |  | Tendering | 22488866 | 22488866 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
65 |  | BEST* |  |  | Awarded | 1075881 | 1075881 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
66 | Manipur | MSPDCL |  |  | Proposed | 154400 | 154400 | 11451 | 357
67 | Meghalaya | MePDCL |  |  | Proposed | 460000 | 460000 | 11419 | 1324
68 | Mizoram | Mizoram PD |  |  | Proposed | 289383 | 289383 | 2300 | 398
69 | Nagaland | Nagaland PD |  |  | Proposed | 317210 | 317210 | 6276 | 392
70 | Odisha | OPTCL | Across Odisha | All above | Completed | 4000 | 0 | [5 empty] | BOOT | Utility owned | JnJ |  |  |  | 4000 | 0
71 |  | Paradip Port Trust |  |  | Completed | 500 | 0 | [5 empty] | Capex |  | Gram Power |  |  |  | 500 | 0
72 | Puducherry | PED | Puducherry | All above | Completed | 28910 | 0 |  |  | Rs. 35.43 Crs |  |  | Capex | SG Pilot | Dongfang Electronics |  |  |  | 28910 | 0
73 |  | PED | Puducherry | All above | Completed | 1658 | 0 | [5 empty] | Capex | Utility owned | Multiple Vendors |  |  |  | 1658 | 0
74 |  | PED* |  |  | Tendering | 403767 | 403767 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
75 | Punjab | PSPCL | Punjab | All above | Completed | 88107 | 0 |  |  | Rs. 50.99 Crs | Rs.19.80 Crs | 12 (implementation)+ 60 (O&M) | Capex | IPDS | PSPCL and HPL |  |  |  | 88107 | 0
76 |  | PSPCL |  |  | Ongoing | 7893 | 0 | [5 empty] | Capex |  | - |  |  |  | 0 | 0
77 |  | PSPCL* |  |  | Proposed | 8784807 | 8784807 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
78 |  | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
79 | Rajasthan | AVVNL | Makarana and Pushkar | All above | Completed | 68673 | 0 |  |  |  | 64 | 120 | Opex | IPDS | BOSCH |  |  |  | 68673 | 0
80 |  | AVVNL |  |  | Ongoing | 122149 | 0 | [5 empty] | Capex |  | - |  |  |  | 0 | 0
81 |  | AVVNL | Satguru Colony, Ajmer | All above | Completed | 1000 | 0 | [5 empty] | Capex | Utility owned | Radius, JnJ |  |  |  | 1000 | 0
82 |  | JaVVNL | Jaipur City and Tonk Circle | All above | Ongoing | 40980 | 0 |  |  | Rs. 149.95 Crs. | Rs. 43.79 Crs. | 12 (implementation) + 60 (O&M) | Capex | IPDS | - |  |  |  | 0 | 0
83 |  | JaVVNL |  |  | Completed | 240820 | 0 | [5 empty] | Capex |  | Genus Power (GPIL) |  |  |  | 240820 | 0
84 |  | JaVVNL | Urban consumers on Baran, Bundi, Bharatpur, Jhalawar, Karauli, Dholpur Circles | All above | Ongoing | 150000 | 0 | NA | NA | Rs. 87.43 Crs. | Rs. 45.3 (with GST) | 60 months | Hybrid | NSGM | Genus |  |  |  | 135944 | 0 | 0
85 |  | JaVVNL | Kota | All above | Completed | 70000 | 0 | [5 empty] | Capex | Utility owned | Genus |  |  |  | 70000 | 0
86 |  | JdVVNL | Jodhpur | All above | Ongoing | 46155 | 0 |  |  |  | 64 | 120 | Capex | IPDS | - |  |  |  | 0 | 0
87 |  | JdVVNL |  |  | Completed | 56027 | 0 | [5 empty] | Opex |  | BOSCH |  |  |  | 56027 | 0
88 |  | AVVNL |  |  | Proposed | 5432231 | 5432231 | 155453 | 11007
89 |  | JdVVNL |  |  | Proposed | 4080082 | 4080082 | 167809 | 10322
90 |  | JVVNL |  |  | Proposed | 4762643 | 4762643 | 111346 | 5799
91 | Sikkim | Sikkim PD | - | All above | Proposed | 144680 | 144680 | 3229 | 633
92 | Tamil Nadu | TANGEDCO |  |  | Proposed | 30000000 | 30000000 | 472500 | 18274
93 | Tamil Nadu | TANGEDCO | Chennai (MoU with Smart Cities) | All above | Ongoing | 141000 | 0 | [5 empty] | Capex | Utility owned | Genus |  |  |  | 126510 | 0
94 | Tripura | TSECL |  |  | Completed | 43081 | 0 | [5 empty] | Capex | SG Pilot | Wipro |  |  |  | 43081 | 0
95 |  | TSECL |  |  | Proposed | 547489 | 547489 | 14908 | 473
96 | Telangana | TSSPDCL | Jeedimetla | All above | Completed | 8882 | 0 |  |  | Rs. 34.93 Crs |  |  | Capex | SG Pilot | ECIL |  |  |  | 8882 | 0
97 | Uttar Pradesh | IITK | IIT Kanpur Campus | All above | Completed | 28 | 0 |  |  | Rs. 11.39 Crs |  |  | Capex | SG Pilot | Synergy Signals |  |  |  | 28 | 0
98 |  | MVVNL | Prayagraj, Azamgarh, Barabanki, Faizabad, Farrukhabad, Gonda, Gorakhpur, Hardoi, Jhansi, Jaunpur, Lucknow, Mirzapur, Orai, Raibareilly, Sahjahanpur, Sultanpur, Unnao, Varanasi, Mughalsarai, Aligarh, Bareilly, Bulandshahar, Etawah, Mainpuri, Moradabad, Meerut, Mathura, Muzaffarnagar, Rampur, Saharanpur, Vrindavan, Firozabad, Hapur, Loni, Sikandrabad, Modinagar, Muradnagar, Khurja, Amroha, Kanpur | All above | Ongoing | 905769 | 0 |  |  |  | 85.95 | 96 | Opex | Utility owned | L&T |  |  |  | 380731 | 3337 | 3337
99 |  | PVVNL |  | All above | Ongoing | 1164138 | 0 |  |  |  | 85.95 | 96 | Opex | Utility owned | L&T |  |  |  | 198726 | 20 | 20
100 |  | DVVNL |  | All above | Ongoing | 628686 | 0 | 1825 |  |  | 85.95 | 96 | Opex | Utility owned | EESL | 5355248 | 145905 | 17430 | 147991 | 127 | 127
101 |  | PuVVNL |  | All above | Ongoing | 1147102 | 0 |  |  |  | 85.95 | 96 | Opex | Utility owned | L&T |  |  |  | 321433 | 1135 | 1135
102 |  | KESCO |  | All above | Ongoing | 156532 | 0 |  |  |  | 85.95 | 96 | Opex | Utility owned | L&T |  |  |  | 134727 | 98577 | 60266
103 |  | DVVNL |  |  | Proposed | 5354069 | 5354069 | 187910 | 4393
104 |  | KESCO |  |  | Proposed | 625000 | 625000 | 6715 | 693
105 |  | MVVNL |  |  | Proposed | 7528737 | 7528737 | 383158 | 1745
106 |  | PVVNL |  |  | Proposed | 6143261 | 6143261 | 531164 | 9349
107 |  | PuVVNL |  |  | Proposed | 7327988 | 7327988 | 417854 | 4694
108 | Uttarakhand | UPCL |  |  | Proposed | 1584205 | 1584205 | [5 empty] | Totex |  | - |  |  |  | 0 | 0
109 | West Bengal | WBSEDCL | Siliguri | All above | Completed | 5164 | 0 |  |  | Rs. 6.95 Crs |  |  | Capex | SG Pilot | Chemtrols |  |  |  | 5164 | 0
110 |  | CESC | Kolkata | All above | Completed | 10000 | 0 | [5 empty] | Capex | Utility owned | Genus & Secure |  |  |  | 10000 | 0
111 |  | WBSEDCL |  |  | Proposed | 20717969 | 20717969 | 305419 | 11874
| Grand Total |  |  |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 1266 |  |  |  | 21633438 | 286092 | 26452 | 5751743 | 1665485 | 265204

## Output_MIS_for_Public (hidden)
Public Dashboard for Smart Metering Works implementation (For display on Portal)
Reporting Month |  | 2023-05-04
Progress as on Date |  | 2023-05-04
A. Smart Consumer Metering
| Name of Nodal Agency (REC/PFC) | Name of State | Name of DISCOM | Name of Scheme (RDSS/ Non-RDSS*) | Sanctioned |  |  | Awarded Scope - Cumulative Quantity (Nos.) | Cumulative Achievement till Date (Nos.) | Achievement during month (Nos.)
[5 empty] | Phase - I Area | Phase - II Area | TOTAL
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 |  |  |  | RDSS |  |  | 0
2 |  |  |  | RDSS |  |  | 0
3 |  |  |  | RDSS |  |  | 0
4 |  |  |  | RDSS |  |  | 0
Sub-Total (RDSS)
1 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
20 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
23 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
24 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
26 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
27 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
28 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
29 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
30 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
31 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
32 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
33 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
34 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
35 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
36 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
37 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
38 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
39 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
40 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
41 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
42 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
43 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
44 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
45 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
46 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
47 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
48 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
49 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
50 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
51 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
52 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
53 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
54 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
55 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
56 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
57 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
58 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
59 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
60 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sub-Total (Non-RDSS) | #REF! |  | #REF! | #REF! | #REF! | #REF!
Total (RDSS + Non-RDSS)
B. DT Metering
| Name of Nodal Agency (REC/PFC) | Name of State | Name of DISCOM | Name of Scheme (RDSS/ Non-RDSS*) |  |  | Sanctioned | Awarded Scope - Cumulative Quantity (Nos.) | Cumulative Achievement till Date (Nos.) | Achievement during month (Nos.)
TOTAL
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 |  |  |  | RDSS
2 |  |  |  | RDSS
3 |  |  |  | RDSS
4 |  |  |  | RDSS
Sub-Total (RDSS)
1 |  |  |  | Non-RDSS (Pls Specify)
2 |  |  |  | Non-RDSS (Pls Specify)
3 |  |  |  | Non-RDSS (Pls Specify)
4 |  |  |  | Non-RDSS (Pls Specify)
Sub-Total (Non-RDSS)
Total (RDSS + Non-RDSS)
C. Feeder Metering
| Name of Nodal Agency (REC/PFC) | Name of State | Name of DISCOM | Name of Scheme (RDSS/ Non-RDSS*) |  |  | Sanctioned | Awarded Scope - Cumulative Quantity (Nos.) | Cumulative Achievement till Date (Nos.) | Achievement during month (Nos.)
TOTAL
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 |  |  |  | RDSS
2 |  |  |  | RDSS
3 |  |  |  | RDSS
4 |  |  |  | RDSS
Sub-Total (RDSS)
1 |  |  |  | Non-RDSS (Pls Specify)
2 |  |  |  | Non-RDSS (Pls Specify)
3 |  |  |  | Non-RDSS (Pls Specify)
4 |  |  |  | Non-RDSS (Pls Specify)
Sub-Total (Non-RDSS)
Total (RDSS + Non-RDSS)
* Non-RDSS - IPDS/ DDUGJY/ PMDP/ SG-Pilot/ NSGM/ Utility Owned

## Scheme-wise (hidden)
S.N. | State | Utility | Project Area | Implementation Agency | SG Pilot |  |  | NSGM | [6 empty] | IPDS | [6 empty] | Utility owned | [6 empty] | Total Nos (State-wise) | [6 empty] | EESL | [6 empty] | Scheme | Sanctioned | Awarded | Installed as on date | Prepaid as on date | Ongoing | Meters in stock | Last Month Progress (August'21) | Target (Current Month) | Achievement (Current Month)
[5 empty] | Sanctioned | Awarded | Installed | Sanctioned | Awarded | Installed | Prepaid Installed | Ongoing | Target June | Achievement | Sanctioned | Awarded | Installed | Prepaid installed | Ongoing | Target June | Achievement | Sanctioned | Awarded | Installed | Prepaid Installed | Ongoing | Target Current month | Achievement | Sanctioned | Awarded | Installed | Prepaid Installed | Ongoing | Target Current month | Achievement | Sanctioned | Awarded | Installed | Prepaid Installed | Ongoing | Target Current Month | Achievement | IPDS | 2035414 | 2035414 | #REF! | #REF! | #REF! | #REF! | 98266 | #REF! | #REF!
1 | Andaman & Nicobar | Dept. of Power | Andman | EESL | [10 empty] | 36800 | 36800 | 36800 | 0 | 0 | #REF! | 573 | 38400 | 38400 | 38400 | 0 | 0 | 0 | 2328 | 75200 | 75200 | 75200 | 0 | 0 | #REF! | 2901 | 75200 | 75200 | 75200 | 0 | 0 | 0 | 2901 | NSGM | #REF! | 179433 | #REF! | 0 | 19275 | 13300 | 13747 | 2000 | 10923
2 | Assam | APDCL | Guwahati and Dibrugarh | Utility Owned | [17 empty] | 70000 | 70000 | 70000 | 2720 | 0 | 0 | - | 70000 | 70000 | 70000 | 2720 | 0 | 0 | 0 |  | 0 | [5 empty] | PMDP (U) | 127050 | 127050 | 124666 | 0 | 2384 | 0 | 2251 | 0 | 6890
|  | APDCL | Jorhat, Silchar & Guwahati | Utility Owned | [17 empty] | 134000 | 134000 | 134000 | 7926 | 0 | 0 | 10567 | 134000 | 134000 | 134000 | 7926 | 0 | 0 | 10567 |  | 0 | [5 empty] | SG Pilot | 156793 | 156793 | 156793 | 0 | 0 | 0 | 0 | - | -
|  | APDCL | Kokrajhar, Goalpara, Nalbari and Guwahati Town | Utility Owned | [17 empty] | 134000 | 134000 | 134000 |  | 0 | 0 | 1259 | 134000 | 134000 | 134000 | 0 | 0 | 0 | 1259 |  | 0 | [5 empty] | Utility Owned | #REF! | 7510769 | 2680927 | 115301 | #REF! | 221294 | 35548 | #REF! | 41922
|  | APDCL | Nagaon, Morigaon,KANCH, Cachar, Badarpur, Jorhat , Golaghat, Sivsagar, Dibrugarh, Tinsukia, GEC-I | Utility Owned | [17 empty] | 363500 | 0 | 0 |  |  |  |  | 363500 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Total | #REF! | 10009459 | #REF! | #REF! | #REF! | #REF! | 149812 | #REF! | #REF!
|  | APDCL | Kokrajhar, Bongaigaon, Barpeta, Rangia, Mangaldoi, Tezpur, North Lakhimpur, GEC-II | Utility Owned | [17 empty] | 256600 | 0 | 0 |  |  |  |  | 256600 | 0 | 0 | 0 | 0 | 0 | [9 empty] | Included 6600 meters @DT Level
|  | APDCL | Guwahati | Utility Owned | 14519 | 14519 | 14519 | [15 empty] | 0 | [5 empty] | 14519 | 14519 | 14519 | 0 | 0 | 0 | 0 |  | 0
3 | Bihar | NBPDCL | 72 nos. IPDS Town | EESL |  | 0 | [8 empty] | 350700 | 350700 | 582514 | 581728 | -231814 | 60000 | 68314 | #REF! | 679300 | 0 |  | #REF! |  |  | #REF! | 1030000 | 582514 | 581728 | #REF! | 60000 | 68314 | #REF! | #REF! | 582514 | 581728 | #REF! | 60000 | 68314
|  | SBPDCL | 58 nos. IPDS Town | EESL |  | 0 | [8 empty] | 434600 | 434600 | #REF! | #REF! | #REF! |  |  | 885400 | 885400 | 0 |  | 885400 |  |  | 1320000 | 1320000 | #REF! | #REF! | #REF! | 0 | 0 | 1320000 | 1320000 | #REF! | #REF! | #REF!
4 | Chandigarh | CED | Chandigarh (Sub Div-5) | RECPDCL |  | 0 |  | 29433 | 29433 | 24214 | 0 | 5219 | 0 | 1276 | [14 empty] | 29433 | 29433 | 24214 | 0 | 5219 | 0 | 1276 |  | 0
|  | CED | Complete City Excl. SD-5 |  |  | 0 |  | #REF! | 0 | - |  | - | [16 empty] | #REF! | 0 | 0 | 0 | - | 0 | 0 |  | 0 | [5 empty] | Implementation Agency | Sanctioned | Awarded | Installed as on date | Prepaid as on date | Ongoing | Meters in stock | Last Month Progress (Aug'21) | Target (Current Month) | Achievement (Current Month)
5 | Delhi | TPDDL | North Delhi | Utility Owned |  | 0 | [15 empty] | 195000 | 195000 | 195000 |  | 0 | 0 | - | 195000 | 195000 | 195000 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | EESL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 68012 | #REF! | 84267
|  | NDMC | NDMC Area | EESL |  | 0 | [15 empty] | 64713 | 64713 | 65059 |  | -346 | 0 | 1195 | 64713 | 64713 | 65059 | 0 | -346 | 0 | 1195 | 64713 | 64713 | 65059 | 0 | -346 | 0 | 1195 | PFCCL | 151740 | 151740 | 0 | 0 | 151740 | 1994 | 0 | 0 | 0
6 | Gujarat | UGVCL | Naroda | Utility Owned | 23760 | 23760 | 23760 | [21 empty] | 23760 | 23760 | 23760 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | RECPDCL | 156483 | 156483 | 148880 | 0 | 7603 | 2384 | 2910 | 0 | 8166
7 | Haryana | UHBVN | Panipat | Utility Owned | 10188 | 10188 | 10188 | [21 empty] | 10188 | 10188 | 10188 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | Utility Owned | #REF! | #REF! | #REF! | #REF! | #REF! | 26487 | 78890 | #REF! | #REF!
|  | POWERGRID | Manesar | Utility Owned | 10 | 10 | 10 | [21 empty] | 10 | 10 | 10 | 0 | 0 | [9 empty] | Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 149812 | #REF! | #REF!
|  | DHBVN, UHBVN | Gurugram, Karnal, Panipat, Panchkula | EESL |  | 0 | [15 empty] | 1000000 | 1000000 | 647692 | 1459 | 352308 | 31000 | 10306 | 1000000 | 1000000 | 647692 | 1459 | 352308 | 31000 | 10306 | 1000000 | 1000000 | 647692 | 1459 | 352308 | 31000 | 10306
8 | Himanchal Pradesh | HPSEB | Kala Amb | Utility Owned | 1335 | 1335 | 1335 | [18 empty] | 0 |  |  | 1335 | 1335 | 1335 | 0 | 0 | 0 | 0 |  | 0
|  | HPSEB | Shimla, Dharamshala | PFCCL |  | 0 | [8 empty] | 135716 | 135716 | 0 | 0 | 135716 |  |  | 16024 | 16024 | 0 |  | 16024 |  |  | 151740 | 151740 | 0 | 0 | 151740 | 0 | 0 |  | 0
9 | J&K | JKPDD | Jammu & Srinagar | RECPDCL |  | 0 | [15 empty] | 127050 | 127050 | 124666 | 0 | 2384 | 0 | 6890 | 127050 | 127050 | 124666 | 0 | 2384 | 0 | 6890 |  | 0
10 | Jharkhand | JBVNL | Ranchi City |  |  | 0 |  | #REF! | 0 | #REF! |  | - | [16 empty] | #REF! | 0 | #REF! | 0 | - | 0 | 0 |  | 0
11 | Karnataka | CESC | Mysore | Utility Owned | 20916 | 20916 | 20916 | [21 empty] | 20916 | 20916 | 20916 | 0 | 0 | 0 | 0 |  | 0
12 | Kerala | CPT | Cochin port area | Utility Owned |  | 0 | [8 empty] | 805 | 805 | 805 | 0 | 0 | 0 | - | [7 empty] | 805 | 805 | 805 | 0 | 0 | 0 | 0 |  | 0
13 | Madhya Pradesh | MPWZ | 5 towns (Dewas, Ujjain, Ratlam, Mhow, Khargone) | Utility Owned |  | 0 | [8 empty] | 345463 | 345463 | 124477 | 0 | 220986 | 0 | 12286 | 4537 | 4537 | [5 empty] | 350000 | 350000 | 124477 | 0 | 225523 | 0 | 12286 |  | 0 | [5 empty] | NSGM remianing Award | #REF! |  | Utility Owned Remaining Award | #REF! |  | Ranchi & CED (NSGM)
|  | MPWZ | Indore | Utility Owned |  | 0 | [8 empty] | 75430 | 75430 | #REF! | #REF! | 0 | #REF! | #REF! | 44606 | 44606 | [5 empty] | 120036 | 120036 | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [5 empty] | Utility Owned Remaining Award | #REF! |  | RECPDCL Remaining Award | 0 |  | J&K
14 | Odisha | OPTCL | Across Odisha | Utility Owned |  | 0 | [15 empty] | 4000 | 4000 | 4000 |  | 0 | 0 | - | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | total | #REF!
15 | Puducherry | PED | Puducherry | Utility Owned | 28910 | 28910 | 28910 | [21 empty] | 28910 | 28910 | 28910 | 0 | 0 | 0 | 0 |  | 0
|  | PED | Puducherry | Utility Owned |  | 0 | [15 empty] | 1658 | 1658 | 1658 |  | 0 |  |  | 1658 | 1658 | 1658 | 0 | 0 | 0 | 0 |  | 0
16 | Punjab | PSPCL | Ludhiyana | Utility Owned |  | 0 | [8 empty] | 88100 | 88100 | 88107 | 0 | -7 | 0 | 15000 | 7900 | 7900 | 0 | 0 |  |  |  | 96000 | 96000 | 88107 | 0 | 7893 | 0 | 15000 |  | 0
17 | Rajasthan | JVVNL | Kota | Utility Owned |  | 0 | [15 empty] | 70000 | 70000 | 70000 |  | 0 | 0 | - | 70000 | 70000 | 70000 | 0 | 0 | 0 | 0 |  | 0
|  | JVVNL | Jaipur & Tonk | Utility Owned |  | 0 | [8 empty] | 281782 | 281782 | 240820 | 0 | 40962 | 0 | 30694 | 18 | 18 | [5 empty] | 281800 | 281800 | 240820 | 0 | 40980 | 0 | 30694 |  | 0
|  | AjVVNL | 66 Towns | EESL |  | 0 | [8 empty] | 188860 | 188860 | 68673 | 0 | 120187 | 0 | 644 | 1962 | 1962 | [5 empty] | 190822 | 190822 | 68673 | 0 | 122149 | 0 | 644 | 122149 | 122149 | 68673 | 0 | 53476 | 0 | 644
|  | JVVNL | 6 Towns | Utility Owned |  | 0 |  | 150000 | 150000 | 135944 | 0 | 14056 | 2000 | 9647 | [14 empty] | 150000 | 150000 | 135944 | 0 | 14056 | 2000 | 9647 |  | 0
|  | AVVNL | Satguru Colony, Ajmer | Utility Owned |  | 0 | [15 empty] | 1000 | 1000 | 1000 |  | 0 |  |  | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 |  | 0
|  | JdVVNL | Jodhpur | EESL |  | 0 | [8 empty] | 97158 | 97158 | #REF! | #REF! | #REF! | 0 | 883 | 5024 | 5024 | [5 empty] | 102182 | 102182 | #REF! | #REF! | #REF! | 0 | 883 | 46155 | 46155 | #REF! | #REF! | #REF! | 0 | 883
18 | Tamil Nadu | TANGEDCO | Chennai (MoU with Smart Cities) | Utility Owned |  | 0 | [15 empty] | 141000 | 141000 | 126510 |  | 14490 | 0 | 16243 | 141000 | 141000 | 126510 | 0 | 14490 | 0 | 16243 |  | 0
19 | Telangana | TSSPDCL | Jeedimetla | Utility Owned | 8882 | 8882 | 8882 | [21 empty] | 8882 | 8882 | 8882 | 0 | 0 | 0 | 0 |  | 0
20 | Tripura | TSECL | Aragtala | Utility Owned | 43081 | 43081 | 43081 | [21 empty] | 43081 | 43081 | 43081 | 0 | 0 | 0 | 0 |  | 0
21 | Uttar Pradesh | IIT Kanpur Lab | IIT Kanpur Campus | Utility Owned | 28 | 28 | 28 | [21 empty] | 28 | 28 | 28 | 0 | 0 | 0 | 0 |  | 0
|  | UPPCL | Across UP | EESL |  | 0 | [15 empty] | 4002227 | 4002227 | 1183608 | 103196 | 2818619 | #REF! | 24 | 4002227 | 4002227 | 1183608 | 103196 | 2818619 | #REF! | 24 | 4002227 | 4002227 | 1183608 | 103196 | 2818619 | #REF! | 24
22 | West Bengal | WBSEDCL | Siliguri | Utility Owned | 5164 | 5164 | 5164 | [21 empty] | 5164 | 5164 | 5164 | 0 | 0 | 0 | 0 |  | 0
|  | CESC | Kolkata, WB | Utility Owned | [17 empty] | 10000 | 10000 | 10000 |  | 0 |  |  | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 |  | 0
Total |  |  |  |  | 156793 | 156793 | 156793 | #REF! | 179433 | #REF! | 0 | 19275 | 2000 | 10923 | 2035414 | 2035414 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 7637819 | 2805593 | 115301 | #REF! | #REF! | 48812 | #REF! | 10009459 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 84267
| 1. Andaman & Nicobar | [5 empty] | 6. Gujarat |  |  |  |  | 12. Kerala |  |  |  |  | 17. Rajasthan
| Scheme | Sanctioned | Installed | Ongoing |  |  | Scheme | Sanctioned | Installed | Ongoing |  | Scheme | Sanctioned | Installed | Ongoing |  | Scheme | Sanctioned | Installed | Ongoing
| IPDS | 36800 | 36800 | 0 |  |  | SG Pilot | 23760 | 23760 | - |  | IPDS | 780 | 805 | -25 |  | NSGM | 150000 | 135944 | 14056
| Utility Owned | 38400 | 38400 | 0 |  |  | No. of Smart Prepaid Meters Installed |  |  | - |  | No. of Smart Prepaid Meters Installed |  |  | - |  | IPDS | 567800 | #REF! | #REF!
| Total | 75200 | 75200 | 0 |  |  | Meters in Stock |  |  | - |  | Meters in Stock |  |  | - |  | Utility Owned | 78004 | 71000 | 0
| No. of Smart Prepaid Meters Installed |  |  | 0 |  |  | Last Month Progress (Jun'21) |  |  | - |  | Last Month Progress (Jun'21) |  |  | - |  | Total | 795804 | #REF! | #REF!
| Meters in Stock |  |  | #REF! | [12 empty] | No. of Smart Prepaid Meters Installed |  |  | 0
| Last Month Progress (June'21) |  |  | 163 | [12 empty] | Meters in Stock |  |  | 13300
[17 empty] | Last Month Progress (Jun'21) |  |  | 24466
| 1. Andaman & Nicobar | [5 empty] | 6. Gujarat
| Implementation Agency | Sanctioned | Installed | Ongoing |  |  | Implementation Agency | Sanctioned | Installed | Ongoing | [6 empty] | 17. Rajasthan
| EESL | 75200 | 75200 | 0 |  |  | Utility Vendor | 23760 | 23760 | 0 | [6 empty] | Implementation Agency | Sanctioned | Installed | Ongoing
[7 empty] | Total | 23760 | 23760 | 0 | [6 empty] | Utility Vendor | 502800 | 447764 | 55036
[17 empty] | EESL | 293004 | #REF! | #REF!
| 2. Assam | [5 empty] | 7. Haryana |  |  |  |  | 13. Madhy Pradesh |  |  |  |  | Total | 795804 | #REF! | #REF!
| Scheme | Sanctioned | Installed | Ongoing |  |  | Scheme | Sanctioned | Installed | Ongoing |  | Scheme | Sanctioned | Installed | Ongoing
| SG Pilot | 14519 | 14519 | 0 |  |  | SG Pilot | 10188 | 10188 | 0 |  | IPDS | 420893 | #REF! | #REF! |  | 18. Tamilnadu
| Utility Owned | 958100 | 338000 | 0 |  |  | Utility Owned | 1000000 | 647692 | 352308 |  | Utility Owned | 49143 | 0 | 49143 |  | Scheme | Sanctioned | Installed | Ongoing
| Total | 972619 | 352519 | 0 |  |  | Total | 1010188 | 657880 | 352308 |  | Total | 470036 | #REF! | #REF! |  | Utility Owned | 141000 | 126510 | 14490
| Meters in Stock |  |  | 0 |  |  | No. of Smart Prepaid Meters Installed |  |  | 1459 |  | No. of Smart Prepaid Meters Installed |  |  | 0 |  | No. of Smart Prepaid Meters Installed |  |  | 0
| No. of Smart Prepaid Meters Installed |  |  | 177487 |  |  | Meters in Stock |  |  | 119553 |  | Meters in Stock |  |  | 1945 |  | Meters in Stock |  |  | 13187
| Last Month Progress (Jun'21) |  |  | 11981 |  |  | Last Month Progress (Jun'21) |  |  | 9175 |  | Last Month Progress (Jun'21) |  |  | 8704 |  | Last Month Progress (Jun'21) |  |  | 2045
| 2. Assam | [5 empty] | 7. Haryana |  |  |  |  | 13. Madhya Pradesh |  |  |  |  | 18. Tamilnadu
| Implementation Agency | Sanctioned | Installed | Ongoing |  |  | Implementation Agency | Sanctioned | Installed | Ongoing |  | Implementation Agency | Sanctioned | Installed | Ongoing |  | Implementation Agency | Sanctioned | Installed | Ongoing
| Utility Vendor | 352519 | 352519 | 0 |  |  | Utility Vendor | 10188 | 10188 | 0 |  | Utility Vendor | 470036 | #REF! | #REF! |  | Utility Vendor | 141000 | 126510 | 14490
| Total | 352519 | 352519 | 0 |  |  | EESL | 1000000 | 647692 | 352308 | [6 empty] | Total | 141000 | 126510 | 14490
[7 empty] | Total | 1010188 | 657880 | 352308
| 3. Bihar | [10 empty] | 14. Odisha
| Scheme | Sanctioned | Installed | Ongoing |  |  | 8. Himanchal Pradesh |  |  |  |  | Scheme | Sanctioned | Installed | Ongoing |  | 19. Telangana
| IPDS | 785300 | #REF! | #REF! |  |  | Scheme | Sanctioned | Installed | Ongoing |  | Utility Owned | 4000 | 4000 | - |  | Scheme | Sanctioned | Installed | Ongoing
| Utility Owned | #REF! | 0 | #REF! |  |  | SG Pilot | 1335 | 1335 | 0 |  | No. of Smart Prepaid Meters Installed |  |  | - |  | SG Pilot | 8882 | 8882 | 0
| Total | #REF! | #REF! | #REF! |  |  | IPDS | 135716 | Under Award | [7 empty] | No. of Smart Prepaid Meters Installed |  |  | 0
| No. of Smart Prepaid Meters Installed |  |  | 1334743 |  |  | Total | 137051 | 1335 | 0 |  | 15. Puducherry
| Meters in Stock |  |  | 189236 |  |  | No. of Smart Prepaid Meters Installed |  |  | 9443 |  | Scheme | Sanctioned | Installed | Ongoing
| Last Month Progress (Jun'21) |  |  | 9601 |  |  | Meters in Stock |  |  | - |  | SG Pilot | 28910 | 28910 | 0
[7 empty] | Last Month Progress (Jun'21) |  |  | - |  | Utility Owned | 1658 | 1658 | 0 |  | 19. Telangan
| 3. Bihar | [10 empty] | Total | 30568 | 30568 | 0 |  | Implementation Agency | Sanctioned | Installed | Ongoing
| Implementation Agency | Sanctioned | Installed | Ongoing |  |  | 8. Himanchal Pradesh |  |  |  |  | No. of Smart Prepaid Meters Installed |  |  | 0 |  | Utility Vendor | 8882 | 8882 | 0
| EESL | #REF! | #REF! | #REF! |  |  | Implementation Agency | Sanctioned | Installed | Ongoing | [6 empty] | Total | 8882 | 8882 | 0
| Total | #REF! | #REF! | #REF! |  |  | Utility Vendor | 1335 | 1335 | 0 |  | 16. Punjab
[7 empty] | PFCCL | 135716 | 0 | 135716 |  | Scheme | Sanctioned | Installed | Ongoing |  | 20. Tripura
| 4. Chandigarh | [5 empty] | Total | 137051 | 1335 | 135716 |  | IPDS | 88100 | 88107 | -7 |  | Scheme | Sanctioned | Installed | Ongoing
| Scheme | Sanctioned | Installed | Ongoing | [7 empty] | Utility Owned | 7900 | 0 | 7900 |  | SG Pilot | 43081 | 43081 | 0
| NSGM | #REF! | 24214 | 5219 |  |  | 9. J&K |  |  |  |  | Total | 96000 | 88107 | 7893 |  | No. of Smart Prepaid Meters Installed |  |  | 0
| No. of Smart Prepaid Meters Installed |  |  | 0 |  |  | Scheme | Sanctioned | Installed | Ongoing |  | No. of Smart Prepaid Meters Installed |  |  | -
| Meters in Stock |  |  | 0 |  |  | Utility Owned | 127050 | Not Started |  |  | Meters in Stock |  |  | 0
| Last Month Progress (Jun'21) |  |  | 872 |  |  | No. of Smart Prepaid Meters Installed |  |  | 0 |  | Last Month Progress (Jun'21) |  |  | 1713
[7 empty] | Meters in Stock |  |  | 2384 | [6 empty] | 20. Tripura
| 4. Chandigarh | [5 empty] | Last Month Progress (Jun'21) |  |  | - |  | 16. Punjab |  |  |  |  | Implementation Agency | Sanctioned | Installed | Ongoing
| Implementation Agency | Sanctioned | Installed | Ongoing | [7 empty] | Implementation Agency | Sanctioned | Installed | Ongoing |  | Utility Vendor | 43081 | 43081 | 0
| RECPDCL | 29433 | 24214 | 5219 |  |  | 9. J&K |  |  |  |  | Utility Vendor | 96000 | 88107 | 7893 |  | Total | 43081 | 43081 | 0
| Utility Vendor | #REF! | - | - |  |  | Implementation Agency | Sanctioned | Installed | Ongoing
| Total | #REF! | 24214 | 5219 |  |  | RECPDCL | 127050 | 124666 | 2384 | [6 empty] | 21. Uttar Pradesh
[7 empty] | Total | 127050 | 124666 | 2384 | [6 empty] | Scheme | Sanctioned | Installed | Ongoing
[17 empty] | SG Pilot | 28 | 28 | 0
| 5. Delhi | [15 empty] | Utility Owned | 4002227 | 1183608 | 2818619
| Scheme | Sanctioned | Installed | Ongoing |  |  | 10. Jharkhand | [9 empty] | Total | 4002255 | 1183636 | 2818619
| Utility Owned | 259713 | 260059 | -346 |  |  | Scheme | Sanctioned | Installed | Ongoing | [6 empty] | No. of Smart Prepaid Meters Installed |  |  | 103196
| No. of Smart Prepaid Meters Installed |  |  | 0 |  |  | NSGM | #REF! | #REF! | #REF! | [6 empty] | Meters in Stock |  |  | 85815
| Meters in Stock |  |  | 355 |  |  | No. of Smart Prepaid Meters Installed |  |  | #REF! | [6 empty] | Last Month Progress (Jun'21) |  |  | 0
| Last Month Progress (Jun'21) |  |  | 147 |  |  | Meters in Stock |  |  | #REF!
[7 empty] | Last Month Progress (Jun'21) |  |  | - | [6 empty] | 21. Uttar Pradesh
| 5. Delhi | [15 empty] | Implementation Agency | Sanctioned | Installed | Ongoing
| Implementation Agency | Sanctioned | Installed | Ongoing | [12 empty] | Utility Vendor | 28 | 28 | 0
| Utility Vendor | 195000 | 195000 | 0 |  |  | 11. Karnataka | [9 empty] | EESL | 4002227 | 1183608 | 2818619
| EESL | 64713 | 65059 | -346 |  |  | Scheme | Sanctioned | Installed | Ongoing | [6 empty] | Total | 4002255 | 1183636 | 2818619
| Total | 259713 | 260059 | -346 |  |  | SG Pilot | 20916 | 20916 | 0
[7 empty] | No. of Smart Prepaid Meters Installed |  |  | 0 | [6 empty] | 22. West Bengal
[17 empty] | Scheme | Sanctioned | Installed | Ongoing
[17 empty] | SG Pilot | 5164 | 5164 | 0
[17 empty] | Utility Owned | 10000 | 10000 | 0
[7 empty] | 11. Karnataka | [9 empty] | Total | 15164 | 15164 | 0
[7 empty] | Implementation Agency | Sanctioned | Installed | Ongoing | [6 empty] | No. of Smart Prepaid Meters Installed |  |  | 0
[7 empty] | Utility Vendor | 20916 | 20916 | 0
22. West Bengal
[17 empty] | Implementation Agency | Sanctioned | Installed | Ongoing
[17 empty] | Utility Vendor | 15164 | 15164 | 0
[17 empty] | Total | 15164 | 15164 | 0

## Monthly Progress (hidden)
|  | Updates from EESL |  |  | Updates from IPDS | [6 empty] | NSGM Projects |  |  |  | Direct update from Utility
Sl | State | Utility | Scheme | Implementation Agency | Nos. of Smart Meters Sanctioned | Nos. of Smart Meters Installed in the end of Month
[6 empty] | 2021-08-21 |  | 2021-07-21 |  | 2021-06-21 |  | 2021-05-21 |  | 2021-04-21 |  | 2021-03-21 |  | 2021-02-21 |  | 2021-01-21
[6 empty] | Cummulative | Incremental | Cummulative | Incremental | Cummulative | Incremental | Cummulative | Incremental | Cummulative | Incremental | Cummulative | Incremental | Cummulative | Incremental | Cummulative
1 | A&N | Dept. of Power | IPDS | EESL | 36800 | 34326 | 738 | 33588 | 905 | 32683 | 0 | 32683 | 0 | 32683 | 538 | 32145 | 653 | 31492 | 1736 | 29756
|  | Dept. of Power | Utility owned | EESL | 38400 | 18837 | 271 | 18566 | 696 | 17870 | 163 | 17707 | 11 | 17696 | 1325 | 16371 | 4073 | 12298 | 188 | 12110
2 | Assam | APDCL | Utility owned | Utility Owned | 70000 |  |  |  | 0 | 70000 |  | 70000 |  | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000
|  | APDCL | SG Pilot | Utility Owned | 14259 |  |  |  | 0 | 14259 |  | 14259 |  | 14259 | 0 | 14259 | 0 | 14259 | 0 | 14259
|  | APDCL | Utility owned | Utility Owned | 134000 | 52568 | 11916 | 40652 | 11640 | 29012 | 11981 | 17031 | 10363 | 6668 | 6668 | 0 | 0 | 0 | 0 | 0
|  | APDCL | Utility owned | Utility Owned | 134000 | 4643 | 3667 | 976 | 976
3 | Bihar | NBPDCL, SBPDCL | IPDS | EESL | 785300 | 215822 | 34346 | 181476 | 24112 | 157364 | 9601 | 147763 | 1064 | 146699 | 3191 | 143508 | 4181 | 139327 | 11166 | 128161
|  |  | Utility owned | EESL | #REF! | 0 | 0 | 0 | 0 | 0 |  | 0
4 | Chandigarh | CED | NSGM | RECPDCL | 29433 | 11171 | 659 | 10512 | 1069 | 9443 | 872 | 8571 | 950 | 7621 | 1626 | 5995 | 477 | 5518 | 5518
5 | Delhi | TPDDL | Utility owned |  | 195000 |  |  |  | 0 | 195000 |  | 195000 |  | 195000 | 0 | 195000 | 0 | 195000 | 0 | 195000
|  | NDMC | Utility owned | EESL | 64713 | 60835 | 244 | 60591 | 178 | 60413 | 147 | 60266 | 163 | 60103 | 122 | 59981 | 251 | 59730 | 266 | 59464
6 | Gujarat | UGVCL | SG Pilot |  | 23760 |  |  |  | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760 | 0 | 23760
7 | Haryana | UHBVN | SG Pilot |  | 10188 |  |  |  | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188 | 0 | 10188
|  | SGKC Lab | SG Pilot |  | 10 |  |  |  | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10
|  | DHBVN, UHBVN | Utility owned | EESL | 1000000 | 304357 | 14019 | 290338 | 10390 | 279948 | 9175 | 270773 | 11795 | 258978 | 8342 | 250636 | 2774 | 247862 | 0 | 247862
8 | Himanchal Pradesh | HPSEB | SG Pilot |  | 1335 |  |  |  | 0 | 1335 |  | 1335 |  | 1335 | 0 | 1335 | 0 | 1335 | 0 | 1335
9 | J&K | JKPDD | PMDP (U) | RECPDCL | 115500 | 2251 | 2251 | 0 | 0
10 | Karnataka | CESC | SG Pilot |  | 20916 |  |  |  | 0 | 20916 |  | 20916 |  | 20916 | 0 | 20916 | 0 | 20916 | 0 | 20916
11 | Kerala | CPT | IPDS |  | 800 |  |  |  | 0 | 780 |  | 780 |  | 780 | 0 | 780 | 0 | 780 | 0 | 780
12 | Madhya Pradesh | MPWZ (5 towns) | IPDS | Utility Owned | 344540 | 65895 | 14491 | 51404 | 5691 | 45713 | 8704 | 37009 | 3363 | 33646 | 6080 | 27566 | 16766 | 10800 | 9619 | 1181
13 |  | MPWZ (Indore) | IPDS | Utility Owned | 118836 |  |  |  | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836 | 0 | 118836
14 | Odisha | OPTCL | Utility owned | Utility Owned | 4000 |  |  |  | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000
15 | Puducherry | PED | SG Pilot | Utility Owned | 28910 |  |  |  | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910 | 0 | 28910
16 |  | PED | Utility owned | Utility Owned | 1658 |  |  |  | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658 | 0 | 1658
17 | Punjab | PSPCL | IPDS | Utility Owned | 96000 | 11817 | 4414 | 7403 | 4803 | 2600 | 1713 | 887 | 673 | 214 | 114 | 100 | 0 | 100 | 0 | 100
18 | Rajasthan | JVVNL | Utility owned | Utility Owned | 70000 |  |  |  | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000
19 |  | JVVNL | IPDS | Utility Owned | 281800 | 84277 | 25883 | 58394 | 12745 | 45649 | 13903 | 31746 | 0 | 31746 | 6939 | 24807 | 16547 | 8260 | 3260 | 5000
20 |  | AjVVNL | IPDS | EESL | 122149 | 26311 | 9584 | 16727 | 9984 | 6743 | 4404 | 2339 | 0 | 2339 | 1837 | 502 | 37 | 465 | 122 | 343
21 |  | JVVNL | NSGM | Utility Owned | 150000 | 43732 | 13088 | 30644 | 6969 | 23675 | 2866 | 20809 | 5082 | 15727 | 2426 | 13301 | 6231 | 7070 | 7070
22 |  | AjVVNL | Utility owned |  | 1000 |  |  |  | 0 | 1000 |  | 1000 |  | 1000 | 0 | 1000 | 0 | 1000 | 0 | 1000
23 |  | JdVVNL | IPDS | EESL | 102182 | 21533 | 8810 | 12723 | 5397 | 7326 | 3293 | 4033 | 0 | 4033 | 2473 | 1560 | 668 | 892 | 376 | 516
24 | Tamil Nadu | TANGEDCO | Utility owned | Utility Owned | 141000 | 26370 | 5431 | 20939 | 8535 | 12404 | 2045 | 10359 | -6579 | 16938 | 2548 | 14390 | 7673 | 6717 | 6717 | 0
25 | Telangana | TSSPDCL | SG Pilot |  | 8882 |  |  |  | 0 | 8882 |  | 8882 |  | 8882 | 0 | 8882 | 0 | 8882 | 0 | 8882
26 | Tripura | TSECL | SG Pilot |  | 43081 |  |  |  | 0 | 43081 |  | 43081 |  | 43081 | 0 | 43081 | 0 | 43081 | 0 | 43081
27 | Uttar Pradesh | IIT Kanpur Lab | SG Pilot |  | 28 |  |  |  | 0 | 28 |  | 28 |  | 28 | 0 | 28 | 0 | 28 | 0 | 28
28 |  | UPPCL | Utility owned | EESL | 4000402 | 1147910 | 0 | 1147910 | 0 | 1147910 | 0 | 1147910 | 0 | 1147910 | 0 | 1147910 | 5633 | 1142277 | 0 | 1142277
20 | West Bengal | WBSEDCL | SG Pilot |  | 5164 |  |  |  | -5164 | 5164 |  | 5164 |  | 5164 |  | 5164 |  | 5164 |  | 5164
|  | CESC | Utility owned |  | 10000 |  |  |  | -10000 | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 10000
| Total |  |  |  | #REF! | 2132655 | 149812 | 1982843 | 104090 | 2506560 | 68867 | 2437693 | 26885 | 2410808 |  | 2366579 |  | 2300615 |  | 2254577
|  | Scheme | Sanctioned | 2021-08-21 |  | 2021-07-21 |  | 2021-06-21 |  | 2021-05-21 |  | 2021-04-21 |  | 2021-03-21 |  | 2021-02-21 |  | 2021-01-21
|  |  |  | Cummulative | Incremental | Cummulative | Incremental | Cummulative | Incremental | Cummulative | Incremental | Cummulative | Incremental | Cummulative | Incremental | Cummulative | Incremental | Cummulative
| For Ongoing deployment | NSGM | 179433 | 54903 | 13747 | 41156 | 8038 | 33118 | 3738 | 29380 | 6032 | 23348 | 4052 | 19296 | 6708 | 12588 | 12588 | 0
|  | IPDS | 1768771 | 459981 | 98266 | 361715 | 63637 | 298078 | 41618 | 256460 | 5100 | 251360 | 21172 | 230188 | 38852 | 191336 | 26279 | 165057
|  | PMDP (U) | 115500 | 2251 | 2251 | 0 | 0
|  | Utility Owned | #REF! | 1615520 | 35548 | 1579972 | 32415 | 1547557 | 23511 | 1524046 | 15753 | 1508293 | 19005 | 1489288 | 20404 | 1468884 | 7171 | 1461713
|  | Total | #REF! | 2132655 | 149812 | 1982843 | 104090 | 1878753 | 68867 | 1809886 | 26885 | 1783001 | 44229 | 1738772 | 65964 | 1672808 | 46038 | 1626770

## Monthly-Progress (hidden)
Part B: Format for monitoring periodic progress
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
S No. | Utility | No of Smart meters implemented till 1st day of the current month |  |  |  | Incremental Physical Progress |  |  | Financial progress |  | Implementation issues
|  | @Consumer level |  | @DT Level | @Feeder Level | Nos. of Smart Meters | HES make | MDM make | in Rs. Lakhs | in %
|  | of Smart type (including Smart Prepaid) | of Smart Prepaid type
1 | APDCL | 16588 | -
2 | DHBVN | 1,20,670 | 7 |  |  |  | Trilliant | Oracle
3 | UHBVN | 1,48,252 | 140 |  |  |  | Trilliant | Oracle
4 | NDMC | 60248 | - |  |  |  | Fluent Grid | Fluent Grid
5 | MVVNL | 3,75,849 | 3337 |  |  |  | Trilliant | Oracle
6 | PVVNL | 1,98,422 | 20 |  |  |  | Trilliant | Oracle
7 | DVVNL | 1,47,460 | 127 |  |  |  | Trilliant | Oracle
8 | PuVVNL | 3,19,946 | 1135 |  |  |  | Trilliant | Oracle
9 | KESCO | 1,06,233 | 34845 |  |  |  | Trilliant | Oracle
10 | NBPDCL | 72531 | 71576 | 0 | 0 |  | Scneider India | Siemens
11 | SBPDCL | 74887 | 74191 | 0 | 0 |  | Scneider India | Siemens
12 | AVVNL | 2339 | - |  |  |  | Bosch | Fluent Grid
13 | JdVVNL | 4033 | - |  |  |  | Bosch | Fluent Grid
14 | JaVVNL | 20809 | - |  |  |  | Cyan Cannode | BCITS
15 | JaVVNL | 31746 | - |  |  |  | Cyan Cannode | BCITS
16 | EDANI | 50390 | - |  |  |  | Bosch | Fluent Grid
17 | MP-West | 37009 | - |  |  |  | Cyan Cannode | Esyasoft
18 | PSPCL | 887 | - |  |  |  | HPL | Analogics Tech
19 | CED | 8571 | -
20 | TANGEDCO | 10359 | -
Total |  | 18,07,229 | 1,85,378 | 0 | 0

## IPDS-EESL-seperate (hidden)
Last Updated |  | 2021-08-27 |  | Already Completed Projects
Sl | State | Utility | Project Area(s) | Completion timeline | Nos. of Smart Meters Sanctioned |  | Nos. of Smart Meters Awarded |  | Business Model (Capex/Opex/Hybrid) | Scheme under which it is funded (Revamped/ IPDS/ NSGM/ Own) | Implementation Agency | Agency Responsible | Nos. of Smart Meters available at Store (Inventory of PROJECT) | Nos. of Smart Meters Installed |  | Target August Month | Achievement August Month | Installed as of 1st August 2021 | Achievement July'21 Month | Installed as of 1st July 2021
[5 empty] | of Smart type | of Smart Prepaid type | of Smart type | of Smart Prepaid type |  |  |  |  | of Smart type | of Smart type | of Smart Prepaid type
|  |  | Smart meter in completed Project |  | 627797 | 1200 |  |  | - | - | - |  | 0 | 627797 | 1200
|  |  | Ongoing Smart Meter Installation |  | 10534747 | 2501740 |  |  | - | - | - |  | 543596 | 2101675 | 277142
1 | Andaman | EDANI | Andman | Sep'21 | 36800 | - | 36800 |  | Opex | IPDS | BOSCH | EESL | 2500 | 34300 | - | 1000 | 712 | 33588 | 905 | 32683
| Andaman | EDANI | Andman |  | 39200 | - | 39200 |  | Opex | Utility Owned | BOSCH | EESL | 21397 | 18837 | - | 1000 | 271 | 18566 | 696 | 17870
2 | Assam | APDCL | Guwahati, Dibrugarh | Completed | 70000 | - | 70000 |  | Capex | Utility Owned | Anvil Cables, Sinhal Udyog | Utility | - | 70000 | 2720 | - | 0 | 70000 | 0 | 70000
| Assam | APDCL | 3 Towns | 21 months from the date of issue of LoA i.e. September 2022 | 134000 | - | 134000 |  | Capex | Utility Owned | Anvil Cables, Sinhal Udyog | Utility | 17399 | 51318 | 652 | 18000 | 10666 | 40652 | 11640 | 29012
| Assam | APDCL | 4 Towns | 22 months from the date of issue of LoA i.e. September 2022 | 134000 | - | 134000 |  | Capex | Utility Owned | Purbanchal Enterprise | Utility | 2638 | 4381 | 0 | 5000 | 3405 | 976 | 976 | 0
| Assam | APDCL | 11 Towns | Under Tendering | 363500 | - | - | - | Opex / Hybrid | Utility Owned |  | Utility | - | 0 | - | - | 0 | 0 |  | -
| Assam | APDCL | 8 Towns | Under Tendering | 256600 | - | - | - | Opex / Hybrid | Utility Owned |  | Utility | - | 0 | - | - | 0 | 0 |  | -
| Assam | APDCL | Guwahati | Completed | 14259 | - | 14259 |  | Capex | SG Pilot | Fluent Grid | Utility | - | 14259 | - | - | 0 | 14259 | 0 | 14259
3 | Bihar | NBPDCL | Across Bihar | December 2022 (The earlier plan was to complete MI by July 2022 as per the agreement. However due to CoVid the same needs to be relooked. | 350700 | 350700 | 350700 | 350700 | Opex | IPDS | EDF, Genus | EESL | 18387.25 | 86271 | 85578 | 30000 | 5003 | 81268 | 5518 | 75750
| Bihar | NBPDCL | Across Bihar |  | 599300 | 599300 | 599300 | 599300 | Opex | Utility Owned | EDF, Genus | EESL | 18387.25 | 0 | 0 | 0 | 0
| Bihar | SBPDCL | Across Bihar |  | 434600 | 434600 | 434600 | 434600 | Opex | IPDS | EDF, Genus | EESL | 18387.25 | 123597 | 123045 | 30000 | 23389 | 100208 | 18594 | 81614
| Bihar | SBPDCL | Across Bihar |  | 965400 | 965400 | 965400 | 965400 | Opex | Utility Owned | EDF, Genus | EESL | 18387.25 | 0 | 0 | 0 | 0
4 | Chandigarh | CED | Sub Div 5 | Sep'21 | 29433 | - | 29433 |  | Capex | NSGM | Genus, Synergy SS | RECPDCL | 13594 | 11147 | - | 5100 | 635 | 10512 | 1069 | 9443
| Chandigarh | CED | Full City ex. SD5 | Under Revised Sanction/Approval | 184000 | - | - |  |  | NSGM |  | Utility | - | 0 | - | 0 | 0 | 0 | 0 | -
5 | Delhi | NDMC | NDMC Area | NDMC has already been saturated. The remaining meters are for new service connections | 64713 | - | 64713 |  | Opex | Utility Owned | LnT, Genus | EESL | 2862 | 60808 | - | 0 | 217 | 60591 | 178 | 60413
| Delhi | TPDDL | North Delhi | Completed | 195000 | - | 195000 |  | Capex | Utility Owned | Landis Gyr | Utility | - | 195000 | - | - | 0 | 195000 | 0 | 195000
6 | Gujarat | UGVCL | Naroda | Completed | 23760 | - | 23760 |  | Capex | SG Pilot | Genus | Utility | - | 23760 | - | - | 0 | 23760 | 0 | 23760
7 | Haryana | UHBVN | Panipat | Completed | 10188 | - | 10188 |  | Capex | SG Pilot | NEDO | Utility | - | 10188 | - | - | 0 | 10188 | 0 | 10188
| Haryana | DHBVN | Across Haryana | July 2022 (as per agreement it is Dec'2023 and January 2024 for UHBVN and DHBVN respectively) | 500000 | - | 500000 |  | Opex | Utility Owned | ITI, Genus, Zen, Keonics - LnT (SI) | EESL | 30276 | 130665 | 7 | 15500 | 1947 | 128718 | 3478 | 125240
| Haryana | UHBVN | Across Haryana |  | 500000 | - | 500000 |  | Opex | Utility Owned | ITI, Genus, Zen, Keonics - LnT (SI) | EESL | 30276 | 171477 | 255 | 15500 | 9857 | 161620 | 6912 | 154708
| Haryana | POWERGRID | Manesar | Completed | 10 | - | 10 |  | Capex | SG Pilot | Genus | Utility | - | 10 | - | - |  | 10 | 0 | 10
8 | Himachal Pradesh | HPSEB | Kala Amb | Completed | 1335 | - | 1335 |  | Capex | SG Pilot | GE | Utility | - | 1335 | - | - | 0 | 1335 | 0 | 1335
| Himachal Pradesh | HPSEB | Shimla, Dhramshala | 7th April 2022 Project to be implemented in 9 months (i.e. ) followed by 99 months of FMS period | 135716 | 135716 | 135716 |  | Capex | IPDS | Schneider Electric | PFCCL | - | 0 | - | 0 | 0 | 0 | 0 | -
| Himachal Pradesh | HPSEB | Shimla, Dhramshala |  | 16024 | 16024 | 16024 |  | Capex | Utility Owned | Schneider Electric | PFCCL | - | 0 | - | 0 | 0 | 0 | 0 | -
9 | Jammu and Kashmir | JKPDD | Jammu and Srinagar | 2022-03-01 | 115500 | - | 115500 |  | Capex | Utility Owned | Techno Electric | RECPDCL | 4446 | 1154 | - | 5000 | 1154 | 0 | 0 | -
10 | Jharkhand | JBVNL | Ranchi | 2024-03-01 | 360000 | - | - |  |  | NSGM |  | Utility | - | 0 | - | 0 | 0 | 0 | 0 | -
11 | Karnataka | CESCOM | Mysuru | Completed | 20916 | - | 20916 |  | Capex | SG Pilot | Enzen Global | Utility | - | 20916 | - | - | 0 | 20916 | 0 | 20916
12 | Kerala | CPT | Cochin Port | Completed | 800 | - | 800 |  | Capex | IPDS | Nsoft India Service | Utility | - | 780 | - | - | 0 | 780 | 0 | 780
13 | Madhya Pradesh | MP-West | 5 Towns | Dec'21. Due to Covid, utilities have requested for further time extension. | 345463 | - | 345463 |  | Capex+Opex | IPDS | MP Smart grid pvt ltd | Utility | 7760 | 62700 | - | 15000 | 11296 | 51404 | 5691 | 45713
| Madhya Pradesh | MP-West | 6 Towns |  | 4537 | - | 4537 |  | Capex+Opex | Utility Owned | MP Smart grid pvt ltd | Utility | - | - | - | - | -
| Madhya Pradesh | MP-West | Indore | Completed | 120036 | 1200 | 120036 |  | Capex | IPDS | LnT | Utility | - | 118836 | 1200 | - | 0 | 118836 | 0 | 118836
14 | Odisha | OPTCL | Across Odisha | Completed | 4000 | - | 4000 |  | BOOT | Utility Owned | JnJ | Utility | - | 4000 | - | - | 0 | 4000 | 0 | 4000
15 | Puducherry | PED | Puducherry | Completed | 28910 | - | 28910 |  | Capex | SG Pilot | Dongfang Electronics | Utility | - | 28910 | - | - | 0 | 28910 | 0 | 28910
| Puducherry | PED | Puducherry | Completed | 1658 | - | 1658 |  | Capex | Utility Owned | Multiple Vendors | Utility | - | 1658 | - | - | 0 | 1658 | 0 | 1658
16 | Punjab | PSPCL | Ludhiana | Dec'21. Due to Covid, utilities have requested for further time extension. | 96000 | - | 96000 |  | Capex | IPDS |  | Utility | 44120 | 9836 | - | 15000 | 2433 | 7403 | 4803 | 2600
17 | Rajasthan | AVVNL | 66 Towns | Dec'21 | 190822 | - | 190822 |  | Opex | IPDS |  | EESL | 20214 | 23029 | - | 29244 | 6302 | 16727 | 9984 | 6743
| Rajasthan | JdVVNL | Jodhpur |  | 102182 | - | 102182 |  | Opex | IPDS |  | EESL | 20214 | 19473 | - | 29244 | 6750 | 12723 | 5397 | 7326
| Rajasthan | AVVNL | Ajmer | Completed | 1000 | - | 1000 |  | Capex | Utility Owned | Radius, JnJ | Utility | - | 1000 | - | - | 0 | 1000 | 0 | 1000
| Rajasthan | JaVVNL | Jaipur and Tonk | Dec'21. Due to Covid, utilities have requested for further time extension. | 281800 | - | 281800 |  | Capex | IPDS | Genus | Utility | 40235 | 77765 | - | 45000 | 19371 | 58394 | 12745 | 45649
| Rajasthan | JaVVNL | 6 Towns | 2022-03-01 | 150000 | - | 150000 |  | Hybrid | NSGM | Genus | Utility | 58542 | 42458 | - | 16000 | 11814 | 30644 | 6969 | 23675
| Rajasthan | JaVVNL | Kota | Completed | 70000 | - | 70000 |  | Capex | Utility Owned | Genus | Utility | - | 70000 | - | - | 0 | 70000 | 0 | 70000
18 | Tamil Nadu | TANGEDCO | Chennai | 28-Aug-21 and AMC for 7yrs | 141000 | - | 141000 |  | Capex | Utility Owned | Genus | Utility | 20461 | 24539 | - | 8000 | 3600 | 20939 | 8535 | 12404
19 | Tripura | TSECL | Agartala | Completed | 43081 | - | 43081 |  | Capex | SG Pilot | Wipro | Utility | - | 43081 | - | - | 0 | 43081 | 0 | 43081
20 | Telangana | TSSPDCL | Jeedimetla | Completed | 8882 | - | 8882 |  | Capex | SG Pilot | ECIL | Utility | - | 8882 | - | - | 0 | 8882 | 0 | 8882
21 | Uttar Pradesh | IITK | Kanpur | Completed | 28 | - | 28 |  | Capex | SG Pilot | Synergy SS | Utility | - | 28 | - | - | 0 | 28 | 0 | 28
| Uttar Pradesh | MVVNL | Lucknow | MI on Hold currently | 905769 | - | 905769 |  | Opex | Utility Owned | ITI, Genus, Zen Keonics - LnT (SI) | EESL | 26622 | 375849 | 3337 | 0 | 0 | 375849 | 0 | 375849
| Uttar Pradesh | PVVNL | Meerut |  | 1164138 | - | 1164138 |  | Opex | Utility Owned | ITI, Genus, Zen Keonics - LnT (SI) | EESL | 26622 | 198422 | 20 | 0 | 0 | 198422 | 0 | 198422
| Uttar Pradesh | DVVNL | Agra |  | 628686 | - | 628686 |  | Opex | Utility Owned | ITI, Genus, Zen Keonics - LnT (SI) | EESL | 26622 | 147460 | 127 | 0 | 0 | 147460 | 0 | 147460
| Uttar Pradesh | PuVVNL | Varanasi |  | 1147102 | - | 1147102 |  | Opex | Utility Owned | ITI, Genus, Zen Keonics - LnT (SI) | EESL | 26622 | 319946 | 1135 | 0 | 0 | 319946 | 0 | 319946
| Uttar Pradesh | KESCO | Kanpur |  | 156532 | - | 156532 |  | Opex | Utility Owned | ITI, Genus, Zen Keonics - LnT (SI) | EESL | 26625 | 106233 | 60266 | 0 | 0 | 106233 | 0 | 106233
22 | West Bengal | WBSEDCL | Siliguri | Completed | 5164 | - | 5164 |  | Capex | SG Pilot | Chemtrols | Utility | - | 5164 | - | - | 0 | 5164 | 0 | 5164
| West Bengal | CESC | Kolkata | Completed | 10000 | - | 10000 |  | Capex | Utility Owned | Genus, Secure | Utility | - | 10000 | - | - | 0 | 10000 | 0 | 10000
| Grand Total |  |  |  | 11162544 | 2502940 | 9998444 | [5 empty] | 543596 | 2729472 | 278342 | 283588 | 118822 | 2610650 | 104090 | 2506560

## Project Cost Details (hidden)
Monthly report for monitoring implementation of smart meters in the country (Status as on last date of a month to be submitted by 5th of ensuing month)
Part A: Details of Smart meter projects | [15 empty] | Part A1: Consumer metering in DISCOMs
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 14 | 15 | 16
S No. | State | Utility | Project Area(s) | Project Scope (Covers Smart Meters/ HES/ MDM) | Project Status (Completed/Ongoing/Tendered/Proposed) | Nos. of Smart Meters Sanctioned |  |  |  | Project Cost |  |  | Business Model (Capex/Opex/Hybrid) | Scheme under which it is funded (Revamped/ IPDS/ NSGM/ Own) | Implementation Agency | Total Nos. of metered consumers in the utility as on date | Nos. of metered consumers in the utility which are of type Smart meter/Smart prepaid | Nos. of metered consumers in the utility which are of type Simple prepaid
[6 empty] | @Consumer level |  | @DT Level | @Feeder Level | CAPEX | OPEX
[6 empty] | of Smart type | of Smart Prepaid type |  |  |  | Cost/meter/month (Rs.) | Contract Period (Months)
1 | Andaman | EDANI | Aberdeen Bazar, Bambooflat, Chakkargaon, Chouldari, Dairy Farm, Ferrargunj, Haddo, Manglutan, Phoneix Bay, Prem Nagar, Prothrapur, Shadipur, Sippighat, Wimberligunj | All above | On Going | 76000 |  |  |  |  | 29 | 96 | Opex | IPDS | BOSCH
2 | Assam | APDCL | Guwahati and Dibrugarh | All above | Completed | 70000 |  |  |  | Rs. 57.74 Crs |  |  | Capex | Utility owned | Anvil Cables & Sinhal Udyog
|  | APDCL | Guwahati | All above | Completed | 14259 |  |  |  | Rs. 19.16 Crs |  |  | Capex | SG Pilot | Fluent Grid
|  | APDCL | Selected areas of Jorhat, Silchar and Guwahati Town | All above | Ongoing | 134000 |  |  |  | Rs. 108.93 Crs |  |  | Capex | UDAY | M/s Anvil Cables Pvt Ltd consortium with M/s Sinhal Udyog
|  | APDCL | Selected areas of Kokrajhar, Goalpara, Nalbari and Guwahati Town | All above | Ongoing | 134000 |  |  |  | Rs. 113.90 Crs |  |  | Capex | UDAY | M/s Purbanchal Enterprise (Meter Make: Landis Gyr)
3 | Bihar | NBPDCL | Motihari, Barauni, Dalsingsarai, Begusarai, Rosera, Bettiah, Sheohar, Muzaffarpur(W), Mahua, Hazipur,Darbhanga(R), Katihar, Supaul, Samastipur, Muzaffarpur(U-I), Ishanganj, Gopalganj, Madhubani, Siwan, Saharsa, Purnea, Forbisganj, Purnea (East), Madhepura, Jhanjharpur, Muzaffarpur(E), Sitamarhi, Khagaria, Chapra(W), Chapra(E), Bagha, Raxaul, Muzaffarpur(U-Ii), Bhagalpur(U), Patna, Gaya(U), Khagaul, Arwal, Bhagalpur(E), Bihta, Buxar, Biharsarif, Rajgir, Ekangarsarai, Jagdishpur, Nawada, Rajauli, Dehrionsone, Aurangabad, Banka, Barh, Bhabhua, Dakbanglow (Poc), Daudnagar, Gaya(R), Sherghati, Jahanabad, Jamui, Lakhisarai, Manpur, Amarpur, Naugachia, Munger, Patna Rural (Poc), Sasaram, Arrah, Masaurhi, Fatuha | All above | On Going | 10,30,000 | 10,30,000 | 0 | 0 | NA | 77.2 | 96 | Opex | IPDS | EDF | 10322630 | 68556 | 2505
|  | SBPDCL |  | All above | On Going | 13,20,000 | 13,20,000 | 0 | 0 | NA | 77.2 | 96 | Opex | IPDS | EDF | 5955560 | 71631 | 6517
4 | Chandigarh | CED | Chandigarh (Sub Div-5) | All above | On Going | 29433 |  |  |  | Rs. 28.58 Crs |  |  | Capex | NSGM | Genus, Synergy Signals & Systems
5 | Delhi | NDMC | New Delhi Area | All above | On Going | 64713 |  |  |  |  | 83.84 | 66 | Opex | IPDS | L&T
|  | TPDDL | North Delhi | All above | Completed | 1,95,000 | [7 empty] | Utility owned | Landis + Gyr
6 | Gujarat | UGVCL | Naroda | All above | Completed | 23760 |  |  |  | Rs. 23.18 Crs |  |  | Capex | SG Pilot | Genus
7 | Haryana | UHBVN | Panipat | All above | Completed | 10188 |  |  |  | NA |  |  | Capex | SG Pilot | NEDO
|  | DHBVN | Gurugram, Faridabad, Karnal, Panipat, Gharaunda, Panchkula, Kalka, Pinjore | All above | On Going | 5,00,000 |  |  |  |  | 86.98 | 96 | Opex | IPDS | L&T
|  | UHBVN |  | All above | On Going | 5,00,000 |  |  |  |  | 86.98 | 96 | Opex | IPDS | L&T
8 | Himanchal Pradesh | HPSEB | Kala Amb | All above | Completed | 1335 |  |  |  | Rs. 19.44 Crs |  |  | Capex | SG Pilot | GE T&D
|  | HPSEB | Shimla & Dhramshala |  | Under Award | 135716
9 | J&K | JKPDD | Jammu & Srinagar |  |  | 200000 | [6 empty] | Opex | Utility owned | Techno Electric
10 | Karnataka | CESC | Mysore | All above | Completed | 20916 |  |  |  | Rs. 32.56 Crs |  |  | Capex | SG Pilot | Enzen Global
11 | Kerala | CPT |  | All above | Completed | 800 | [6 empty] | Capex | IPDS ST&D
12 | MP | MP-West | Dewas, Ujjain, Ratlam, Mhow, Khargone | All above | Ongoing | 3,44,540 | 5460 |  |  | Rs. 123.90 Crs. | Rs. 135.87 Crs. (Rs. 64.70 per node per month) | 30 (implementation)+ 60 (O&M) | Capex+Opex | IPDS | MP Smart grid pvt ltd
|  | MP-West | Indore city | All above | Completed | 1,18,836 | 1200 |  |  | Rs. 59.34 Crs. | Rs.15.62 Crs. (Rs. 78.10 Lakhs per quarter) | 24 (implementation)+ 60 (O&M) | Capex | IPDS ST&D | L&T
13 | Odisha | OPTCL | Across Odisha | All above | Completed | 4000 | [7 empty] | Utility owned | JnJ
14 | Puducherry | PED | Puducherry | All above | Completed | 28910 |  |  |  | Rs. 35.43 Crs |  |  | Capex | SG Pilot | Dongfang Electronics
|  | PED | Puducherry | All above | Completed | 1658 | [7 empty] | Utility owned | Multiple Vendors
15 | Punjab | PSPCL | Punjab | All above | Ongoing | 96000 |  |  |  | Rs. 50.99 Crs | Rs.19.80 Crs (Rs. 99 Lakhs per quarter) | 12 (implementation)+ 60 (O&M) | Capex | IPDS | PSPCL and HPL
16 | Rajasthan | AVVNL | Makarana and Pushkar | All above | On Going | 1,90,822 |  |  |  |  | 64 | 120 | Opex | IPDS | BOSCH
|  | AVVNL | Satguru Colony, Ajmer | All above | Completed | 1000 | [7 empty] | Utility owned | Radius, JnJ
|  | JaVVNL | Jaipur City and Tonk Circle | All above | On Going | 2,81,800 |  |  |  | Rs. 149.95 Crs. | Rs. 43.79 Crs. (Rs. 2.19 Crs per quarter) | 12 (implementation) + 60 (O&M) | Capex | IPDS | Genus Power (GPIL)
|  | JaVVNL | Urban consumers on Baran, Bundi, Bharatpur, Jhalawar, Karauli, Dholpur Circles | All above | On Going | 1,50,000 |  | NA | NA | Rs. 87.43 Crs. | 45.3 | 60 months | Hybrid | NSGM | Genus
|  | JaVVNL | Kota | All above | Completed | 70000 | [6 empty] | Capex | Utility owned | Genus
|  | JdVVNL | Jodhpur | All above | On Going | 1,02,182 |  |  |  |  | 64 | 120 | Opex | IPDS | BOSCH
17 | Tamil Nadu | TANGEDCO | Chennai (MoU with Smart Cities) | All above | On Going | 1,41,000 | [6 empty] | Capex | Utility owned | Genus
18 | Telangana | TSSPDCL | Jeedimetla | All above | Completed | 8882 |  |  |  | Rs. 34.93 Crs |  |  | Capex | SG Pilot | ECIL
19 | Tripura | TSECL | Aragtala | All above | Completed | 43081 |  |  |  | Rs. 63.43 Crs |  |  | Capex | SG Pilot | Wipro
20 | Uttar Pradesh | IITK | IIT Kanpur Campus | All above | Completed | 28 |  |  |  | Rs. 11.39 Crs |  |  | Capex | SG Pilot
|  | MVVNL | Prayagraj, Azamgarh, Barabanki, Faizabad, Farrukhabad, Gonda, Gorakhpur, Hardoi, Jhansi, Jaunpur, Lucknow, Mirzapur, Orai, Raibareilly, Sahjahanpur, Sultanpur, Unnao, Varanasi, Mughalsarai, Aligarh, Bareilly, Bulandshahar, Etawah, Mainpuri, Moradabad, Meerut, Mathura, Muzaffarnagar, Rampur, Saharanpur, Vrindavan, Firozabad, Hapur, Loni, Sikandrabad, Modinagar, Muradnagar, Khurja, Amroha, Kanpur | All above | On Going | 9,05,769 |  |  |  |  | 85.95 | 96 | Opex | IPDS | L&T
|  | PVVNL |  | All above | On Going | 11,64,138 |  |  |  |  | 85.95 | 96 | Opex | IPDS | L&T
|  | DVVNL |  | All above | On Going | 6,26,861 |  | 1825 |  |  | 85.95 | 96 | Opex | Utility owned | EESL | 5355248 | 145905 | 17430
|  | PuVVNL |  | All above | On Going | 11,47,102 |  |  |  |  | 85.95 | 96 | Opex | IPDS | L&T
|  | KESCO |  | All above | On Going | 1,56,532 |  |  |  |  | 85.95 | 96 | Opex | IPDS | L&T
21 | West Bengal | WBSEDCL | Siliguri | All above | Completed | 5164 |  |  |  | Rs. 6.95 Crs |  |  | Capex | SG Pilot | Chemtrols
|  | CESC | Kolkata | All above | Completed | 10000 | [7 empty] | Utility owned | Genus & Secure
| Total |  |  |  |  | 97,22,719 | 23,56,660 | 1825 | [7 empty] | 2,16,33,438 | 2,86,092 | 26452

## State-wise data (hidden)
Already Completed Projects
Deployment Completed
Sl | State | Utility | Project Area(s) | Scheme | Implementation Agency | Consumers / Nodes | Statewise Totals | Business Model | No. of Prepaid Meters
1 | Andaman & Nicobar | Dept. of Power | Andman | IPDS (Awarded to EESL) | BOSCH | 50390 | 50390 | OPEX
2 | Assam | APDCL | Guwahati and Dibrugarh | Utility owned | M/s Anvil Cables & Sinhal Udyog | 70000 | 101761 | CAPEX
|  | APDCL | Guwahati | SG Pilot | Fluent Grid | 14259 |  | CAPEX
|  | APDCL | Jorhat, Silchar & Guwahati | Utility owned | M/s Anvil Cables & Sinhal Udyog | 17502 |  | CAPEX
3 | Bihar | NBPDCL, SBPDCL | 130 towns | IPDS Smart Metering * | EDF & Genus | 147763 | 147763 | OPEX | 143947
4 | Chandigarh | CED | Chandigarh (Sub Div-5) | NSGM | Genus, Synergy Signals & Systems | 8958 | 8958 | CAPEX
5 | Delhi | TPDDL | North Delhi | Utility owned | Landis + Gyr | 195000 | 255270
|  | NDMC | NDMC Area | Utility owned * | L&T & Genus | 60270 |  | OPEX
6 | Gujarat | UGVCL | Naroda | SG Pilot | Genus | 23760 | 23760 | CAPEX
7 | Haryana | UHBVN | Panipat | SG Pilot | NEDO | 10188 | 280961 | CAPEX | 122
|  | DHBVN, UHBVN | Gurugram, Karnal, Panipat, Panchkula | Utility owned * | ITI, Genus, Zen, Keonics - L&T (SI) | 270773 |  | OPEX
8 | Himanchal Pradesh | HPSEB | Kala Amb | SG Pilot | GE T&D | 1335 | 1335 | CAPEX
9 | Karnataka | CESC | Mysore | SG Pilot | Enzen Global | 20916 | 20916 | CAPEX
10 | Kerala | CPT | Cochin port area | IPDS ST&D | Nsoft India Service | 780 | 780
11 | Madhya Pradesh | MPWZ | 5 towns (Dewas, Ujjain, Ratlam, Mhow, Khargone) | IPDS-Smart Metering |  | 38139 | 156975 | OPEX
|  | MPWZ | Indore | IPDS-ST&D | L&T | 118836
12 | Odisha | OPTCL | Across Odisha | Utility owned | JnJ | 4000 | 4000
13 | Puducherry | PED | Puducherry | SG Pilot | Dongfang Electronics | 28910 | 30568 | CAPEX
|  | PED | Puducherry | Utility owned $ | Multiple Vendors | 1658
14 | Punjab | PSPCL | Punjab | IPDS Smart Metering |  | 887 | 887 | CAPEX
15 | Rajasthan | JVVNL | Kota | Utility owned | Genus | 70000 | 136435
|  | JVVNL | Jaipur & Tonk | IPDS Smart Metering | Genus | 38220 |  | OPEX
|  | AjVVNL | 66 Towns | IPDS Smart Metering* |  | 2339 |  | OPEX
|  | JVVNL | 6 Towns | NSGM | Genus | 20843 |  | CAPEX
|  | AVVNL | Satguru Colony, Ajmer | Utility owned ^ | Radius, JnJ | 1000
|  | JdVVNL | Jodhpur | IPDS Smart Metering * |  | 4033 |  | OPEX
16 | Tamil Nadu | TANGEDCO | T Nagar, Chennai | Utility owned | Genus | 10359 | 10359 | CAPEX
17 | Telangana | TSSPDCL | Jeedimetla | SG Pilot | ECIL | 8882 | 8882 | CAPEX
18 | Tripura | TSECL | Agartala | SG Pilot | Wipro | 43081 | 43081 | CAPEX
19 | Uttar Pradesh | IIT Kanpur Lab | IIT Kanpur Campus | SG Pilot |  | 28 | 1147938 | CAPEX | 26899
|  | UPPCL | Across UP | Utility owned * | ITI, Genus, Zen Keonics - L&T (SI) | 1147910 |  | OPEX
20 | West Bengal | WBSEDCL | Siliguri | SG Pilot | Chemtrols | 5164 | 15164 | CAPEX
|  | CESC | Kolkata, WB | Utility owned | Genus & Secure | 10000
| Total |  |  |  |  | 2446183 | 2446183
| * MoU with EESL |  | $ MoU with POWERGRID |  | ^ MoU with USAID
Ongoing Projects
Sl | State | Utility | Project Area(s) | Scheme | Implementation Agency | Consumers / Nodes | Statewise Totals | Business Model | No. of Prepaid Meters
1 | Andaman & Nicobar | Dept. of Power | Andman | IPDS (Awarded to EESL) | BOSCH | 25610 | 25610 | OPEX
2 | Assam | APDCL | Jorhat, Silchar and Guwahati Town | Utility owned | M/s Anvil Cables & Sinhal Udyog | 116498 | 250498 | CAPEX
|  | APDCL | Kokrajhar, Goalpara, Nalbari and Guwahati Town | Utility owned | M/s Purbanchal Enterprise (Meter Make: Landis Gyr) | 134000 |  | CAPEX
3 | Bihar | NBPDCL, SBPDCL | 130 towns | IPDS Smart Metering* | EDF & Genus | 2202237 | 2202237 | OPEX
4 | Chandigarh | CED | Chandigarh (Sub Div-5) | NSGM | Genus, Synergy Signals & Systems | 20475 | 20475 | CAPEX
5 | Delhi | NDMC | NDMC Area | Utility owned * | L&T & Genus | 4443 | 4443 | OPEX
6 | Haryana | DHBVN, UHBVN | Gurugram, Karnal, Panipat, Panchkula | Utility owned * | L&T, ITI, Genus, Zen, Keonics | 729227 | 729227 | OPEX
7 | J&K | JKPDD | Jammu & Srinagar | Utility owned $ | Techno Electric | 200000 | 200000 | OPEX
8 | Madhya Pradesh | MPWZ | 5 towns (Dewas, Ujjain, Ratlam, Mhow, Khargone) | IPDS Smart Metering | Indian Power Corporation Ltd. | 311861 | 311861 | OPEX
9 | Punjab | PSPCL | Punjab | IPDS Smart Metering | HPL | 95113 | 95113 | OPEX
10 | Rajasthan | JVVNL | Jaipur & Tonk | IPDS Smart Metering | Genus | 243580 | 659369 | OPEX
|  | JVVNL | 6 Towns | NSGM | Genus | 129157 |  | CAPEX
|  | AjVVNL | 66 Towns | IPDS Smart Metering* |  | 188483 |  | OPEX
|  | JdVVNL | Jodhpur | IPDS Smart Metering* |  | 98149 |  | OPEX
11 | Tamil Nadu | TANGEDCO | T Nagar, Chennai | Utility owned | Genus | 130641 | 130641 | CAPEX
12 | Uttar Pradesh | UPPCL | Across UP | Utility owned * | L&T, ITI, Genus, Zen, Keonics | 2854317 | 2854317 | OPEX
| Total |  |  |  |  | 7483791 | 7483791
| * MoU with EESL |  | $ MoU with RECPDCL

## EESLNSGM project Status (hidden)
SI No. | State | Utility | Project Area | Smart Meter sanctioned | Smart Meter awarded | Smart Meter Installed | Ongoing | Completion timeline | Months left till Completion | Required Target per month (In Jan'22) till 07.01.2022 | Required Target per week | EESL Jan'22 Target | EESL Jan'22 weekly target | Shortfall in Monthly Target | Shortfall in WeeklyTarget | Remarks | 1st week | 2nd week | 3rd week | 4th Week
1 | Haryana | DHBVN | Gurugram, Faridabad, Karnal, Panipat, Gharaunda, Panchkula, Kalka, Pinjore | 500000 | 500000 | 242521 | 257479 | 2022-07-01 | 7 | 50329.7143 | 12582.4286 | 31000 | 7750 | 19329.7143 | 4832.4286 | As per EESL Target July 2022 = 83333 | 6129 | 5222 | 4708 | 5150
|  | UHBVN |  | 500000 | 500000 | 405171 | 94829
2 | Andaman | EDANI | Andaman | 75200 | 75200 | 75200 | 0 | 2021-12-01 | 1 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | Completion timeline is granted till December 2021 for all projects being implemented under IPDS. Due to 2nd wave of Covid utilities have requested for further time extension. | 663 | 2124 | 201 | 455
3 | Bihar | NBPDCL | 72 nos. IPDS Town | #REF! | #REF! | 582514 | #REF! | 2022-12-01 | 12 | #REF! | #REF! | 60000 | 15000 | #REF! | #REF! |  | 14880 | 12674 | 5101 | 12482
|  | SBPDCL | 58 nos. IPDS Town | 1320000 | 1320000 | #REF! | #REF!
4 | Rajasthan | AVVNL | 66 Towns | 122149 | 122149 | 68673 | 53476 | 2021-12-01 | 1 | #REF! | #REF! | 0 | 0 | #REF! | #REF! |  | 2183 | 1407 | 2778 | 2840
|  | JdVVNL | Jodhpur | 46155 | 46155 | #REF! | #REF!
5 | Delhi | NDMC | NDMC Area | 64713 | 64713 | 65059 | -346 | Completed | [7 empty] | NDMC has already been saturated. The remaining meters are for new service connections
6 | Uttar Pradesh | MVVNL | Lucknow | 905769 | 905769 | 380731 | 525038 | MI on Hold currently
|  | PVVNL | Meerut | 1164138 | 1164138 | 198726 | 965412
|  | DVVNL | Agra | 628686 | 628686 | 147991 | 480695
|  | PuVVNL | Varanasi | 1147102 | 1147102 | 321433 | 825669
|  | KESCO | Kanpur | 156532 | 156532 | 134727 | 21805
[6 empty] | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[6 empty] | 2855608 | #REF!
NSGM Projects Status
SI No. | State | Utility | Project Area | Smart Meter sanctioned | Smart Meter awarded | Smart Meter Installed | Ongoing | Completion timeline | Months left till Completion | Required Target per month (In Dec'21) | Required Target per week | Utility Nov'21 Target | Utility Dec'21 weekly target | Shortfall in Monthly Target | Shortfall in WeeklyTarget | Remarks | 1st week | 2nd week | 3rd week | 4th Week
1 | Chandigarh | CED | SD-5 | 29443 | 29443 | 24214 | 5229 | Dec'21 | 1 | 5229 | 1307.25 | 0 | 0 | 5229 | 1307.25 | RECPDCL submitted completion timeline in weekly shared smart metering status til Dec'21 | 556 | 474 | 676 | 602
2 | Rajasthan | JVVNL | 6 towns | 150000 | 150000 | 135944 | 14056 | March'22 | 3 | 4685.3333 | 1171.3333 | 2000 | 500 | 2685.3333 | 671.3333 |  | 1374 | 1988 | 1709 | 2052
160158